## EVMS Metrics Tracker
Active Metrics - purpose is to show the current list of metrics that have been approved for use by the DCMA EVMS Group Configuration Control Board (CCB) | [15 empty] | METRIC RESULTS
Test Metric Count | Unique Test Metric ID | Changed? (Aug 2025) | GL | Attribute ID | Current Metric Revision | Test Metric Rev Date | Test Definition | Test Metric Numerator (X) | Test Metric Denominator (Y) | Metric Threshold | Artifacts | Test Type | Sample Required | Priority | Revision Comments | Test Metric Numerator (X) | Test Metric Denominator (Y) | Result (X/Y) or (X) | OOT/NoOOT | Notes | If "OOT", Exception Okay?
1 | 01A101b | No | 01 | 01A1 | V8.0 | 2024-12-06 | Is there a single product-oriented WBS? | X = Occurrence of a WBS that is not product-oriented | n/a | X = 0 | 03, 20, 38, 46 | M | No | Low | V8.0: No Changes V7.0: Global 508 Formatting, Update assumptions and instructions V6.0: Updated to include IPMDAR V5.0: No Changes V4.0: Updated assumptions and Instructions V3.6: Updated Instructions V3.5: No Changes v3.4: Update Attribute V3.3: No Changes V3.1: Removed Block 4 (Frequency) Pilot: New metric to test there is a single product oriented WBS (split from 101a)
2 | 01A201a | No | 01 | 01A2 | V8.0 | 2024-12-06 | Are contract work scope (SOW) requirements included in the WBS? | X = Count of sampled SOW paragraphs identifying scope that are not in the WBS | Y = Total count of sampled SOW paragraphs identifying scope | X/Y = 0% | 04, 05, 06, 09, 38, 59 | M | Yes | Standard | V8.0: No Changes V7.0: Global 508 Formatting, No changes V6.0: Global formatting and Assumptions V5.0: Updated Assumptions and Instructions V4.0: Updated Data Elements, Assumptions, and Instructions V3.6: No Changes V3.5: No Changes V3.4: No Changes V3.3: No Changes V3.1: Removed Block 4 (Frequency) Pilot: Changed to annual max, added sampling, changed threshold to 0.
3 | 02A101a | No | 02 | 02A1 | V8.0 | 2024-12-06 | Is there a single OBS used on the contract? | X = Count of mismatches between the program organizational breakdown structure (OBS) and IPMR/CPR Format 2 or IPMDAR CPD | n/a | X = 0 | 07, 20 | M | No | Standard | V8.0: No Changes V7.0: Global 508 Formatting, No changes V6.0: Updated to include IPMDAR V5.0: No Changes V4.0: Updated Instructions V3.6: No Changes V3.5: No Changes v3.4: Update Attribute V3.3: No Changes V3.1: Removed Block 4 (Frequency)
4 | 02A102a | No | 02 | 02A1 | V8.0 | 2024-12-06 | Are all major subcontractors/suppliers and intra-organizational work with an EVMS DFARS clause flow down requirement included in the OBS reporting requirements in Format 2? | X = Count of major subcontractors/suppliers and intra-organizational elements with an EVMS DFARS clause flow down requirement not identified in the OBS reporting requirements in Format 2 or CPD | Y = Total count of major subcontractors/suppliers and intra-organizational elements with an EVMS DFARS clause flow down requirement | X/Y = 0% | 06, 20, 21 | M | No | Low | V8.0: No Changes V7.0: Global 508 Formatting, No changes V6.0: Updated to include IPMDAR V5.0: No Changes V4.0: Updated Test Definition, Test Metric, Data Elements Required, and Instructions V3.6: No Changes V3.5: No Changes v3.4: Update Attribute V3.3: No Changes V3.1: Removed Block 4 (Frequency) Pilot: Changed threshold to 0.
5 | 03A101h | No | 03 | 03A1 | V8.0 | 2024-12-06 | Is control account data traceable between the system artifacts including schedule, cost data, and work authorization documents? • Does the OBS align between the IMS and EV Cost Tool? | X = Count of incomplete CAs where IMS OBS does not match EV Cost Tool OBS, or there are more than one IMS OBS assigned, or no IMS OBS assigned. | Y = Total count of incomplete CAs in the IMS | X/Y ≤ 5% | 11, 13, 44, 45, 59 | A | No | Conditional | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements, Assumptions and Instructions V3.6.1: Admin update to Test Step, Test Metric, Instructions; Update Assumptions. V3.6: No Changes V3.5: Update Test Metric and Assumptions v3.4: Update: Attribute and Metric Threshold V3.3: Removed Data Elements, removed unnecessary Assumption & added incomplete Assumption V3.2: Minor Updates to Data Elements, Assumptions & Instructions V3.1: Removed Block 4 (Frequency)
6 | 03A101i | No | 03 | 03A1 | V8.0 | 2024-12-06 | Is control account data traceable between system artifacts including schedule, cost data, and work authorization documents? • Does the WBS align between the IMS and EV Cost Tool? | X = Count of incomplete CAs where IMS WBS does not match EV Cost Tool WBS, or there are more than one IMS WBS assigned, or no IMS WBS assigned. | Y = Total count of incomplete CAs in the IMS | X/Y ≤ 5% | 11, 13, 44, 45 | A | No | Low | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required and Instructions V3.6.1: Update Assumptions; Admin update to Instructions. V3.6: No Changes V3.5: Update Test Metrics and Assumptions V3.4: No Changes V3.3: Removed Data Elements, removed unnecessary Assumption & added incomplete Assumption V3.2: Added Actual Finish Date in Data Elements, added IMS incomplete assumption V3.1: Removed Block 4 (Frequency) Pilot: Threshold change to ≤ 5%
7 | 04A101a | No | 04 | 04A1 | V8.0 | 2024-12-06 | Has an organizational authority been established for indirect cost management? | X = Count of the functions/positions identified within the EVMSD that do not correspond with the functions/positions responsible for approval and control of indirect costs found in the organizational chart(s) or any other company documentation | n/a | X = 0 | 03, 39 | M | No | Low | V8.0: No Changes V7.0: Global 508 Formatting, No changes V6.0: Global update to layout and assumptions V5.0: Updated Data Elements, Assumptions, and Instructions V4.0: Updated Instructions V3.6: No Changes V3.5: No Changes v3.4: Update Attribute V3.3: No Changes V3.2: Updated Assumptions and Instructions V3.1: Removed Block 4 (Frequency) Pilot: Clarified test as evaluating pools against disclosure statement; test not required if Disclosure Statement has been approved.
8 | 05A101a | No | 05 | 05A1 | V8.0 | 2024-12-06 | Does each control account have exactly one responsible organizational element assigned? | X = Count of CAs with more than one OBS element or no OBS elements assigned | Y = Total count of CAs | X/Y = 0% | 07, 13, 44 | A | No | Low | V8.0: No Changes V7.0: Global 508 Formatting, No changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: Update Assumptions and Instructions v3.4: Update Attribute V3.3: No Changes V3.1: Minor changes, removed frequency Pilot: Changed to exactly on OBS; threshold at 0; removed attribute 02A1
9 | 05A102a | No | 05 | 05A1 | V8.0 | 2024-12-06 | Is each control account assigned to a single Control Account Manager (CAM)? | X = Count of CAs that have more than one CAM or no CAM assigned | Y = Total count of CAs | X/Y ≤ 5% | 13, 44, 59 | A | No | Low | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: Update Instructions v3.4: Update Attribute V3.3: No Changes V3.1: Removed Block 4 (Frequency) Pilot: Changed to exactly on CAM
10 | 05A103a | No | 05 | 05A1 | V8.0 | 2024-12-06 | Does each control account have exactly one WBS element assigned? | X = Count of CAs with more than one WBS element or no WBS elements assigned | Y = Total count of CAs | X/Y = 0% | 13, 44 | A | No | Low | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: Update Instructions v3.4: Update Attribute V3.3: No Changes V3.1: Removed Block 4 (Frequency) Pilot: Changed to exactly on WBS; threshold at 0
11 | 06A101a | Yes | 06 | 06A1 | V8.0 | 2025-08-21 | Does each non-LOE unique WP, PP, SLPP have task(s) represented in both the IMS and EV Cost Tool? | X = Count of all PPs/SLPPs and incomplete non-LOE WPs in the EV Cost Tool that are not in the IMS and count of incomplete non-LOE WPs, PPs, SLPPs in the IMS that are not in the EV Cost Tool | Y = Total count of all unique PP and SLPP, and incomplete, non-LOE WPs in the EV Cost Tool or the IMS | X/Y = 0% | 03, 11, 13, 44, 45 | A | No | Standard | V8.0: Updated to clarify all SLPP and PP are included V7.0: Global 508 Formatting, Update Test Definition, Test Metric, Data Elements Required, Assumptions, and Instructions V6.0: Global formatting and Assumptions V5.0: Updated Assumptions and Instructions V4.0: Updated Test Definition, Data Elements Required, Assumptions, and Instructions V3.6.1: Update to Assumptions. Minor update to Test Metric & Instructions. V3.6: Update Test Step, Data Elements, Assumptions, and Instructions V3.5: No Changes v3.4: Update Attribute V3.3: Added necessary Data Elements and Test Metric/Instruction language V3.1: Defining incomplete WPs, PPs, and SLPPs in IMS as no actual finish date, Removed Block 4 (Frequency) Pilot: Added SLPPs to metric
12 | 06A102a | No | 06 | 06A1 | V8.0 | 2024-12-06 | Are authorized risk mitigation activities incorporated into the IMS as required by the process instructions? | X = Count of risk mitigation activities not in the IMS | Y = Total count of risk mitigation activities | X/Y ≤ 10% | 03, 11, 28, 45, 62 | M | No | Standard | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Updated Data Elements V5.0: No Changes V4.0: Updated Data Elements Required and Instructions V3.6: No Changes V3.5: No Changes v3.4: Update Attribute V3.3: No Changes V3.1: Removed Block 4 (Frequency) Pilot: Attribute changed to A1 - renumbered from 06A503a
13 | 06A204b | No | 06 | 06A2 | V8.0 | 2024-12-06 | Are there open starts or finishes (“dangling logic”) in the schedule? | X = Count of incomplete Non-LOE tasks/activities & milestones with open starts or finishes | Y = Total count of incomplete Non-LOE tasks/activities & milestones | X/Y = 0% | 11, 45 | A | No | Standard | V8.0: No Changes V7.0: Global 508 Formatting, No Change V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Assumptions, Data Elements Required and Instructions V3.6: Update Data Elements and Assumptions V3.5: Update Assumptions and Instructions v3.4: Update: Attribute, Assumptions, and Instructions V3.3: Updated “discrete” to “Non-LOE” in Blocks 7 & 12 V3.2: Reworded assumptions (open finishes and starts) & specified metric to include only discrete activities V3.1: Defining incomplete WPs, PPs, and SLPPs in IMS as no actual finish date, Removed Block 4 (Frequency) Pilot: New metric to evaluate open finishes (dangling logic)
14 | 06A205a | No | 06 | 06A2 | V8.0 | 2024-12-06 | Are lags used in the schedule? | X = Count of incomplete tasks/activities & milestones with at least one lag in the predecessor logic in the IMS | Y = Total count of incomplete tasks/activities & milestones in the IMS | X/Y ≤ 10% | 11, 45 | A | No | Low | V8.0: No Changes V7.0: Global 508 Formatting, No changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required and Instructions V3.6: No Changes V3.5: Update Assumptions and Instructions v3.4: Update Attribute V3.3: Added Data Element V3.1: Defining incomplete WPs, PPs, and SLPPs in IMS as no actual finish date, Removed Block 4 (Frequency)
15 | 06A208a | No | 06 | 06A2 | V8.0 | 2024-12-06 | Do summary tasks/activities in the schedule have logic applied? | X = Count of summary tasks/activities with logic applied (# predecessors > 0 or # successors > 0) | n/a | X = 0 | 11, 45 | A | No | Low | V8.0: No Changes V7.0: Global 508 Formatting, No changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Test Definition, Test Metric, Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: Update Test Metric, Assumptions, and Instructions v3.4: Update Attribute V3.3: No Changes V3.1: Removed Block 4 (Frequency) Pilot: Threshold changed to 0
16 | 06A209a | Yes | 06 | 06A2 | V8.0 | 2025-08-21 | Are schedule network constraints limited? | X = Count of incomplete tasks/activities & milestones with hard constraints | Y = Total count of incomplete tasks/activities & milestones | X/Y = 0% | 11, 20, 45 | A | No | Low | V8.0: Added Hard Constraint Definitions for IPMDAR SPD V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required and Instructions V3.6: No Changes V3.5: Update Assumptions and Instructions v3.4: Update Attribute V3.3: Added Data Element V3.1: Defining incomplete WPs, PPs, and SLPPs in IMS as no actual finish date, Removed Block 4 (Frequency) Pilot: Updated assumptions for 3 scheduling tools, threshold to 0
17 | 06A210a | No | 06 | 06A2 | V8.0 | 2024-12-06 | Do LOE tasks/activities have discrete successors? | X = Count of incomplete LOE tasks/activities in the IMS with at least one Non-LOE successor | Y = Total count of incomplete LOE tasks/activities in the IMS | X/Y = 0% | 11, 45 | A/M | No | Standard | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Test Type, Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: Update Test Metric v3.4: Update Attribute V3.3: Added Data Element, Updated “discrete” to “Non-LOE”, added Assumption 4 V3.2: Added Assumption 3 V3.1: Changed to Incomplete LOE and updated assumptions, Removed Block 4 (Frequency) Pilot: Changed test to look for successors; added denominator
18 | 06A211a | No | 06 | 06A2 | V8.0 | 2024-12-06 | Is high total float rationale/justification acceptable? | X = Count of high total float non-LOE tasks/activities & milestones sampled with inadequate rationale | Y = Total count of high total float non-LOE tasks/activities & milestones sampled | X/Y ≤ 20% | 11, 45 | M | Yes | Standard | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: Updated Test Definition, Test Metric, and Instructions V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: Update Assumptions v3.4: Update: Attribute, Assumptions, and Instructions V3.3: Added “Non-LOE” language, added 2 Data Elements fixed formatting errors V3.1: Defining incomplete WPs, PPs, and SLPPs in IMS as no actual finish date, Removed Block 4 (Frequency) Pilot: Changed to test from evaluating Total Float to testing Free Float
19 | 06A212a | No | 06 | 06A2 | V8.0 | 2024-12-06 | Are there out of sequence tasks/activities & milestones? | X = Count of out of sequence conditions | n/a | X = 0 | 11, 45 | A | No | Conditional | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required, Assumptions and Instructions V3.6: No Changes V3.5: Update Test Metric and Instructions v3.4: Update: Test Metric, Assumptions, and Instructions V3.3: No Changes V3.1: Improved instruction syntax, Removed Block 4 (Frequency)
20 | 06A301a | No | 06 | 06A3 | V8.0 | 2024-12-06 | Are lower level baseline and forecast dates traceable to the corresponding higher level dates in the IMS? | X = Count of sampled incomplete lower level schedule tasks/activities & milestones that are not traceable to the corresponding IMS baseline and forecast start or finish dates | Y = Total count of sampled incomplete lower level schedule tasks/activities & milestones | X/Y = 0% | 03, 11, 36, 37, 45, 58 | M | Yes | Standard | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: Data Elements, Updated Assumptions, and Instructions V4.0: Updated Test Definition, Test Metric, Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: Update Assumptions v3.4: Update: Attribute, Assumptions, and Instructions V3.3: Added Data Element V3.1: Removed Block 4 (Frequency) Pilot: CCB REVISED 3/23/2017 to account for direction of trace (from lower level schedules to IMS).
21 | 06A301b | No | 06 | 06A3 | V8.0 | 2024-12-06 | Does the IMS baseline finish date align with contractual/CLIN finish (POP) date? | X = Count of IMS baseline dates not in alignment with contractual dates | n/a | X = 0 | 06, 11, 45, 57 | M | No | Standard | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required and Instructions V3.6: No Changes V3.5: No Changes v3.4: Update Attribute V3.3: No Changes V3.1: Removed Block 4 (Frequency) Pilot: Revised attribute to 06A3; added CLIN and milestone dates as options for trace. Old metric ID 07A104a
22 | 06A401a | No | 06 | 06A4 | V8.0 | 2024-12-06 | Does the schedule tool produce a critical path that represents the longest total duration with the least amount of total float? | X = Count of tasks/activities & milestones on the constraint method critical path that are not on the contractor’s critical path | n/a | X = 0 | 11, 12, 45 | M | No | Standard | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: Updated Assumptions and Instructions V4.0: Updated Data Elements Required and Instructions V3.6.1: Update Data Elements Required and Instructions V3.6: No Changes V3.5: No Changes v3.4: Update Attribute V3.3: No Changes V3.1: Revised Process, Removed Block 4 (Frequency) Pilot: Attribute changed to A4 - renumbered from 06A207a
23 | 06A401b | No | 06 | 06A4 | V8.0 | 2024-12-06 | Are key contractual milestones and events identified in the IMS? | X = Count of sampled key contractual milestones and events that are not in the IMS | Y = Total count of sampled key contractual milestones and events | X/Y = 0% | 04, 06, 11, 45 | M | Yes | Low | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required and Instructions V3.6: Update Test Metric V3.5: Update Assumptions v3.4: Update Attribute V3.3: No Changes V3.1: Deleted “Incomplete”, Removed Block 4 (Frequency) Pilot: New metric based on previous 07A101a
24 | 06A501a | No | 06 | 06A5 | V8.0 | 2024-12-06 | In the IMS, do all of the tasks/activities & milestones have baseline start and baseline finish dates? | X = Count of tasks/activities & milestones without baseline dates | Y = Total count of tasks/activities & milestones | X/Y ≤ 5% | 11, 45 | A | No | Low | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: No Changes V3.4: No Changes V3.3: No Changes V3.1: Removed Block 4 (Frequency)
25 | 06A504a | No | 06 | 06A5 | V8.0 | 2024-12-06 | Are actual start dates changed after first reported? | X = Count of tasks/activities & milestones where actual start date does not equal previously reported actual start date | Y = Total count of tasks/activities & milestones with actual start dates | X/Y ≤ 10% | 11, 45 | A | No | Low | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6.1: Updated Assumptions and Instructions V3.6: No Changes V3.5: No Changes V3.4: No Changes V3.3: No Changes V3.2: Updated Data Elements & Assumptions for requiring consecutive months for IMS V3.1: Removed Block 4 (Frequency)
26 | 06A504b | No | 06 | 06A5 | V8.0 | 2024-12-06 | Are actual finish dates changed after first reported? | X = Count of tasks/activities & milestones where actual finish date does not equal previously reported actual finish date | Y = Total count of tasks/activities & milestones with actual finish dates | X/Y ≤ 10% | 11, 45 | A | No | Low | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6.1: Updated Assumptions and Instructions V3.6: No Changes V3.5: No Changes V3.4: No Changes V3.3: No Changes V3.2: Updated Data Elements & Assumptions for requiring consecutive months for IMS V3.1: Removed Block 4 (Frequency)
27 | 06A505a | Yes | 06 | 06A5 | V8.0 | 2025-08-21 | Do all in progress tasks/activities & milestones have actual start dates and do not have an actual finish date? | X = Count of in progress tasks/activities & milestones with no actual start date or an actual finish date | Y = Total count of in progress tasks/activities & milestones | X/Y ≤ 5% | 11, 13, 44, 45 | A | No | Low | V8.0: Updated to include checking for actual finish on in progress work V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: Updated Assumptions V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6.1: Updated Test Step, Test Metric, Data Elements, Assumptions and Instructions V3.6: No Changes V3.5: No Changes V3.4: No Changes V3.3: No Changes V3.1: Removed Block 4 (Frequency)
28 | 06A505b | No | 06 | 06A5 | V8.0 | 2025-08-21 | Do all complete tasks/activities & milestones have actual finish dates? | X = Count of complete tasks/activities & milestones with no actual finish date | Y = Total count of complete tasks/activities & milestones | X/Y ≤ 5% | 11, 13, 45 | A | No | Low | V8.0: No changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: Updated Assumptions V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6.1: Updated Assumptions V3.6: Update Test Step, Test Metric, Data Elements, Assumptions, and Instructions V3.5: No Changes V3.4: No Changes V3.3: No Changes V3.1: Removed Block 4 (Frequency)
29 | 06A506a | No | 06 | 06A5 | V8.0 | 2024-12-06 | Are actual start and actual finish dates valid for all tasks/activities & milestones in the IMS? | X = Count of tasks/activities & milestones with either actual start or actual finish after status date | Y = Total count of tasks/activities & milestones with an actual start date | X/Y ≤ 5% | 11, 45 | A | No | Low | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: No Changes V3.4: No Changes V3.3: Added actual start date specification in instructions V3.1: Removed Block 4 (Frequency) Pilot: Attribute updated to A5 - resulting change in metric ID to 06A506a from 06A201a; threshold at 5%
30 | 06A506b | Yes | 06 | 06A5 | V8.0 | 2025-08-21 | Are forecast start and finish dates representative of the remaining work for all incomplete tasks/activities & milestones in the IMS? | X = Count of incomplete tasks/activities & milestones with either forecast start or forecast finish on or before the status date | n/a | X = 0 | 11, 45 | A | No | Low | V8.0: Updated to include on or before status date V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6: No Changes v3.5.1: Update Test Metric, Assumptions, and Instructions V3.5: Update Test Metric, Assumptions, and Instructions V3.4: No Changes V3.3: Actual Start Date/Finish Date added to Data Elements V3.1: Removed Block 4 (Frequency) Pilot: Attribute updated to A5 - resulting change in metric ID to 06A506b from 06A201b; Red Team proposed revisions incorporated 3/23/2017
31 | 06A506c | No | 06 | 06A5 | V8.0 | 2024-12-06 | Are forecast start/finish dates riding the status date of the IMS for two consecutive months? | X = Count of incomplete tasks/activities & milestones with either forecast start or forecast finish date riding the status date | Y = Total count of incomplete tasks/activities & milestones | X/Y ≤ 1% | 11, 45 | A | No | Standard | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required and Instructions V3.6: No Changes v3.5.1: Update Assumptions V3.5: Update Assumptions and Instructions V3.4: No Changes V3.3: No Changes V3.2: Modified Data Elements to “Two Consecutive Months”, Changed terminology to “Forecast Start/Finish riding the status date” in Instructions V3.1: Minor Changes, Removed Block 4 (Frequency)
32 | 06I101b | Yes | 06 | 06I1 | V8.0 | 2025-08-21 | Do schedule margin tasks/activities represent risk impact to subsequent significant events/milestones? | X = Count of schedule margin tasks/activities that do not represent risk impact to subsequent events/milestone | n/a | X = 0 | 03, 11, 45, 62 | M | No | Standard | V8.0:Updated to include Schedule Margin and task calendar type as data elements. Updated into include instruction 2.e to check if milestone and SM tasks have different calendars. V7.0: Global 508 Formatting, No Changes V6.0: Updated Data Elements V5.0: No Changes V4.0: Updated Test Definition, Attribute number, Test Metric, Data Elements Required, Assumptions, and Instructions V3.6: Update Instructions V3.5: No Changes v3.4: Update: Test Step, Test Metric, and Instructions V3.3: Added Data Element 11E V3.1: New metric approved at NOV2018 CCB
33 | 06I201a | No | 06 | 06I2 | V8.0 | 2024-12-06 | Are Schedule Visibility Tasks (SVTs) identified and controlled in the IMS? | X = Count of incomplete tasks/activities and millstones that are not properly identified and controlled as SVTs in the IMS | n/a | X = 0 | 03, 11, 45 | M | No | Standard | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Assumptions, Attribute number, and Instructions V3.6.1: Updated Data Elements Required, Assumptions, and Instructions. V3.6: Update Test Metric, Data Elements, Assumptions, and Instructions V3.5: No Changes V3.4: No Changes V3.3: Added Data Elements & Assumption 2 V3.1: New metric approved at NOV2018 CCB
34 | 07A102b | No | 07 | 07A1 | V8.0 | 2024-12-06 | Is the IMP traceable to the IMS? | X = Count of IMP criteria that are not represented in the IMS | Y = Total count of IMP criteria | X/Y = 0% | 03, 10, 11, 45 | M | No | Standard | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: Updated Assumptions V4.0: Updated Assumptions and Instructions V3.6: No Changes V3.5: No Changes v3.4: Update Attribute V3.3: No Changes V3.1: Changed to Manual, Removed Block 4 (Frequency) Pilot: Threshold changed to 0
35 | 08A101a | No | 08 | 08A1 | V8.0 | 2024-12-06 | Is the time-phased PMB in alignment with the IMS? | X = Count of sampled incomplete WPs/PPs/SLPPs in the EV Cost Tool where the time-phased budget baseline does not align with the IMS | Y = Total count of sampled incomplete WPs/PPs/SLPPs in the EV Cost Tool | X/Y ≤ 10% | 02, 11, 13, 44, 45 | M | Yes | Standard | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Updated Data Elements, Instructions, and global formatting and Assumptions V5.0: Updated Data Elements V4.0: Updated Test Metric, Data Elements Required, Assumptions, and Instructions V3.6: Update Test Metric, Data Elements, Assumptions, and Instructions V3.5: Update Data Elements and Assumptions v3.4: Update Assumptions V3.3: No Changes V3.1: Revised alternate test for non-resource loaded IMS, Removed Block 4 (Frequency) Pilot: Added assumptions 1 & 2 pertaining to resource loaded IMS and frequency.
36 | 08A103a | Yes | 08 | 08A1 | V8.1 | 2025-08-21 | Is control account data traceable between system artifacts including schedule, cost data, and work authorization documents? • Do the baseline dates in the IMS align with the dates in the EV Cost Tool? | X = Count of incomplete WPs in IMS where POP does not align with EV Cost Tool POP | Y = Total count of incomplete WPs in the IMS | X/Y ≤ 0% | 11, 13, 44, 45 | A | No | Standard | V8.1: Typo correction and included rounding assumption omitted from V8.0 V8.0: Realigned DECM 03A101f from GL03 to GL08. Test Metric ID changed from 03A101f to 08A103a V7.0: Global 508 Formatting, Updated Assumptions V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required and Instructions V3.6.1: Admin update to Test Step, Test Metric, Instructions; Update Assumptions V3.6: No Changes V3.5: Update: Attribute, Assumption v3.4: Update: Attribute, Metric Threshold, Data Elements Required, Assumptions, and Instructions V3.3: No Changes V3.2: Updated Data Elements & Assumptions for BCWS time-phasing V3.1: Updated assumptions, Removed Block 4 (Frequency) Pilot: Removed attribute 08A1, threshold less than equal to 5%
37 | 08A201a | No | 08 | 08A2 | V8.0 | 2024-12-06 | Was customer authorization received before reporting an OTB in the Integrated Program Management Report (IPMR)/Contract Performance Report (CPR)/ Integrated Program Management Data and Analysis Report (IPMDAR)? | X = Occurrences where customer authorization was not received prior to reporting an OTB on IPMR/CPR/IPMDAR | n/a | X = 0 | 20, 25 | M | No | Low | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Updated to include IPMDAR; global formatting and Assumptions V5.0: No Changes V4.0: Updated Instructions V3.6: Update Instructions V3.5: No Changes V3.4: No Changes V3.3: No Changes V3.1: Removed Block 4 (Frequency) Pilot: Modified instructions
38 | 08I101a | No | 08 | 08I1 | V8.0 | 2024-12-06 | Do all SLPPs have duration? | X = Count of SLPPs with baseline duration less than or equal to one day | Y = Total count of SLPPs | X/Y ≤ 10% | 11, 45 | A | No | Low | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required, Attribute number, and Instructions V3.6: No Changes V3.5: Update Test Metric and Instructions V3.4: No Changes V3.3: New metric approved at APR2019 CCB
39 | 08I102a | No | 08 | 08I1 | V8.0 | 2024-12-06 | Have SLPPs incurred actual costs? | X = Count of SLPPs with ACWPCUM | Y = Total count of SLPPs | X/Y ≤ 2% | 13, 44 | A | No | Low | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required, Attribute number, and Instructions V3.6: No Changes V3.5: No Changes V3.4: No Changes V3.3: New metric approved at APR2019 CCB
40 | 08I103a | No | 08 | 08I1 | V8.0 | 2024-12-06 | Have SLPPs earned performance? | X = Count of SLPPs with BCWPCUM | Y = Total count of SLPPs | X/Y ≤ 2% | 13, 44 | A | No | Low | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required, Attribute number, and Instructions V3.6: No Changes V3.5: No Changes V3.4: No Changes V3.3: New metric approved at APR2019 CCB
41 | 09A101a | No | 09 | 09A1 | V8.0 | 2024-12-06 | Is authorization date prior to budgeted baseline start? | X = Count of sampled incomplete CAs where the EV Cost Tool baseline start date precedes the WAD authorization date (signature) | Y = Total count of sampled incomplete CAs from the EV Cost Tool | X/Y ≤ 10% | 02, 09, 13, 44 | M | Yes | Conditional | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Test Metric, Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: Update Assumptions v3.4: Update: Attribute, Data Elements Required, and Assumptions V3.3: No Changes V3.1: Updated assumptions, Removed Block 4 (Frequency)
42 | 09A102a | No | 09 | 09A1 | V8.0 | 2024-12-06 | Is work authorization date prior to the incurrence of actual costs? | X = Count of sampled incomplete CAs where ACWP incurred before the work authorization date | Y = Total count of sampled incomplete CAs that have incurred actual costs | X/Y ≤ 10% | 02, 09, 13, 44 | M | Yes | Standard | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: Update Assumptions v3.4: Update: Attribute and Assumptions V3.3: No Changes V3.1: Updated assumptions, Removed Block 4 (Frequency) Pilot: Approved; Changed to a count (not a sum) metric by RED/CCB.
43 | 09A103a | Yes | 09 | 09A1 | V8.0 | 2025-08-21 | Are elements of cost defined/identified for each control account? | X = Sum of BAC for incomplete CAs with budgets that cannot be segregated by element of cost | Y = Total BAC of incomplete CAs | X/Y ≤ 10% | 13, 44 | A | No | Low | V8.0: Clarify missing EOC in assumptions. Moved rounding Assumption 1 to instructions Step 1 V7.0: Global 508 Formatting, Updated Assumptions V6.0: Global formatting and Assumptions V4.0: Updated Data Elements Required and Instructions V3.6: No Changes V3.5: No Changes v3.4: Update Attribute V3.3: No Changes V3.1: Removed sampling requirement and updated assumptions, Removed Block 4 (Frequency)
44 | 09A104a | Yes | 09 | 09A1 | V8.0 | 2025-08-21 | Is control account data traceable between system artifacts including schedule, cost data, and work authorization documents? • Do baseline dates align between the work authorization documentation (WAD) and IMS? (count) | X = Count of sampled incomplete CAs with IMS baseline dates outside the WAD POP | Y = Total count of incomplete CAs in IMS that were sampled | X/Y ≤ 5% | 09, 11, 45 | M | Yes | Standard | V8.0: Realigned 03A101a from GL03 to GL 09. Test Metric ID changed from 03A101a to 09A104a. V7.0: Global 508 Formatting, No changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements and Instructions V3.6.1: Update Assumptions V3.6: No Changes V3.5: Update Assumptions v3.4: Update: Attribute, Data Elements Required, and Assumptions V3.3: No Changes V3.2: Updated Data Elements with EV Cost Tool Data, updated assumptions V3.1: Minor changes, Removed Block 4 (Frequency) Pilot: Added in $/hours and initial sampling; threshold ≤ 5%
45 | 09A105a | Yes | 09 | 09A1 | V8.0 | 2025-08-21 | Is control account data traceable between system artifacts including schedule, cost data, and work authorization documents? • Does BAC (hours or dollars) within the EV Cost Tool reconcile to the work authorization documentation (WAD)? (count) | X = Count of sampled incomplete CAs where the BAC from the WAD does not match the BAC in the EV Cost Tool data | Y = Total count of sampled incomplete CAs in the EV Cost Tool data | X/Y ≤ 10% | 09, 13, 44 | M | Yes | Low | V8.0: Realigned DECM 03A101c from GL03 to GL 09. Test Metric ID changes from 03A101c to 09A105a. V7.0: Global 508 Formatting, No changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Test Definition, Test Metric, Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: Update Assumptions v3.4: Update Attribute V3.3: No Changes V3.1: Removed Block 4 (Frequency) Pilot: Frequency changed to quarterly
46 | 09A106a | Yes | 09 | 09A1 | V8.0 | 2025-08-21 | Is control account data traceable between system artifacts including schedule, cost data, and work authorization documents? • Do the CA baseline dates align between the WAD and the EV Cost Tool? | X = Count of sampled incomplete CAs with baseline start and baseline finish dates outside the WAD POP in the EV Cost Tool data | Y = Total count of sampled incomplete CAs in the EV Cost Tool data | X/Y ≤ 5% | 02, 09, 13, 44 | M | Yes | Conditional | V8.0: Realigned DECM 03A101g from GL03 to GL09. Test Metric ID changes from 03A101g to 09A106a. V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Update Test Definition, Test Metric, Data Elements Required, Assumptions, and Instructions V3.6.1: Admin update to Test Step, Test Metric, Instructions; Update Assumptions V3.6: No Changes V3.5: Update Assumptions v3.4: Update: Attribute, Data Elements Required, and Assumptions V3.3: No Changes V3.2: Added “Date” to Data Elements for BL Finish/Start V3.1: Updated assumptions, Removed Block 4 (Frequency) Pilot: Threshold change to ≤ 5%
47 | 10A102a | No | 10 | 10A1 | V8.0 | 2024-12-06 | Is each Work Package assigned a single EVT? | X = Count of incomplete WPs that have more than one EVT or no EVT assigned | Y = Total count of incomplete WPs | X/Y ≤ 5% | 13, 44 | A | No | Low | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V4.0: Updated Test Definition, Test Metric, Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: No Changes v3.4: Update Attribute V3.3: Updated Assumptions V3.1: Minor Changes, Removed Block 4 (Frequency)
48 | 10A103a | No | 10 | 10A1 | V8.0 | 2024-12-06 | Are 0-100 EVTs applied to incomplete WPs with one accounting period of budget? | X = Count of 0-100 EVT incomplete WPs with more than one accounting period of budget | Y = Total count of 0-100 EVT incomplete WPs | X/Y ≤ 5% | 02, 13, 44 | A | No | Low | V8.0: No Changes V7.0: Global 508 Formatting, Updated Assumptions V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required and Instructions V3.6: No Changes V3.5: No Changes v3.4: Update: Attribute, Test Metric, Data Elements Required, and Instructions V3.3: Deleted Assumption V3.1: Minor Changes, Removed Block 4 (Frequency)
49 | 10A104a | No | 10 | 10A1 | V8.0 | 2024-12-06 | Are %Start-%Finish EVTs applied to incomplete WPs with two accounting periods of budget? | X = Count of incomplete WPs with %Start-%Finish EVTs with more than two consecutive accounting periods of budget | Y = Total count of incomplete WPs with %Start-%Finish EVTs | X/Y ≤ 5% | 02, 13, 44 | A | No | Low | V8.0: No Changes V7.0: Global 508 Formatting, Updated Assumptions V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required and Instructions V3.6: No Changes V3.5: Update Test Metric, Assumptions, and Instructions v3.4: Update: Attribute, Test Metric, Data Elements Required, Assumptions, and Instructions V3.3: No Changes V3.1: Minor Changes, Removed Block 4 (Frequency)
50 | 10A105a | No | 10 | 10A1 | V8.0 | 2024-12-06 | Is BCWP claimed consistent with the WP EVT? | X = Count of in-progress Non-LOE, non-material WPs sampled with a recorded percent complete that is not consistent with budget and EVT. | Y = Total count of in-progress Non-LOE, non-material WPs sampled | X/Y ≤ 5% | 13, 32, 44 | A/M | Yes | Standard | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required and Instructions V3.6: Update Test Metric, Data Elements, Assumptions, and Instructions V3.5: Update Attribute, Test Step, Test Metric, Data Elements, Assumptions, and Instructions v3.4: Update: Attribute and Assumptions V3.3: No Changes V3.1: Removed Block 4 (Frequency) Pilot: Updated test to validate QBD is predetermined and objective
51 | 10A109b | No | 10 | 10A1 | V8.0 | 2024-12-06 | Does each WP/PP/SLPPs have an assigned budget? | X = Count of WPs/PPs/SLPPs with BAC ≤ 0 | Y = Total count of WPs/PPs/SLPPs | X/Y ≤ 5% | 13, 44 | A | No | Standard | V8.0: No Changes V7.0: Global 508 Formatting, Updated Assumptions V6.0: Global formatting and Assumptions V5.0: Updated Assumptions V4.0: Updated Test Definition, Test Metric, Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: Update Assumptions v3.4: Update Attribute V3.3: Added Assumption V3.1: New metric approved at NOV2018 CCB
52 | 10A110a | Yes | 10 | 10A1 | V8.0 | 2025-08-21 | Is control account data traceable between system artifacts including schedule, cost data, and work authorization documents? •Does non-LOE WP EV percent complete align between the IMS and EV Cost Tool? | X = Count of non-LOE WPs in IMS where EV % complete does not match EV % complete in the EV Cost Tool data | Y = Total count of non-LOE WPs in the IMS | X/Y = 0% | 11, 13, 44, 45 | A/M | No | Standard | V8.0: Realigned DECM 03A101e from GL03 to GL10. Updated Test Metric ID from 03A101e to 10A110a. Discrete changed to non-LOE. Updated assumptions and instructions to include potential issues when EV% complete is calculated. V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Test Definition, Test Metric, Data Elements Required, Assumptions, and Instructions V3.6: Added Instruction one block 12 V3.5: Update Assumptions v3.4: Update: Attribute and Assumptions V3.3: No Changes V3.1: Added discrete and updated assumptions, Removed Block 4 (Frequency) Pilot: Threshold change to 0, assumption added to allow 1% variance
53 | 10A201a | No | 10 | 10A2 | V8.0 | 2024-12-06 | Are EVTs for material consistent with the manner in which material is planned and performance claimed? | X = Count of sampled in-progress material WPs with EVTs that are not consistent with the manner in which material is planned | Y = Total count of sampled in-progress material WPs | X/Y ≤ 10% | 03, 13, 29, 32, 44 | M | Yes | Standard | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: Updated Assumptions and Instructions V4.0: Updated Test Definition, Test Metric, Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: Update Assumptions v3.4: Update: Attribute and Assumptions V3.3: No Changes V3.1: Minor Changes, Removed Block 4 (Frequency) Pilot: New test submitted from Pilot site; Merge 21A501a with this metric; keep this metric and delete 21A501a
54 | 10A302a | No | 10 | 10A3 | V8.0 | 2024-12-06 | Have PPs incurred actual costs? | X = Count of PPs with ACWPCUM | Y = Total count of PPs | X/Y ≤ 2% | 13, 44 | A | No | Low | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: No Changes v3.4: Update Attribute V3.3: Block 10: Replaced Artifact V3.1: Removed Block 4 (Frequency)
55 | 10A302b | No | 10 | 10A3 | V8.0 | 2024-12-06 | Have PPs earned performance? | X = Count of PPs with BCWPCUM | Y = Total count of PPs | X/Y ≤ 2% | 13, 44 | A | No | Low | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required and Instructions V3.6: No Changes V3.5: No Changes v3.4: Update Attribute V3.3: Block 10: Replaced Artifact V3.1: Removed Block 4 (Frequency)
56 | 10A303a | No | 10 | 10A3 | V8.0 | 2024-12-06 | Do all PPs have duration? | X = Count of PPs (tasks/activities & milestones level) with baseline duration less than or equal to one day | Y = Total count of PPs (tasks/activities & milestones level) | X/Y ≤ 10% | 11, 45 | A | No | Low | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: Updated Test Metric, Data Elements, Assumptions, and Instructions V4.0: Updated Data Elements Required and Instructions V3.6: No Changes V3.5: Update Test Metric and Instructions v3.4: Update Attribute V3.3: Block 10: Replaced Artifact, adjusted BL Duration to <1 V3.1: Removed Block 4 (Frequency)
57 | 11A101a | No | 11 | 11A1 | V8.0 | 2024-12-06 | For all CAs, does the BAC value for the CA equate to the sum of the WP and PP budgets within the CA? | X = Sum of the absolute values of (CA BAC – the sum of its WP and PP budgets) | Y = Total program BAC | X/Y ≤ 1% | 13, 44 | A | No | Low | V8.0: No Changes V7.0: Global 508 Formatting, Updated Assumptions V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: No Changes V3.4: No Changes V3.3: No Changes V3.1: Removed Block 4 (Frequency)
58 | 12A101a | No | 12 | 12A1 | V8.0 | 2024-12-06 | Are the contractor’s Level of Effort (LOE) WPs supportive in nature and/or do not produce technical content leading to an end item or product? | X = Sum of BAC of sampled incomplete LOE WPs that are not supportive in nature and/or produce technical content leading to an end item or product | Y = Total BAC of sampled incomplete LOE WPs | X/Y ≤ 15% | 03, 04, 05, 09, 11, 13, 44, 45 | M | Yes | Low | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: Update Assumptions v3.4: Update Assumptions V3.3: No Changes V3.1: Removed Block 4 (Frequency) Pilot: Test rewritten to target LOE determination process.
59 | 12A201a | No | 12 | 12A2 | V8.0 | 2024-12-06 | Are LOE WPs separately evaluated from non-LOE WPs within the same control account? | X = Count of sampled incomplete CAs requiring VARs that have LOE and non-LOE WPs where cost performance of LOE work and cost/schedule performance of non-LOE work is not separately evaluated | Y = Total count of sampled incomplete CAs requiring VARs that have LOE and non-LOE WPs | X/Y ≤ 10% | 13, 15, 16, 44 | M | Yes | Standard | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: Updated Test Definition, Test Metric, Assumptions, and Instructions V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: Update Assumptions v3.4: Update: Attribute and Assumptions V3.3: No Changes V3.1: Updated assumptions, Removed Block 4 (Frequency)
60 | 12A301a | No | 12 | 12A3 | V8.0 | 2024-12-06 | Does the time-phasing of LOE WP budgets properly reflect when the work will be accomplished? | X = Count of sampled incomplete LOE WPs where budget time-phasing does not properly reflect when the work will be accomplished | Y = Total count of sampled incomplete LOE WPs | X/Y ≤ 10% | 13, 44 | M | Yes | Low | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: Update Assumptions v3.4: Update: Attribute and Assumptions V3.3: No Changes V3.1: Updated test steps, Removed Block 4 (Frequency)
61 | 12A401a | No | 12 | 12A4 | V8.0 | 2024-12-06 | Does the contractor proactively manage Level of Effort (LOE) CAs/WPs to avoid inaccurate performance measurement? | X = Sum of BCWPCUR of incomplete LOE CAs/WPs where BCWPCUR > 0 and ACWPCUR = 0 for the last two consecutive periods | Y = Total BCWPCUR for incomplete LOE CAs/WPs | X/Y ≤ 5% | 13, 44 | A | No | Standard | V8.0: No Changes V7.0: Global 508 Formatting, Updated Assumptions V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6: Update Test Metric and Instructions V3.5: Update Test Metric, Data Elements, Assumptions, and Instructions V3.4: No Changes V3.3: No Changes V3.1: New metric approved at NOV2018 CCB
62 | 12I101a | No | 12 | 12I1 | V8.0 | 2024-12-06 | Do LOE WPs have schedule variances? | X = Count of incomplete LOE WPs where (BCWPCUM - BCWSCUM) does not equal 0 | Y = Total count of incomplete LOE WPs | X/Y = 0% | 13, 44 | A | No | Low | V8.0: No Changes V7.0: Global 508 Formatting, Updated Assumptions V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: No Changes V3.4: No Changes V3.3: No Changes V3.1: Removed Block 4 (Frequency)
63 | 13A101a | No | 13 | 13A1, 13A2 | V8.0 | 2024-12-06 | Are published indirect rates consistent with those budgeted in the EV Cost Tool? | X = Count of sampled budgeted indirect rates that do not match between published rates and the budget rate table in the EV Cost Tool | Y = Total count of sampled indirect rates | X/Y = 0% | 03, 13, 18, 23, 24, 43, 44 | M | Yes | Low | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Test Definition, Test Metric, Data Elements Required, and Instructions V3.6: No Changes V3.5: Update Assumptions v3.4: Update Assumptions V3.3: No Changes V3.1: Removed Block 4 (Frequency) Pilot: Test updated to allow for incorporation of latest budgeted rates on changes
64 | 14A101a | Yes | 14 | 14A1 | V8.0 | 2025-08-21 | Is MR excluded from PMB? | X = Absolute value of (MR - (TAB - PMB)) | Y = MR | X/Y = 0% | 20, 41 | A | No | Low | V8.0: Moved rounding assumption to instructions V7.0: Global 508 Formatting, No Changes V6.0: Updated to include IPMDAR; global formatting and Assumptions V5.0: No Changes V4.0: Updated Assumptions and Instructions V3.6: No Changes V3.5: No Changes V3.4: No Changes V3.3: No Changes V3.1: Removed Block 4 (Frequency) Pilot: Test updated to use budget log value
65 | 14A201a | Yes | 14 | 14A2 | V8.0 | 2025-08-21 | Is UB included in PMB? | X = Absolute value of (UB - (PMB - Distributed Budget)) | Y = UB | X/Y = 0% | 13, 20, 41, 44 | A | No | Low | V8.0: Moved Rounding Assumptions to the Instructions V7.0: Global 508 Formatting, No Changes V6.0: Updated to include IPMDAR; global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: No Changes V3.4: No Changes V3.3: No Changes V3.1: Removed Block 4 (Frequency) Pilot: Test updated to use budget log value
66 | 14A202a | No | 14 | 14A2 | V8.0 | 2024-12-06 | Does UB have defined scope and is traceable to contractual actions? | X = Count of sampled UB transactions without defined scope/not traceable to contract actions | Y = Total count of sampled UB transactions | X/Y ≤ 20% | 18, 41, 43 | M | Yes | Low | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Instructions V3.6: No Changes V3.5: Update Assumptions v3.4: Update: Test Metric, Assumptions, and Instructions V3.3: No Changes V3.1: Removed Block 4 (Frequency)
67 | 14I101a | No | 14 | 14I1 | V8.0 | 2024-12-06 | Is MR traceable from the subcontractor/supplier to the prime EVMS? | X = Subcontractor/Supplier MR that is not traceable to the prime EVMS | Y = Subcontractor/Supplier MR | X/Y ≤ 5% | 03, 06, 13, 20, 22, 44 | M | No | Standard | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Updated to include IPMDAR; global formatting and Assumptions V5.0: No Changes V4.0: Updated Test Definition, Test Metric, Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: No Changes V3.4: No Changes V3.3: No Changes V3.1: Removed Block 4 (Frequency)
68 | 15A101a | Yes | 15 | 15A1, 15A2 | V8.0 | 2025-08-21 | Does Total Allocated Budget (TAB) reconcile to the sum of budgets? | X = (NCC + AUW + OTB) – (PMB + MR) | Y = TAB | X/Y = 0% | 13, 20, 44 | A | No | Low | V8.0: Moved rounding assumption to instructions V7.0: Global 508 Formatting, No Changes V6.0: Updated to include IPMDAR; global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: Update Instructions v3.4: Update Attribute V3.3: No Changes V3.1: Changed to Automated, Removed Block 4 (Frequency) Pilot: Changed threshold to 0.
69 | 16A101a | Yes | 16 | 16A1 | V8.0 | 2025-08-21 | Does ACWPCUM in the EVMS reconcile to actual costs in the accounting system? | X = Sum of actual direct costs that do not reconcile between the EV Cost Tool and the Accounting System | Y = Sum of total direct ACWPCUM from the EV Cost Tool | X/Y ≤ 1% | 13, 14, 44, 54 | M | No | Low | V8.0: Moved rounding assumption to instructions V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Test Metric, Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: Update Assumptions v3.4: Update Attribute V3.3: No Changes V3.2: Added Rounding $100 rounding error Assumption V3.1: Removed Block 4 (Frequency)
70 | 16A301a | No | 16 | 16A3 | V8.0 | 2024-12-06 | Are estimated actuals properly used to account for the cost of work accomplished that has not yet been recorded in the accounting system? | X = Count of sampled instances of estimated actuals that are not supported/documented | Y = Total count of sampled instances of estimated actuals | X/Y ≤ 5% | 13, 44, 49 | M | Yes | Standard | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required and Instructions V3.6: No Changes V3.5: Update Assumptions v3.4: Update Assumptions V3.3: No Changes V3.2: Corrected Instruction Step 3 from “Denominator” to “Numerator” for X V3.1: Removed Block 4 (Frequency) Pilot: No CCB changes; same as Integration Team version
71 | 16A501a | No | 16 | 16A5, 16A6 | V8.0 | 2024-12-06 | Is Non-Material ACWP being recorded without BCWP? | X = Absolute value of Non-Material, Non-LOE ACWPCUR on incomplete CAs/WPs where Non-Material, Non-LOE ACWPCUR ≠ 0 and Non-Material, Non-LOE BCWPCUR = 0 | Y = Absolute value of total Non-Material, Non-LOE ACWPCUR on incomplete CAs/WPs | X/Y ≤ 5% | 13, 44 | A | No | Standard | V8.0: No Changes V7.0: Global 508 Formatting, Updated Assumptions V6.0: Updated Assumptions; global formatting and Assumptions V5.0: Updated Test Metric and Instructions V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6: Update Assumptions V3.5: Update Test Metric, Data Elements, Assumptions, And Instructions v3.4.1 Update: Instruction Step 2 v3.4: Update: Attribute and Test Metric V3.3: Added 2 Data Elements, updated Block 7 & 12 with incomplete CAs/WPs V3.2: Updated test step language. Minor updates to assumptions and instructions. Update to logic to include negative BCWP V3.1: Exclude LOE from the calculations in order to maintain symmetry with the corresponding GL21 Material Test Metrics, Removed Block 4 (Frequency) Pilot: Changed from CUM to CUR only
72 | 16A501b | No | 16 | 16A5, 16A6 | V8.0 | 2024-12-06 | Is Non-Material BCWP being recorded without ACWP? | X = Absolute value of Non-Material, Non-LOE BCWPCUR on incomplete CAs/WPs where Non-Material, Non-LOE BCWPCUR ≠ 0 and Non-Material, Non-LOE ACWPCUR = 0 | Y = Absolute value of total Non-Material, Non-LOE BCWPCUR on incomplete CAs/WPs | X/Y ≤ 5% | 13, 44 | A | No | Standard | V8.0: No Changes V7.0: Global 508 Formatting, Updated Assumptions V6.0: Updated Assumptions; global formatting and Assumptions V5.0: Updated Test Metric and Instructions V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6: Update Assumptions V3.5: Update Test Metric, Data Elements, Assumptions, And Instructions v3.4: Update: Attribute, Test Metric, Assumptions, and Instructions V3.3: Added language in blocks 7 & 12 for clarity and consistency; added 2 Data Elements V3.2: Updated test step language. Minor updates to assumptions and instructions.
73 | 16A501c | No | 16 | 16A5, 16A6 | V8.0 | 2024-12-06 | Is Non-Material ACWP being recorded without BCWP? | X = Absolute value of Non-Material, Non-LOE ACWPCUM on incomplete CAs/WPs where Non-Material, Non-LOE ACWPCUM ≠ 0 and Non-Material, Non-LOE BCWPCUM = 0 | Y = Absolute value of total Non-Material, Non-LOE ACWPCUM on incomplete CAs/WPs | X/Y ≤ 5% | 13, 44 | A | No | Low | V8.0: No Changes V7.0: Global 508 Formatting, Updated Assumptions V6.0: Updated Assumptions; global formatting and Assumptions V5.0: Updated Test Metric and Instructions V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6: Update Assumptions V3.5: Update Test Metric, Data Elements, Assumptions, And Instructions v3.4: Update: Attribute and Test Metric V3.3: Language added for clarification V3.2: New metric (approved by Jan 2019 CCB)
74 | 16A501d | No | 16 | 16A5, 16A6 | V8.0 | 2024-12-06 | Is Non-Material BCWP being recorded without ACWP? | X = Absolute value of Non-Material, Non-LOE BCWPCUM on incomplete CAs/WPs where Non-Material, Non-LOE BCWPCUM ≠ 0 and Non-Material Non-LOE ACWPCUM = 0 | Y = Absolute value of total Non-Material, Non-LOE BCWPCUM on incomplete CA/WPs | X/Y ≤ 5% | 13, 44 | A | No | Low | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Updated Assumptions; global formatting and Assumptions V5.0: Updated Test Metric and Instructions V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6: Update Assumptions V3.5: Update Test Metric, Data Elements, Assumptions, And Instructions v3.4: Update: Attribute and Test Metric V3.3: Language added for clarification V3.2: New metric (approved by Jan 2019 CCB)
75 | 16A502a | No | 16 | 16A5, 16A6 | V8.0 | 2024-12-06 | Are actual costs excluding material being incurred on completed work? | X = Absolute value of Non-Material, Non-LOE ACWPCUR on completed CA/WP where Non-Material, Non-LOE ACWPCUR ≠ 0 and Non-material, Non-LOE BCWPCUR = 0 | Y = Absolute value of total Non-Material, Non-LOE ACWPCUR on completed CAs/WPs. | X/Y ≤ 5% | 13, 44 | A | No | Standard | V8.0: No Changes V7.0: Global 508 Formatting, Updated Assumptions V6.0: Updated Assumptions; global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6.1: Update Assumptions V3.6: Update Assumptions and Instructions V3.5: Update Test Metric, Assumptions, and Instructions v3.4: Update Attribute V3.3: Updated Assumptions, language added for clarification V3.2: Minor updates to assumptions & instructions. Updated block 7 for consistency V3.1: Exclude LOE from the calculations in order to maintain symmetry with the corresponding GL21 Material Test Metrics, Removed Block 4 (Frequency)
76 | 17A101a | Yes | 17 | 17A1 | V8.0 | 2025-08-21 | Does ACWPCUR summarize from the lowest defined level where actual costs are collected through the WBS hierarchy without allocation to two or more higher-level WBS elements? | X = Count of occurrences where the sum of the child ACWPCUR does not equal the ACWPCUR of the parent WBS element | Y = Count of parent WBS elements | X/Y = 0% | 13, 44 | M | No | Low | V8.0: Moved rounding assumption to instructions V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: No Changes v3.4: Update Attribute V3.3: No Changes V3.2: Clarified rounding error assumption V3.1: Removed Block 4 (Frequency) Pilot: Changed wording of test; threshold set at 0
77 | 18A101a | Yes | 18 | 18A1 | V8.0 | 2025-08-21 | Does ACWPCUR summarize from the lowest defined level where actual costs are collected through the OBS hierarchy without allocation to two or more higher-level OBS elements? | X = Count of occurrences where the sum of the child ACWPCUR does not equal the ACWPCUR of the parent OBS element | Y = Count of parent OBS elements | X/Y = 0% | 13, 44 | M | No | Low | V8.0: Moved rounding assumption to instructions V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: No Changes v3.4: Update Attribute V3.3: No Changes V3.2: Clarified rounding error assumption V3.1: Removed Block 4 (Frequency) Pilot: Changed wording of test; threshold set at 0
78 | 19A101a | No | 19 | 19A1 | V8.0 | 2024-12-06 | Are published indirect rates consistent with those applied in the EV Cost Tool for actual costs? | X = Count of indirect rates that do not match between published rates and the rate table in the EV Cost Tool | Y = Total count of indirect rates | X/Y = 0% | 13, 24, 44 | M | No | Low | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Test Definition, Test Metric, Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: No Changes V3.4: No Changes V3.3: No Changes V3.1: Removed Block 4 (Frequency) Pilot: Added assumption so that this test is only performed where actuals are burdened in the EVMS and not the Acct Sys
79 | 19A101b | No | 19 | 19A1 | V8.0 | 2024-12-06 | Are the bases and rates for allocating costs from each indirect pool consistently applied? | X = Count of sampled indirect rates that do not match between published rates and the rate applied in the EVMS cost report | Y = Total count of sampled indirect rates | X/Y = 0% | 13, 23, 24, 44 | M | Yes | Low | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: Updated Assumptions V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: No Changes V3.4: No Changes V3.3: No Changes V3.1: Removed Block 4 (Frequency) Pilot: Added assumption so that this test is only performed where actuals are burdened in the EVMS and not the Acct Sys
80 | 19A401a | No | 19 | 19A4 | V8.0 | 2024-12-06 | Does ACWPCUM in the EVMS reconcile to actual costs in the accounting system? | X = Sum of actual indirect costs that do not reconcile between the EV Cost Tool and the Accounting System | Y = Sum of total indirect ACWPCUM from the EV Cost Tool | X/Y ≤ 1% | 13, 14, 44, 54 | M | No | Low | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Test Metric, Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: No Changes v3.4: Update: Unique Test Metric ID from 19A301a to 19A401a and Attribute V3.3: No Changes V3.1: New metric approved at NOV2018 CCB. This new metric replaces a deleted metric with the same metric number. See the "Deleted Metrics Archive" tab for more information on the deleted 19A301a. .
81 | 20A101a | No | 20 | 20A1 | V8.0 | 2024-12-06 | If required, is the contractor’s system capable of reporting in unit or lot costs in a production or manufacturing environment? | X = System that cannot produce reports in unit or lot costs in terms of labor, material, other direct costs, and indirect costs derived from the accounting system | n/a | X = 0 | 06, 14 | M | No | Low | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Instructions V3.6: No Changes V3.5: No Changes v3.4: Update Attribute V3.3: No Changes V3.1: Removed Block 4 (Frequency) Pilot: Only perform if contractual requirement
82 | 20A201a | No | 20 | 20A2 | V8.0 | 2024-12-06 | If required, are the cost accumulation structures established identifying recurring/non-recurring costs? | X = System that cannot produce reports in terms of recurring or nonrecurring costs derived from the accounting system | n/a | X = 0 | 06, 14 | M | No | Low | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Instructions V3.6: No Changes V3.5: No Changes V3.4: No Changes V3.3: No Changes V3.1: Removed Block 4 (Frequency) Pilot: Only perform if contractual requirement
83 | 21A301a | No | 21 | 21A3 | V8.0 | 2024-12-06 | Are actual material costs being incurred on completed work? | X = Absolute value of Material, Non-LOE ACWPCUR on completed CAs/WPs where Material, Non-LOE ACWPCUR ≠ 0, and Material, Non-LOE BCWPCUR = 0 | Y = Absolute value of total Material, Non-LOE ACWPCUR on completed CAs/WPs. | X/Y ≤ 5% | 13, 44 | A | No | Standard | V8.0: No Changes V7.0: Global 508 Formatting, Updated Assumptions V6.0: Updated Assumptions; global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6.1: Update Assumptions V3.6: Update Assumptions and Instructions V3.5: Update Test Step, Test Metric, Data Elements, Assumptions, And Instructions V3.4: No Changes V3.3: Language added for clarification, removed Data Element 49 for consistency across metrics V3.1: Removed Block 4 (Frequency) Pilot: Denominator changed to ACWP cum (when?)
84 | 21A302a | No | 21 | 21A3 | V8.0 | 2024-12-06 | Is material ACWP being recorded without BCWP? | X = Absolute value of Material, Non-LOE ACWPCUR on incomplete CAs/WPs where Material, Non-LOE ACWPCUR ≠ 0 and Material, Non-LOE BCWPCUR = 0 | Y = Absolute value of total Material, Non-LOE ACWPCUR on incomplete CAs/WPs | X/Y ≤ 5% | 13, 44 | A | No | Conditional | V8.0: No Changes V7.0: Global 508 Formatting, Updated Assumptions V6.0: Updated Assumptions; global formatting and Assumptions V5.0: Updated Test Metric and Instructions V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6: Update Assumptions V3.5: Update Test Metric, Data Elements, Assumptions, And Instructions v3.4: Update Test Metric V3.3: Language added for clarification, removed Data Element 49 for consistency across metrics V3.2: Updated test step language. Updated logic to include negative BCWP. Minor updates for consistency in instructions and test metric sections V3.1: Removed Block 4 (Frequency) Pilot: Test adjusted to review current values unless frequency is less than monthly
85 | 21A302b | No | 21 | 21A3 | V8.0 | 2024-12-06 | Is material BCWP being recorded without ACWP? | X = Absolute value of Material, Non-LOE BCWPCUR on incomplete CAs/WPs where Material, Non-LOE BCWPCUR ≠ 0 and Material, Non-LOE ACWPCUR = 0 | Y = Absolute value of total Material, Non-LOE BCWPCUR on incomplete CAs/WPs | X/Y ≤ 5% | 13, 44 | A | No | Standard | V8.0: No Changes V7.0: Global 508 Formatting, Updated Assumptions V6.0: Updated Assumptions; global formatting and Assumptions V5.0: Updated Test Metric and Instructions V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6: Update Assumptions V3.5: Update Test Metric, Data Elements, Assumptions, And Instructions v3.4: Update Test Metric V3.3: Language added for clarification, removed Data Element 49 for consistency across metrics V3.2: Updated test step language. Updated logic to include negative ACWP. Minor updates for consistency to test metric and assumptions. V3.1: Removed Block 4 (Frequency) Pilot: Test adjusted to review current values unless frequency is less than monthly
86 | 21A302c | No | 21 | 21A3 | V8.0 | 2024-12-06 | Is material ACWP being recorded without BCWP? | X = Absolute value of Material, Non-LOE ACWPCUM on incomplete CAs/WPs where Material, Non-LOE ACWPCUM ≠ 0 and Material, Non-LOE BCWPCUM = 0 | Y = Absolute value of total Material, Non-LOE ACWPCUM on incomplete CAs/WPs | X/Y ≤ 5% | 13, 44 | A | No | Low | V8.0: No Changes V7.0: Global 508 Formatting, Updated Assumptions V6.0: Updated Assumptions; global formatting and Assumptions V5.0: Updated Test Metric and Instructions V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6: Update Assumptions V3.5: Update Test Metric, Data Elements, Assumptions, And Instructions v3.4: Update Test Metric V3.3: Language added for clarification, removed Data Element 49 for consistency across metrics V3.2: New metric (approved by Jan 2019 CCB)
87 | 21A302d | No | 21 | 21A3 | V8.0 | 2024-12-06 | Is material BCWP being recorded without ACWP? | X = Absolute value of Material, Non-LOE BCWPCUM on incomplete CAs/WPs where Material, Non-LOE BCWPCUM ≠ 0 and Material Non-LOE ACWPCUM = 0 | Y = Absolute value of total Material, Non-LOE BCWPCUM on incomplete CAs/WPs | X/Y ≤ 5% | 13, 44 | A | No | Low | V8.0: No Changes V7.0: Global 508 Formatting, Updated Assumptions V6.0: Updated Assumptions; global formatting and Assumptions V5.0: Updated Test Metric and Instructions V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6: Update Assumptions V3.5: Update Test Metric, Data Elements, Assumptions, And Instructions v3.4: Update Test Metric V3.3: Language added for clarification V3.2: New metric (approved by Jan 2019 CCB)
88 | 21A401a | No | 21 | 21A4, 21A5 | V8.0 | 2024-12-06 | Are material EVTs implemented per the contractor’s procedures? | X = BAC of sampled incomplete material WPs with LOE, PERT, Apportioned, or blank EVT not implemented per the contractor’s procedures | Y = Total BAC of sampled incomplete LOE, PERT, Apportioned, or blank EVT material WPs | X/Y ≤ 0% | 03, 13, 44 | M | Yes | Standard | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: Updated Attribute, Test Definition, Test Metric, Threshold, Data Elements, Assumptions, and Instructions V4.0: Updated Data Elements Required and Instructions V3.6: No Changes V3.5: Update Test Step, Test Metric, Assumptions, And Instructions v3.4: Update: Attribute and Assumptions V3.3: No Changes V3.2: Added “incomplete” to the test metric section V3.1: Removed Block 4 (Frequency) Pilot: Updated test to include high value/critical materials
89 | 21A601a | No | 21 | 21A6 | V8.0 | 2024-12-06 | Does the contractor have the ability to account for all material purchased (e.g. material issued to control accounts, return of unused material, scrap quantity and disposition, and residual inventory)? | X = Count of sampled material items issued to contract that are not accounted for | Y = Total count of sampled material items identified in BOM | X/Y ≤ 5% | 29, 55 | M | Yes | Low | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: Updated Data Elements, Assumptions, and Instructions V4.0: Updated Instructions V3.6: No Changes V3.5: Update Assumptions v3.4: Update Assumptions V3.3: No Changes V3.1: Removed Block 4 (Frequency) Pilot: Revised test for follow-up process if MMAS is not approved.
90 | 21I101a | No | 21 | 21I1 | V8.0 | 2024-12-06 | Are material transfers and loans processed to ensure appropriate collection of direct costs and performance measurement? | X = Count of sampled material transfers and loans not processed correctly | Y = Total number of sampled material transfers and loans | X/Y ≤ 10% | 13, 14, 29, 44 | M | Yes | Standard | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required and Instructions V3.6: No Changes V3.5: No Changes v3.4: Update Assumptions V3.3: No Changes V3.1: Removed Block 4 (Frequency)
91 | 22A101a | No | 22 | 22A1 | V8.0 | 2024-12-06 | Are there cost and schedule variance calculations at the control account level (at a minimum)? | X = Count of sampled incomplete control accounts without correct variance calculations | Y = Total count of sampled incomplete control accounts | X/Y = 0% | 13, 44, 52 | M | Yes | Low | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Test Metric, Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: Update Assumptions v3.4: Update Assumptions V3.3: No Changes V3.2: SUPSHIP added as an organization that can validate tool set in Assumption #2 V3.1: Removed Block 4 (Frequency) Pilot: Added EVMS Analysis Tool data element (#52). Approved.
92 | 22I102a | No | 22 | 22I1 | V8.0 | 2024-12-06 | Is performance greater than budget (BAC)? | X = BCWPCUM for WPs where BCWPCUM is greater than BAC | Y = Total BCWPCUM for all WPs | X/Y = 0% | 13, 44 | A | No | Low | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: No Changes V3.4: No Changes V3.3: Added Assumption 2 V3.1: Removed Block 4 (Frequency) Pilot: Formerly 10A101a - Moved to GL 22, new UID
93 | 23A101a | No | 23 | 23A1 | V8.0 | 2024-12-06 | Are required VARs being generated for control accounts and SLPPs that exceed established internal thresholds? | X = Count of incomplete control accounts and SLPPs missing VARs where required | Y = Total count of incomplete control accounts and SLPPs requiring VARs | X/Y ≤ 2% | 03, 13, 15, 16, 44 | M | No | Standard | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: No Changes V3.4: No Changes V3.3: Added SLPP into the test step, assumptions and instructions; V3.1: Removed Block 4 (Frequency) Pilot: Instructions reworded during CCB. Approved.
94 | 23A201a | No | 23 | 23A1, 23A2 | V8.0 | 2024-12-06 | Are Rate & Volume (Labor) and Price & Usage (Material) Variance formulas correctly applied at the control account level? | Verify formulas: Labor Rate Variance = (Earned Rate - Actual Rate) * Actual Hours Volume Variance = (Earned Hours - Actual Hours) * Earned Rate Material Price Variance = (Earned Unit Price - Actual Unit Price) * Actual Quantity Usage Variance = (Earned Quantity - Actual Quantity) * Earned Unit Price | n/a | Within Threshold / Out of Threshold | 17 | M | No | Standard | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: Updated Attribute V4.0: Updated Metric Threshold and Instructions V3.6: No Changes V3.5: Update Test Step and Instructions v3.4: Update Attribute V3.3: No Changes V3.1: Removed Block 4 (Frequency) Pilot: Updated formulas (both labor and material price/usage variances), added assumption. Approved.
95 | 23A301a | No | 23 | 23A3 | V8.0 | 2024-12-06 | Does the Schedule Variance (SV) analysis include documented impact to future tasks/activities & milestones on the critical path, near-critical paths, or driving paths? | X = Count of sampled CA with reported SV VARs that do not address impact to the critical path, near-critical paths, or driving paths | Y = Total count of sampled CA with reported SV VARs | X/Y ≤ 20% | 11, 12, 16, 45 | M | Yes | Standard | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6.1: Update Test Step, Data Elements Required, Assumptions and Instructions V3.6: No Changes V3.5: Update Test Metric, Data Elements, Assumptions, and Instructions v3.4: Update Assumptions V3.3: No Changes V3.1: Removed Block 4 (Frequency) Pilot: Added assumption about SVs with no CP impact; changed threshold and freq to quarterly.
96 | 23A401a | No | 23 | 23A4 | V8.0 | 2024-12-06 | Do the root cause analysis, impact and corrective action address the variance/issue? | X = Count of sampled VARs (including root cause, impact, and corrective action) that do not address variance/issue | Y = Total count of sampled VARs | X/Y ≤ 15% | 03, 17, 20, 46 | M | Yes | Standard | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Updated to include IPMDAR; global formatting and Assumptions V5.0: No Changes V4.0: Updated Assumptions and Instructions V3.6: No Changes V3.5: Update Assumptions v3.4: Update Assumptions V3.3: No Changes V3.1: Removed Block 4 (Frequency) Pilot: Added assumption about unrecoverable variances. Instructions focus on VAR process. Approved.
97 | 24A101a | No | 24 | 24A1 | V8.0 | 2024-12-06 | Does indirect variance analysis address root cause, impact, and corrective action? | X = Count of overhead categories that do not address indirect cost variances when required | Y = Total count of overhead categories that require indirect cost variance analysis | X/Y ≤ 5% | 15, 17, 23, 24 | M | No | Standard | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Instructions V3.6: No Changes V3.5: No Changes v3.4: Update Attribute V3.3: No Changes V3.1: Removed Block 4 (Frequency) Pilot: Focus is on addressing objective evidence that variance analysis was conducted, not "quality" or "adequacy" of indirect VARs. Approved.
98 | 25A101a | Yes | 25 | 25A1 | V8.0 | 2025-08-21 | Do BCWS, BCWP, ACWP, BAC and EAC summarize through the WBS? | X = Count of occurrences where the sum of the child {*} does not equal the {*} of the parent WBS element, where {*} equals: a) BCWSCUR b) BCWSCUM c) BCWPCUR d) BCWPCUM e) ACWPCUM f) BAC g) EAC | Y = Total count of parent WBS elements | X/Y = 0% | 13, 44 | M | No | Low | V8.0: Moved rounding assumption to instructions V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: No Changes v3.4: Update Attribute V3.3: No Changes V3.2: Clarified rounding error assumption V3.1: Removed Block 4 (Frequency) Pilot: Updated formula; combined 25A101a-g into a single metric sheet; set threshold at 0. Approved.
99 | 25A102a | Yes | 25 | 25A1 | V8.0 | 2025-08-21 | Do BCWS, BCWP, ACWP, BAC and EAC summarize through the OBS? | X = Count of occurrences where the sum of the child {*} does not equal the {*} of the parent OBS element, where {*} equals: a) BCWSCUR b) BCWSCUM c) BCWPCUR d) BCWPCUM e) ACWPCUM f) BAC g) EAC | Y = Total count of parent OBS elements | X/Y = 0% | 13, 44 | M | No | Low | V8.0: Moved rounding assumption to instructions V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: No Changes V3.4: No Changes V3.2: Clarified rounding error assumption V3.3: No Changes V3.1: Removed Block 4 (Frequency) Pilot: Updated formula; combined 25A102a-g into a single metric sheet; set threshold at 0. Approved.
100 | 25A201a | Yes | 25 | 25A2 | V8.0 | 2025-08-21 | Is subcontractor/supplier data aligned with and traceable through the prime system? • Do the subcontractor/supplier EVM data elements reconcile to the prime EV Cost Tool? | X = The sampled BAC value of the incomplete subcontractor/supplier CAs where a data element (BCWP, BCWS, ACWP, BAC) from the subcontractor's/supplier’s IPMR/CPR/IMPDAR cannot be reconciled to the prime EV Cost Tool | Y = Sum of sampled BAC for CA element tested | X/Y ≤ 5% | 13, 22, 44 | M | Yes | Low | V8.0: Realigned from Guideline 3 to Guideline 25. Test Metric ID changed from 03A102a to 25A201a. V7.0: Global 508 Formatting, No Changes V6.0: Updated to include IPMDAR V5.0: No Changes V4.0: Updated Test Definition, Test Metric, Data Elements Required, Assumptions, and Instructions V3.6: Update Test Metric V3.5: Update Assumptions V3.4: No Changes V3.3: No Changes V3.2: Added Complete CA definition in Assumptions V3.1: Removed Block 4 (Frequency) Pilot: Threshold change to ≤ 5%; test run on 10 samples CAs; run via dollars or hours; removed attribute 10A2
101 | 26A201a | Yes | 26 | 26A2 | V8.0 | 2025-08-21 | Are corrective actions properly managed and tracked? | X = Count of VARs with corrective actions that are missing or not properly recorded | Y = Total count of VARs with corrective actions | X/Y ≤ 10% | 19, 20 | M | No | Standard | V8.0: Incorporated checking for ECD in the past from DECM 26A201b and deleted that DECM. Threshold lowered to 10%. V7.0: Global 508 Formatting, No Changes V6.0: Updated to include IPMDAR; global formatting and Assumptions V5.0: No Changes V4.0: Updated Instructions V3.6: No Changes V3.5: No Changes V3.4: No Changes V3.3: No Changes V3.1: Removed Block 4 (Frequency)
102 | 27A101a | No | 27 | 27A1 | V8.0 | 2025-08-21 | Are comprehensive EACs completed at least annually? | X = 0 if the contract performed a comprehensive EAC (CEAC) within the past year (at a minimum). X = 1 if a CEAC has not been performed within the past year. | n/a | X = 0 | 33 | M | No | Conditional | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Updated to review a single contract; global formatting and Assumptions V5.0: No Changes V4.0: Updated Instructions V3.6: Update Assumptions V3.5: No Changes v3.4: Update Attribute V3.3: No Changes V3.1: Removed Block 4 (Frequency) Pilot: Modified at CCB; changed to "CEAC performed at least annually"; changed instructions to CEAC commencement (not completion) date. Approved.
103 | 27A101b | No | 27 | 27A1 | V8.0 | 2024-12-06 | Are comprehensive EACs performed according to the standards described in the EVM system description? | X = Count of contracts with a CEAC not performed according to the EVMSD | n/a | X = 0 | 03, 06, 33 | M | No | Standard | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Instructions V3.6: Update Assumptions V3.5: No Changes v3.4: Update Attribute V3.3: No Changes V3.1: Removed Block 4 (Frequency) Pilot: NEW METRIC added at CCB (2 Feb 17)
104 | 27A102a | Yes | 27 | 27A1 | V8.0 | 2025-08-21 | Are time-phased estimates to complete aligned with the remaining tasks in the integrated master schedule? | X = Count of all PPs/SLPPs and incomplete WPs in the EV Cost Tool where time-phased ETC does not align with forecast dates in the IMS | Y = Total count of all PPs/SLPPS and incomplete WPs in the EV Cost Tool that are also within the IMS | X/Y ≤ 10% | 02, 11, 13, 44, 45 | A | No | Standard | V8.0: Corrected Assumption numbering. Clarified all SLPP and PP are included in metric. Changed Discrete to non-LOE, Moved rounding assumption to instructions. V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: Updated Data Elements and Assumptions V4.0: Updated Test Metric, Data Elements Required, and Instructions V3.6.1: Update Test Metric, Assumptions, and Instructions V3.6: No Changes v3.5.1: Update Instructions V3.5: Update Test Metric, Data Elements, Assumptions, and Instructions v3.4: Update: Attribute and Assumptions V3.3: No Changes V3.1: Updated assumptions, minor changes, Removed Block 4 (Frequency) Pilot: Changed instructions for clarity; added assumption about resource-loaded IMS; added data element 53 Resource Plans; freq to quarterly. Approved.
105 | 27A102b | No | 27 | 27A1 | V8.0 | 2024-12-06 | Are time-phased estimates to complete aligned with the remaining tasks in the integrated master schedule? | X = Count of sampled incomplete WPs/PPs/SLPPs in the EV Cost Tool where time-phased ETC does not align with forecast dates in the IMS | Y = Total count of sampled incomplete WPs/PPs/SLPPs in the EV Cost Tool that are also within the IMS | X/Y ≤ 10% | 02, 11, 13, 44, 45 | M | Yes | Standard | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Updated Data Elements and Instructions; global formatting and Assumptions V5.0: Updated Data Elements and Assumptions V4.0: Updated Test Metric, Data Elements Required, and Instructions V3.6.1: Update Test Metric, Assumptions, and Instructions V3.6: New metric approved at JUL2020 CCB
106 | 27A103a | No | 27 | 27A1 | V8.0 | 2024-12-06 | Do EACs exist at the control account level? | X = Count of incomplete CAs with zero, missing, or negative EACs | Y = Total count of incomplete CAs | X/Y = 0% | 13, 44 | A | No | Low | V8.0: No Changes V7.0: Global 508 Formatting, Updated Assumptions V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required and Instructions V3.6: No Changes V3.5: No Changes v3.4: Update Attribute V3.3: No Changes V3.2: Changed Threshold to 0% V3.1: Removed Block 4 (Frequency) Pilot: Minor wording changes. Approved.
107 | 27A104b | No | 27 | 27A1 | V8.0 | 2024-12-06 | Are ETCs generated for completed WPs? | X = Sum ETC value of completed WPs with ETC | n/a | X = 0 | 13, 44 | A | No | Standard | V8.0: No Changes V7.0: Global 508 Formatting, Updated Assumptions V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required and Instructions V3.6: Update Assumptions V3.5: No Changes v3.4: Update: Attribute, Test Metric, Metric Threshold, and Instructions V3.3: Updated Block 12 language and filtered Y for completed WPs with ETCs only. V3.1: New metric approved at NOV2018 CCB
108 | 27A105a | Yes | 27 | 27A1 | V8.0 | 2025-08-21 | Is ACWPCUM greater than EAC? | X = Count of CAs/WPs where ACWPCUM > EAC | Y = Total count of CAs/WPs | X/Y = 0% | 13, 44 | A | No | Low | V8.0: Moved rounding assumption to instructions V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: Update Test Metric, Data Elements, Assumptions, and Instructions v3.4: Update: Attribute and Metric Threshold V3.3: No Changes V3.2: Clarified rounding error assumption V3.1: Removed Block 4 (Frequency) Pilot: Minor wording changes. Approved.
109 | 27A106a | No | 27 | 27A1 | V8.0 | 2024-12-06 | Do EACs consider performance to date? | X = Count of CAs that are ≥ 15% and ≤ 95% complete where ¦TCPIEAC – CPICUM¦ > 0.1 | Y = Total count of CAs that are ≥ 15% and ≤ 95% complete | X/Y ≤ 25% | 13, 44 | A | No | Standard | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required and Instructions V3.6: No Changes V3.5: Update Assumptions and Instructions v3.4: Update: Attribute, Test Metric, and Instructions V3.3: No Changes V3.1: Updated assumptions, Removed Block 4 (Frequency) Pilot: Combines 27A201a and 27A201c. Changed wording of instructions from "adequate justification" of EACs to "verify substantiation" of EACs out of tolerance.
110 | 27A203a | No | 27 | 27A2 | V8.0 | 2024-12-06 | Is the latest information related to direct/indirect rates used for development of ETCs? | X = Count of sampled incomplete WPs from the EV Cost Tool where direct and indirect rates are not applied correctly to the ETC | Y = Total count of sampled incomplete WPs | X/Y = 0% | 13, 14, 24, 44 | M | Yes | Standard | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: Updated Data Elements V4.0: Updated Test Metric, Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: Update Assumptions v3.4: Update: Attribute and Assumptions V3.3: No Changes V3.1: Removed Block 4 (Frequency)
111 | 27A401a | Yes | 27 | 27A4, 27A5 | V8.0 | 2025-08-21 | Is the program EAC substantiated from the risk and opportunity management process and/or the Program Manager’s assessment? | X = Occurrence of a program EAC not substantiated with risks/opportunities and/or Program Manager’s assessment per the system description and risk management process | n/a | X = 0 | 03, 13, 20, 28, 44, 62 | M | No | Standard | V8.0: Moved rounding assumption to instructions V7.0: Global 508 Formatting, No Changes V6.0: Updated Data Elements and to include IPMDAR; global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: No Changes v3.4: Update: Attribute, Data Elements Required, Assumptions, and Instructions V3.3: No Changes V3.1: Removed Block 4 (Frequency) Pilot: Wording changes. Approved.
112 | 27I101a | No | 27 | 27I1 | V8.0 | 2024-12-06 | Are ETCs generated for WPs/PPs/SLPPs? | X = Count of incomplete WPs/PPs/SLPPs with BAC > 0 and ETC ≤ 0 | Y = Total count of incomplete WPs/PPs/SLPPs with BAC > 0 | X/Y = 0% | 13, 44 | A | No | Standard | V8.0: No Changes V7.0: Global 508 Formatting, Updated Assumptions V6.0: Global formatting and Assumptions V5.0: Updated Data Elements V4.0: Updated Test Definition, Test Metric, Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: Update Assumptions V3.4: No Changes V3.3: New metric (approved by Apr 2019 CCB). Essentially replaces 27A104a with the only difference being that the metric is traceable to an intent statement rather than an EVMSIG attribute statement.
113 | 27I201a | No | 27 | 27I2 | V8.0 | 2024-12-06 | Are EACs reviewed and updated as needed for UB and SLPPs? | X = Count of UB and SLPPs where BAC ≠ EAC or EAC is negative | n/a | X = 0 | 13, 20, 44 | A | No | Low | V8.0: No Changes V7.0: Global 508 Formatting, Updated Assumptions V6.0: Updated to include IPMDAR; global formatting and Assumptions V5.0: No Changes V4.0: Updated Test Metric, Data Elements Required, and Instructions V3.6.1: Update Test Step, Test Metric, Data Elements Required, and Instructions V3.6: Update Test Metric, Data Elements, and Instructions V3.5: No Changes v3.4: Update: Test Metric and Instructions V3.3: New metric (approved by Apr 2019 CCB)
114 | 28A101a | No | 28 | 28A1 | V8.0 | 2024-12-06 | Are authorized work scope/budget changes incorporated into the PMB as soon as practicable? | X = Count of sampled contract modifications that were not incorporated into the PMB in a timely manner in accordance with the system description | Y = Total count of sampled contract modifications | X/Y ≤ 10% | 03, 06, 18 | M | Yes | Conditional | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Instructions V3.6: No Changes V3.5: Update Assumptions v3.4: Update Assumptions V3.3: No Changes V3.2: Revised instruction language to be consistent with assumption & global assumption (#2) V3.1: Removed Block 4 (Frequency)
115 | 28A201a | No | 28 | 28A2 | V8.0 | 2024-12-06 | Is UB distributed in a timely manner? | X = Dollar value of UB samples not distributed within the timeframe specified in the SD | Y = Total UB dollar value of sampled contract mods or baseline change requests | X/Y = 0% | 03, 18 | M | Yes | Standard | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Instructions V3.6: No Changes V3.5: Update Assumptions v3.4: Update Assumptions V3.3: No Changes V3.1: Removed Block 4 (Frequency)
116 | 29A101a | Yes | 29 | 29A1 | V8.0 | 2025-08-21 | Do current budgets reconcile to prior budgets through the documented changes? | X = Count of sampled CAs where prior period CA BAC does not reconcile with current period CA BAC through change documentation | Y = Total count of sampled CAs with budget changes within the past 12 months | X/Y = 0% | 13, 41, 43, 44 | M | Yes | Standard | V8.0: Moved rounding assumption to instructions V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: Update Assumptions v3.4: Update Assumptions V3.3: No Changes V3.2: Clarified rounding error assumption V3.1: Removed Block 4 (Frequency) Pilot: Changed to sample of CA; changed assumptions; changed instructions
117 | 29A201a | Yes | 29 | 29A2 | V8.0 | 2025-08-21 | Do MR values in customer reports and budget logs match? | X = ¦ Format 1 MR - Budget Log MR ¦ or ¦ CPD MR – Budget Log MR¦ | Y = Format 1 MR or CPD MR | X/Y = 0% | 20, 41 | M | No | Low | V8.0: Moved rounding assumption to instructions V7.0: Global 508 Formatting, No Changes V6.0: Updated to include IPMDAR; global formatting and Assumptions V5.0: No Changes V4.0: Updated Assumptions and Instructions V3.6: No Changes V3.5: No Changes v3.4: Update Attribute V3.3: No Changes V3.2: Clarified rounding error assumption V3.1: Removed Block 4 (Frequency) Pilot: Minor wording changes. Added assumption about negative MR. Approved.
118 | 29A201b | Yes | 29 | 29A2 | V8.0 | 2025-08-21 | Do UB values in customer reports and budget logs match? | X = ¦ Format 1/CPD UB - Budget Log UB ¦ | Y = Format 1/CPD UB | X/Y = 0% | 20, 41 | M | No | Low | V8.0: Moved rounding assumption to instructions V7.0: Global 508 Formatting, No Changes V6.0: Updated to include IPMDAR; global formatting and Assumptions V5.0: No Changes V4.0: Updated Assumptions and Instructions V3.6: No Changes V3.5: No Changes v3.4: Update Attribute V3.3: No Changes V3.2: Assumptions updated to state rounding error is applied to UB V3.1: Removed Block 4 (Frequency) Pilot: Minor wording changes. Added assumption about negative UB. Approved.
119 | 29A202a | No | 29 | 29A2 | V8.0 | 2024-12-06 | Are all MR transactions processed for purposes authorized by the system description? | X = Count of sampled MR transactions processed for purposes not authorized by the system description | n/a | X = 0 | 03, 41, 43 | M | Yes | Standard | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Instructions V3.6: No Changes V3.5: Update Assumptions v3.4: Update: Attribute, Test Metric, Metric Threshold, Assumptions, and Instructions V3.3: No Changes V3.2: Modified Assumption 1 V3.1: Removed Block 4 (Frequency) Pilot: Removed sample size. Approved.
120 | 29A203a | No | 29 | 29A2 | V8.0 | 2024-12-06 | Are all UB transactions processed for purposes authorized by the system description? | X = Count of sampled UB transactions processed for purposes not authorized by the system description | n/a | X = 0 | 03, 41, 43 | M | Yes | Standard | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Instructions V3.6: No Changes V3.5: Update Assumptions v3.4: Update: Attribute, Test Metric, Metric Threshold, Assumptions, and Instructions V3.3: No Changes V3.2: Modified Assumption 1 V3.1: Removed Block 4 (Frequency) Pilot: Removed sample size. Approved.
121 | 29A204a | Yes | 29 | 29A2 | V8.0 | 2025-08-21 | Are MR transactions accurately tracked? | X = ¦ (Previous period MR + sum (current period MR changes)) - current period MR ¦ | Y = Current period MR | X/Y ≤ 5% | 20, 41 | M | No | Low | V8.0: Moved rounding assumption to instructions V7.0: Global 508 Formatting, No Changes V6.0: Updated to include IPMDAR; global formatting and Assumptions V5.0: No Changes V4.0: Updated Assumptions and Instructions V3.6: No Changes V3.5: No Changes v3.4: Update Attribute V3.3: No Changes V3.2: Assumptions updated to state rounding error is applied to MR. V3.1: Removed Block 4 (Frequency)
122 | 29A205a | Yes | 29 | 29A2 | V8.0 | 2025-08-21 | Are UB transactions accurately tracked? | X = ¦ (Previous period UB + sum (current period UB changes)) - current period UB ¦ | Y = Current period UB | X/Y ≤ 5% | 20, 41 | M | No | Low | V8.0: Moved rounding assumption to instructions V7.0: Global 508 Formatting, No Changes V6.0: Updated to include IPMDAR; global formatting and Assumptions V5.0: No Changes V4.0: Updated Assumptions and Instructions V3.6: No Changes V3.5: No Changes v3.4: Update Attribute V3.3: No Changes V3.2: Block 11 updated to state rounding error is applied to UB. V3.1: Removed Block 4 (Frequency)
123 | 29A401a | No | 29 | 29A4 | V8.0 | 2024-12-06 | Are there changes to open WPs? | X = Count of prior period open WPs where current month BAC ≠ previous month BAC | n/a | X = 0 | 13, 44 | A | No | Standard | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: Updated Test Metric, Threshold, Data Elements and Instructions V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6: Update Test Metric, and Instructions V3.5: Update Data Elements and Instructions v3.4: Update Attribute V3.3: Added Assumption 3, Deleted Instruction 6, Added Data Element ACWPCUM V3.2: Add Data Element BCWPCUM V3.1: Updated assumptions, Removed Block 4 (Frequency) Pilot: Removed references to actual costs incurred; changed assumption defining an "open" WP.
124 | 29A501a | No | 29 | 29A5 | V8.0 | 2024-12-06 | Are PMB changes being controlled in the freeze period per the system description? | X = Count of sampled PMB changes that are within the freeze period which do not meet the allowable System Description exceptions | n/a | X = 0 | 03, 18, 43 | M | Yes | Standard | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Instructions V3.6: Update Instructions V3.5: Update Assumptions v3.4: Update: Test Metric, Metric Threshold, Assumptions, and instructions V3.3: No Changes V3.2: Modified Assumption 1 V3.1: Removed Block 4 (Frequency) Pilot: Removed sample size. Approved.
125 | 29A501c | Yes | 29 | 29A5 | V8.0 | 2025-08-21 | Are changes being controlled in the freeze period? | X = Sum of ¦(Cost Data sum of BCWSCUR for the current period as of prior period) – (Cost Data sum of BCWSCUR for the current period as of current period)¦ for the last 2 reporting periods | Y = Sum of ¦Cost Data sum of BCWSCUR for the current period as of current period¦ for the last 2 reporting periods | X/Y ≤ 10% | 02, 13 | A | No | Standard | V8.0: Updated to lower level of testing to WP level and clarify how to handle added/deleted WPs V7.0: Global 508 Formatting, No Changes V6.0: NEW replaced 29A501b
126 | 29A601a | No | 29 | 29A6 | V8.0 | 2024-12-06 | Is all effort detailed planned within the current rolling wave/freeze period? | X = Count of PPs/SLPPs where baseline start precedes the next rolling wave cycle | Y = Total count of PPs/SLPPs | X/Y ≤ 10% | 02, 03, 13, 44 | M | No | Standard | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6: Update Assumptions and Instructions V3.5: Update Test Step and Assumptions v3.4: Update: Data Elements Required and Assumptions V3.3: No Changes V3.1: New metric approved at NOV2018 CCB
127 | 29I401a | No | 29 | 29I4 | V8.0 | 2024-12-06 | Are baseline dates being updated to mask legitimate variances? | X = Count of sampled baseline date changes without substantiation | n/a | X = 0 | 03, 11, 18, 43, 45 | A/M | Yes | Standard | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Test Metric, Data Elements Required, Assumptions, and Instructions V3.6.1: Update Test Step, Assumptions, and Instructions. V3.6: No Changes V3.5: Update Assumptions v3.4: Update: Test Metric, Metric Threshold, Assumptions, and Instructions V3.3: Updated blocks 10, 11, and 12. Clarified sampling methodology of Non-LOE tasks/activities & milestones. V3.1: Removed Block 4 (Frequency)
128 | 29I402a | Yes | 29 | 29I4 | V8.0 | 2025-08-21 | Are budgets for LOE effort based on a sound basis of estimate and time-phased to properly reflect when the work will be accomplished? | X = Count of LOE CAs/WPs where the first ACWP was 3 reporting periods or more before the first BCWS | Y = Total count of LOE CAs/WPs | X/Y = 0% | 13, 44 | A/M | No | Conditional | V8.0: Updated Assumption to include rounding V7.0: Global 508 Formatting, Update Data Elements Required and Assumptions V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6.1: Update Test Step, Test Metric, Data Elements Required, Assumptions, and Instructions. V3.6: New metric approved at JUL2020 CCB
129 | 29I402b | No | 29 | 29I4 | V8.0 | 2024-12-06 | Are budgets for LOE effort based on a sound basis of estimate and time-phased to properly reflect when the work will be accomplished? | X = Count of LOE CAs/WPs where the first BCWS was 3 reporting periods or more before the first ACWP | Y = Total count of LOE CAs/WPs | X/Y = 0% | 13, 44 | A/M | No | Standard | V8.0: No Changes V7.0: Global 508 Formatting, Update Data Elements Required and Assumptions V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required and Instructions V3.6.1: Update Test Step, Test Metric, Data Elements Required, Assumptions, and Instructions. V3.6: New metric approved at JUL2020 CCB
130 | 29I402c | No | 29 | 29I4 | V8.0 | 2024-12-06 | Are budgets for LOE effort based on a sound basis of estimate and time-phased to properly reflect when the work will be accomplished? | X = Count of LOE CAs/WPs where the last ACWP was 3 reporting periods or more before the last BCWS | Y = Total count of LOE CAs/WPs | X/Y = 0% | 13, 44 | A/M | No | Conditional | V8.0: No Changes V7.0: Global 508 Formatting, Update Data Elements Required and Assumptions V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6.1: Update Test Step, Test Metric, Data Elements Required, Assumptions, and Instructions. V3.6: New metric approved at JUL2020 CCB
131 | 29I402d | No | 29 | 29I4 | V8.0 | 2024-12-06 | Are budgets for LOE effort based on a sound basis of estimate and time-phased to properly reflect when the work will be accomplished? | X = Count of LOE CAs/WPs where the last BCWS was 3 reporting periods or more before the last ACWP | Y = Total count of LOE CAs/WPs | X/Y = 0% | 13, 44 | A/M | No | Conditional | V8.0: No Changes V7.0: Global 508 Formatting, Update Data Elements Required and Assumptions V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required and Instructions V3.6.1: Update Test Step, Test Metric, Data Elements Required, Assumptions, and Instructions. V3.6: New metric approved at JUL2020 CCB
132 | 30A101d | Yes | 30 | 30A1 | V8.0 | 2025-08-21 | Are retroactive changes being made to cumulative BCWS? | X = Sum of BCWSCUM for WPs where (reporting period BCWSCUM - reporting period BCWSCUR) ≠ prior reporting period BCWSCUM | Y = Total BCWSCUM for all WPs | X/Y ≤ 5% | 13, 44 | A | No | Low | V8.0: Moved assumption into instruction to clarify where step rounding error was applied. V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: No Changes V3.4: No Changes V3.3: Added Assumption 3 for clarification V3.1: Changed from count to sum and updated assumptions, Removed Block 4 (Frequency)
133 | 30A101e | Yes | 30 | 30A1 | V8.0 | 2025-08-21 | Are retroactive changes being made to cumulative BCWP? | X = Sum of BCWPCUM for all WPs where (reporting period BCWPCUM - reporting period BCWPCUR) ≠ prior reporting period BCWPCUM | Y = Total BCWPCUM for all WPs | X/Y ≤ 5% | 13, 44 | A | No | Low | V8.0: Moved rounding assumption to instructions V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: No Changes V3.4: No Changes V3.3: Added Assumption 3 for clarification V3.1: Changed from count to sum and updated assumptions, Removed Block 4 (Frequency)
134 | 30A101f | Yes | 30 | 30A1 | V8.0 | 2025-08-21 | Are retroactive changes being made to cumulative ACWP? | X = Sum ACWPCUM for all CAs/WPs where (reporting period ACWPCUM - reporting period ACWPCUR) ≠ prior period ACWPCUM | Y = Total ACWPCUM for all CAs/WPs | X/Y ≤ 5% | 13, 44 | A | No | Low | V8.0: Moved assumption into instruction to clarify where step rounding error was applied. V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Test Type, Data Elements Required, Assumptions, and Instructions V3.6: No Changes V3.5: No Changes V3.4: No Changes V3.3: Added Assumption 4 for clarification V3.2: Added “CAs” to align with Block 11 assumption referencing the test to be conducted at the level at which actual costs are collected. V3.1: Changed from count to sum and updated assumptions, Removed Block 4 (Frequency) Pilot: Added assumption about level where actuals collected. Approved.
135 | 31A101a | No | 31 | 31A1 | V8.0 | 2024-12-06 | Do all CBB or TAB changes in the baseline control log have approved contractual documentation prior to incorporation? | X = Count of sampled CBB/TAB changes that do not have contractual authorization prior to incorporation | Y = Total count of sampled CBB/TAB changes | X/Y = 0% | 06, 41 | M | Yes | Low | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Instructions V3.6: No Changes V3.5: Update Assumptions v3.4: Update Assumptions V3.3: No Changes V3.1: Removed Block 4 (Frequency) Pilot: Minor wording changes. Approved.
136 | 32A101a | Yes | 32 | 32A1 | V8.0 | 2025-08-21 | Do the authorized budget changes in the baseline change log trace to the IPMR/CPR/IPMDAR? | X = ¦Net change in PMB from baseline change log - Net change in PMB from IPMR/CPR/IPMDAR¦ for the selected reporting period | Y = ¦Net change in PMB from baseline change log for the selected reporting period¦ | X/Y ≤ 5% | 18, 20 | M | No | Low | V8.0: Moved assumption into instruction to clarify where step rounding error was applied. V7.0: Global 508 Formatting, No Changes V6.0: Updated to include IPMDAR; global formatting and Assumptions V5.0: No Changes V4.0: Updated Assumptions and Instructions V3.6: No Changes V3.5: No Changes V3.4: No Changes V3.3: No Changes V3.2: Assumptions updated IPMR/CPR rounding error to align with other test metrics V3.1: Removed Block 4 (Frequency) Pilot: Minor wording changes. Approved.
137 | 32A101b | No | 32 | 32A1 | V8.0 | 2024-12-06 | Do the authorized budget changes in the change logs trace to the baseline change documentation? | X = Sum of the budget change values from sampled baseline log changes that do not trace to the baseline change documentation IAW contractor procedures | Y = Total sum of the sampled budget change values from the baseline change log | X/Y ≤ 5% | 18, 43 | M | Yes | Standard | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Instructions V3.6: No Changes V3.5: Update Assumptions v3.4: Update Instructions V3.3: No Changes V3.1: Removed Block 4 (Frequency) Pilot: Removed assumption. Approved.
138 | 32A102a | No | 32 | 32A1 | V8.0 | 2024-12-06 | Does the IMS incorporate the latest authorized changes? | X = Count of sampled baseline change documents where either the baseline start or baseline finish date has been incorrectly incorporated into the IMS | Y = Total count of sampled baseline change documents | X/Y ≤ 10% | 11, 43, 45 | M | Yes | Low | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Data Elements Required and Instructions V3.6: Update Test Metric V3.5: Update Assumptions v3.4: Update Assumptions V3.3: No Changes V3.1: Removed Block 4 (Frequency) Pilot: Minor changes. Approved.
139 | 32A104a | No | 32 | 32A1 | V8.0 | 2024-12-06 | Does the baseline change documentation provide substantiation for the change? | X = Count of sampled baseline change documents without substantiation | n/a | X = 0 | 18, 43 | M | Yes | Standard | V8.0: No Changes V7.0: Global 508 Formatting, No Changes V6.0: Global formatting and Assumptions V5.0: No Changes V4.0: Updated Instructions V3.6: No Changes V3.5: Update Assumptions v3.4: Update: Test Metric, Metric Threshold, Assumptions, and Instructions V3.3: No Changes V3.1: Removed Block 4 (Frequency) Pilot: Minor changes. Approved.
Note on P2: Griffin, Joshua K. (Kyle): Reference applicable Metric Specification Sheet for change history details.

## Artifacts and Data Elements
Artifact Name | Data Element
02 Accounting/Fiscal Calendar | A Accounting month dates
02 Accounting/Fiscal Calendar | B Beginning of period (BOP) dates
02 Accounting/Fiscal Calendar | C End of period (EOP) dates
03 EVM System Description | A Material categorization process
03 EVM System Description | B Internal replanning parameters
03 EVM System Description | C Permitted applications of MR
03 EVM System Description | D Permitted baseline changes during freeze period
03 EVM System Description | E Permitted changes to open WPs
03 EVM System Description | F Permitted EVTs for material
03 EVM System Description | G Permitted UB transactions
03 EVM System Description | H Planning window/freeze period
03 EVM System Description | J PMB incorporation timeframe
03 EVM System Description | K Process for incorporating indirect rates into budgets
03 EVM System Description | L Process for incorporating subcontractor/supplier MR
03 EVM System Description | M Requirements for EAC risk/opportunity incorporation
03 EVM System Description | N UB distribution timeframe
03 EVM System Description | P Variance analysis thresholds
03 EVM System Description | Q WBS reporting level requirements
03 EVM System Description | R Indirect Cost Management Organization
03 EVM System Description | S VAR requirements
03 EVM System Description | T Freeze period baseline change exceptions
03 EVM System Description | U Guidance on EVTs
03 EVM System Description | V Process for LOE/discrete work decomposition
03 EVM System Description | W CEAC Process/Requirements
04 Contract Statement of Work | A Contractual milestones
04 Contract Statement of Work | B SOW paragraphs
05 Contract Work Breakdown Structure Dictionary | A SOW references
06 Contractual Documents | A Contracts requiring EVMS
06 Contractual Documents | B Contractual milestones
06 Contractual Documents | C Contractual and/or CLIN Period of Performance (PoP)
06 Contractual Documents | D Requirement to report recurring/non-recurring costs
06 Contractual Documents | E Requirement to report unit or lot costs
06 Contractual Documents | F Subcontractor/Supplier EVMS flow-down requirements
06 Contractual Documents | G Contractual mods (authorization dates)
06 Contractual Documents | H Contractual mods adding/removing scope
07 Organization Breakdown Structure | A OBS elements
08 Control Account Plans | A Element of Cost (material)
09 Work Authorization Documentation (WAD) | A Approval date
09 Work Authorization Documentation (WAD) | B BAC
09 Work Authorization Documentation (WAD) | C Baseline Finish Date
09 Work Authorization Documentation (WAD) | D Baseline Start Date
09 Work Authorization Documentation (WAD) | E Current/previous CA BAC
09 Work Authorization Documentation (WAD) | F Period of Performance (PoP)
09 Work Authorization Documentation (WAD) | G Scope description
10 Integrated Master Plan | A IMP code
10 Integrated Master Plan | B Summary tasks
11 Integrated Master Schedule (IMS) | A Actual Finish Date
11 Integrated Master Schedule (IMS) | AA Leads
11 Integrated Master Schedule (IMS) | AB OBS elements
11 Integrated Master Schedule (IMS) | AC Planning Package UIDs
11 Integrated Master Schedule (IMS) | AD Predecessors
11 Integrated Master Schedule (IMS) | AE Predecessor (Type)
11 Integrated Master Schedule (IMS) | AF Remaining Duration
11 Integrated Master Schedule (IMS) | AG Status Date
11 Integrated Master Schedule (IMS) | AH Subcontractor/Supplier ID
11 Integrated Master Schedule (IMS) | AJ Successors
11 Integrated Master Schedule (IMS) | AK Successor (Type)
11 Integrated Master Schedule (IMS) | AL Summary Task UIDs
11 Integrated Master Schedule (IMS) | AM Task/Activity/Milestone UIDs
11 Integrated Master Schedule (IMS) | AN WBS elements
11 Integrated Master Schedule (IMS) | AP WP/PP/SLPP UIDs
11 Integrated Master Schedule (IMS) | AQ Duration/Forecast Duration
11 Integrated Master Schedule (IMS) | AR CA UIDs
11 Integrated Master Schedule (IMS) | AS Planning Level Code
11 Integrated Master Schedule (IMS) | AT ETC (time-phasing)
11 Integrated Master Schedule (IMS) | B Actual Finish Date (prior month)
11 Integrated Master Schedule (IMS) | C Actual Start Date
11 Integrated Master Schedule (IMS) | D Actual Start Date (prior month)
11 Integrated Master Schedule (IMS) | E Approved risk mitigation activities
11 Integrated Master Schedule (IMS) | F Baseline Duration
11 Integrated Master Schedule (IMS) | G Baseline Finish Date
11 Integrated Master Schedule (IMS) | H Baseline Finish Date (period to period comparison)
11 Integrated Master Schedule (IMS) | J Baseline Start Date
11 Integrated Master Schedule (IMS) | K Baseline Start Date (period to period comparison)
11 Integrated Master Schedule (IMS) | L BCWS (time-phasing)
11 Integrated Master Schedule (IMS) | M Beginning of period (BOP) dates
11 Integrated Master Schedule (IMS) | N Constraint Date
11 Integrated Master Schedule (IMS) | P Constraint Method Critical Path Activities
11 Integrated Master Schedule (IMS) | Q Constraint Type
11 Integrated Master Schedule (IMS) | R Contractual milestones
11 Integrated Master Schedule (IMS) | S End of period (EOP) dates
11 Integrated Master Schedule (IMS) | T EV % complete
11 Integrated Master Schedule (IMS) | U EVT
11 Integrated Master Schedule (IMS) | V Forecast Finish Date
11 Integrated Master Schedule (IMS) | W Forecast Start Date
11 Integrated Master Schedule (IMS) | X Total Float/Slack
11 Integrated Master Schedule (IMS) | Y IMP code
11 Integrated Master Schedule (IMS) | Z Lags
12 Program Critical Path | A Program Critical Path Activities
12 Program Critical Path | B Near-Critical Path Activities
12 Program Critical Path | C Driving Path Activities
13 EV Cost Tool Data | A Monthly overhead cost accumulation (by overhead pool)
13 EV Cost Tool Data | AA CA UIDs
13 EV Cost Tool Data | AB CAM assignment
13 EV Cost Tool Data | AC CPICUM (derived)
13 EV Cost Tool Data | AD Cumulative Cost Variance
13 EV Cost Tool Data | AE Cumulative Schedule Variance
13 EV Cost Tool Data | AF Current Cost Variance
13 EV Cost Tool Data | AG Current Schedule Variance
13 EV Cost Tool Data | AH EAC
13 EV Cost Tool Data | AJ Element of Cost
13 EV Cost Tool Data | AK Element of Cost (material)
13 EV Cost Tool Data | AL ETC
13 EV Cost Tool Data | AM ETC (time-phased)
13 EV Cost Tool Data | AN EV % complete
13 EV Cost Tool Data | AP EVT
13 EV Cost Tool Data | AQ Indirect rate table
13 EV Cost Tool Data | AR MR
13 EV Cost Tool Data | AS OBS elements
13 EV Cost Tool Data | AT Planning Package UIDs
13 EV Cost Tool Data | AU Subcontractor/Supplier ID
13 EV Cost Tool Data | AV Subcontractor/Supplier MR
13 EV Cost Tool Data | AW TCPIEAC (derived)
13 EV Cost Tool Data | AX UB
13 EV Cost Tool Data | AY Variance at Complete
13 EV Cost Tool Data | AZ WBS elements
13 EV Cost Tool Data | B Unburdened and burdened cost
13 EV Cost Tool Data | BA WP/PP/SLPP UIDs
13 EV Cost Tool Data | BB BCWPCUR (monthly historical)
13 EV Cost Tool Data | C ACWPCUM
13 EV Cost Tool Data | D ACWPCUM (current and prior month)
13 EV Cost Tool Data | E ACWPCUR
13 EV Cost Tool Data | EB ACWPCUR (monthly historical)
13 EV Cost Tool Data | F ACWPCUR (non-material)
13 EV Cost Tool Data | G ACWPCUR (of selected months)
13 EV Cost Tool Data | H BAC
13 EV Cost Tool Data | J BAC for CA
13 EV Cost Tool Data | K BAC for CA/SLPP
13 EV Cost Tool Data | L BAC for WP (current and prior month)
13 EV Cost Tool Data | M BAC for WP/PP
13 EV Cost Tool Data | N Baseline Finish Date
13 EV Cost Tool Data | P Baseline Start Date
13 EV Cost Tool Data | Q BCWPCUM
13 EV Cost Tool Data | R BCWPCUM (current and prior month)
13 EV Cost Tool Data | S BCWPCUR
13 EV Cost Tool Data | T BCWPCUR (non-material)
13 EV Cost Tool Data | U BCWS (time-phasing)
13 EV Cost Tool Data | V BCWSCUM
13 EV Cost Tool Data | W BCWSCUM (current and prior month)
13 EV Cost Tool Data | X BCWSCUR
13 EV Cost Tool Data | Y BCWSCUR for CA
13 EV Cost Tool Data | Z BCWSCUR for WP and PP
14 Accounting System Data | A Capability to report recurring/non-recurring costs
14 Accounting System Data | B Capability to report unit or lot costs
14 Accounting System Data | C Contract level cumulative actual direct costs
14 Accounting System Data | E Direct/indirect rates
14 Accounting System Data | F Indirect rates (rate table)
14 Accounting System Data | G Material transfers/loans
14 Accounting System Data | H Contract Level Cumulative Actual Indirect Costs
15 Internal Variance Analysis Thresholds | A Internal variance analysis thresholds
16 Internal Variance Analysis Reports | A VARs
17 Variance Analysis Reports (VARs) | A Indirect VARs
17 Variance Analysis Reports (VARs) | B Price Variance (PV) formula
17 Variance Analysis Reports (VARs) | C Usage Variance (UV) formula
17 Variance Analysis Reports (VARs) | D VARs
17 Variance Analysis Reports (VARs) | E Rate Variance (RV) Formula
17 Variance Analysis Reports (VARs) | F Volume Variance (VV) Formula
18 Baseline Control Logs | A Baseline changes (effective dates)
18 Baseline Control Logs | B Baseline changes (selected)
18 Baseline Control Logs | C Baseline changes involving budget distributions
18 Baseline Control Logs | D Baseline changes involving UB transactions
18 Baseline Control Logs | E Budget change values
18 Baseline Control Logs | F CBB
18 Baseline Control Logs | G Date of contractual mod incorporation into PMB
18 Baseline Control Logs | H OTB budget
18 Baseline Control Logs | J PMB change
18 Baseline Control Logs | K UB
18 Baseline Control Logs | L UB distributions
19 Corrective Action Log | A Corrective action log entries
19 Corrective Action Log | B Corrective action log status date
19 Corrective Action Log | C Estimated completion dates (open corrective actions)
20 IPMR/CPR/IPMDAR | A Format 1 BCWSCUM / CPD BCWS (To Date)
20 IPMR/CPR/IPMDAR | B Format 1 BCWSCUR / CPD BCWS (To Date)
20 IPMR/CPR/IPMDAR | C Format 1 current period MR / CPD Summary Performance
20 IPMR/CPR/IPMDAR | D Format 1 current period UB / CPD Summary Performance
20 IPMR/CPR/IPMDAR | E Format 1 Date of OTB/OTS / CPD Contract Data
20 IPMR/CPR/IPMDAR | F Format 1 EACs (Best, Worst, Most Likely) / CPD Contract Data
20 IPMR/CPR/IPMDAR | G Format 1 lowest reporting-level WBS elements / CPD WBS
20 IPMR/CPR/IPMDAR | H Format 1 LRE / CPD EST (To Complete)
20 IPMR/CPR/IPMDAR | J Format 1 MR / CPD Summary Performance
20 IPMR/CPR/IPMDAR | K Format 1 PMB / CPD Summary Performance
20 IPMR/CPR/IPMDAR | L Format 1 previous period MR / CPD Summary Performance (prior period)
20 IPMR/CPR/IPMDAR | M Format 1 previous period UB / CPD Summary Performance
20 IPMR/CPR/IPMDAR | N Format 1 TAB / CPD Contract Data
20 IPMR/CPR/IPMDAR | P Format 1 UB / CPD Summary Performance
20 IPMR/CPR/IPMDAR | Q Format 2 OBS elements / CPD OBS
20 IPMR/CPR/IPMDAR | R Format 3 beginning of period BCWS
20 IPMR/CPR/IPMDAR | S Format 3 PMB net change (derived)
20 IPMR/CPR/IPMDAR | T Format 5 / Performance Narrative Report EAC rationale
20 IPMR/CPR/IPMDAR | U Format 5 / Performance Narrative Report VARs
20 IPMR/CPR/IPMDAR | V Format 5 / Performance Narrative Report VARs requiring corrective actions
20 IPMR/CPR/IPMDAR | W Format 5 / Performance Narrative Report IMS discussion of schedule margin
20 IPMR/CPR/IPMDAR | X Format 1 CBB / CPD Contract Data
20 IPMR/CPR/IPMDAR | Y Format 1 NCC / CPD Contract Data
20 IPMR/CPR/IPMDAR | Z Format 1 AUW / CPD Contract Data
20 IPMR/CPR/IPMDAR | AA Format 1 OTB/reprogramming budget / CPD Programming Adjustments
21 List of Major Subcontractors/Suppliers
22 Subcontractor/Supplier IPMR/CPR/IPMDAR | A ACWPCUM / CPD Summary Performance
22 Subcontractor/Supplier IPMR/CPR/IPMDAR | B BAC / CPD Summary Performance
22 Subcontractor/Supplier IPMR/CPR/IPMDAR | C BCWPCUM / CPD Summary Performance
22 Subcontractor/Supplier IPMR/CPR/IPMDAR | D BCWSCUM / CPD Summary Performance
22 Subcontractor/Supplier IPMR/CPR/IPMDAR | E Subcontractor/Supplier MR / CPD Summary Performance
22 Subcontractor/Supplier IPMR/CPR/IPMDAR | F ACWPCUR / CPD ACWP (To Date)
22 Subcontractor/Supplier IPMR/CPR/IPMDAR | G BCWPCUR / CPD BCWP (To Date)
22 Subcontractor/Supplier IPMR/CPR/IPMDAR | H BCWSCUR / CPD BCWS (To Date)
23 CAS Disclosure Statement | A Indirect cost pools
23 CAS Disclosure Statement | B Method of application of indirect rates to direct costs
23 CAS Disclosure Statement | C Indirect Cost Management Authority/Responsibility
23 CAS Disclosure Statement | D Process for updating and applying indirect rates
24 FPRA/FPRP (or published rates) | A Direct/indirect rates
24 FPRA/FPRP (or published rates) | B Overhead categories/departments
24 FPRA/FPRP (or published rates) | C Published indirect rates
25 Customer Approval for OTB | A OTB approval
25 Customer Approval for OTB | B OTB budget
28 Risk & Opportunities Log/Register | A Approved risk mitigation activities
28 Risk & Opportunities Log/Register | B Factored risks/opportunities
29 MRP/ERP System Data | A Material items issued to contract
29 MRP/ERP System Data | B Material transfers/loans
29 MRP/ERP System Data | C Material Need dates based on Material Category
32 Quantifiable Backup Data | A EV % complete
32 Quantifiable Backup Data | B QBD Steps and Weights
33 Comprehensive EAC Documentation | A CEAC commencement and completion dates
36 Program Detail Schedules | A Baseline Finish Date
36 Program Detail Schedules | B Baseline Start Date
36 Program Detail Schedules | C Forecast Finish Date
36 Program Detail Schedules | D Forecast Start Date
36 Program Detail Schedules | E Actual Start Date
36 Program Detail Schedules | F Actual Finish Date
37 Subcontractor/Supplier Schedule (IMS) | A Baseline Finish Date
37 Subcontractor/Supplier Schedule (IMS) | B Baseline Start Date
37 Subcontractor/Supplier Schedule (IMS) | C Forecast Finish Date
37 Subcontractor/Supplier Schedule (IMS) | D Forecast Start Date
37 Subcontractor/Supplier Schedule (IMS) | E Actual Start Date
37 Subcontractor/Supplier Schedule (IMS) | F Actual Finish Date
37 Subcontractor/Supplier Schedule (IMS) | G Task/Milestone UIDs
38 Contract WBS | A Lowest reporting-level WBS elements
39 Organizational Charts | A Indirect Cost Management Organization
39 Organizational Charts | B OBS elements
41 Budget Log | A Baseline changes
41 Budget Log | B CBB/TAB changes (effective dates)
41 Budget Log | C Current period MR changes
41 Budget Log | D Current period UB changes
41 Budget Log | E Current/previous CA BAC
41 Budget Log | F MR
41 Budget Log | G MR transactions
41 Budget Log | H Scope description
41 Budget Log | J UB
41 Budget Log | K UB transactions
43 Baseline Change Request | A Baseline change substantiation
43 Baseline Change Request | B Baseline Finish Date
43 Baseline Change Request | C Baseline Start Date
43 Baseline Change Request | D Budget change values
43 Baseline Change Request | E MR transaction substantiation
43 Baseline Change Request | F Scope description
43 Baseline Change Request | G UB transaction substantiation
46 IPMR/CPR/IPMDAR CDRL | A VAR thresholds/requirements
46 IPMR/CPR/IPMDAR CDRL | B WBS reporting level requirements
49 Estimated Actuals Reconciliation | A Estimated actual costs
49 Estimated Actuals Reconciliation | B Estimated actual costs (supporting documentation)
50 Cost Tool Calendar | A Beginning of period (BOP) dates
50 Cost Tool Calendar | B End of period (EOP) dates
52 EVMS Analysis Tool Data | A Cumulative Cost Variance
52 EVMS Analysis Tool Data | B Cumulative Schedule Variance
52 EVMS Analysis Tool Data | C Current Cost Variance
52 EVMS Analysis Tool Data | D Current Schedule Variance
52 EVMS Analysis Tool Data | E Variance at Complete
53 Resource Plans | A ETC (time-phased)
54 Actual Cost Reconciliation | A Actual cost reconciliation
55 BOM | A Material items issued to contract
56 CSDR | A Lowest reporting-level WBS elements
57 Customer Approval for OTS | A OTS approval
58 Other Lower Level/Supplemental Schedules (e.g., MRP/ERP System) | A Baseline Finish Date
58 Other Lower Level/Supplemental Schedules (e.g., MRP/ERP System) | B Baseline Start Date
58 Other Lower Level/Supplemental Schedules (e.g., MRP/ERP System) | C Forecast Finish Date
58 Other Lower Level/Supplemental Schedules (e.g., MRP/ERP System) | D Forecast Start Date
59 RAM | A CAM assignment
60 Letter of Accounting System Approval from ACO or other cognizant authority | A Accounting System Approval
61 Letter of MMAS Approval from ACO or other cognizant authority | A MMAS Approval

## Artifact Descriptions
Data Item List All data are required in electronic format. PDF files are not considered electronic format, unless they are used to improve data or augment information (such as hand-writing, additional comments, and/or signatures). Please provide data in a file structure using the outline given below with descriptive file names. Provide subfolders for each contract with each maintaining the sequence given below. Artifact names and numbers can change over time so please review the data prior to submittal.
Request Date: |  | Requested Data Delivery Date:
Artifact # | Artifact Name | Artifact Description | Periodicity
01 | Program Summary Data | For each program provide the below items in one excel file
Integrated Master Plan (IMP) on Contract? (Yes/No)
# of IMP Codes
Freeze Period (i.e. 60 days)
Number of Work Packages (WP)
Number of Control Accounts (CA)
02 | Accounting Fiscal Calendar | Fiscal Calendar Used (include all accounting periods from beginning of program until program completion)
03 | EVM System Description | System Descriptions, corporate operating instructions, standard operating procedures, and program unique directives/procedures. (Include the latest approved versions)
04 | Contract Statement of Work | Contract Statement of Work
05 | Contract Work Breakdown Structure Dictionary | Contract Work Breakdown Structure Dictionary. Include reference ID to the SOW.
06 | Contractual Documents | Initial contract, and contract modifications since program inception, e.g., contract modification, letter to proceed from contracts office or legal office, not-to-exceed letter, change order, engineering change order, delivery order, basic ordering agreement, etc.
Comprehensive list by date, dollar value, funding and changes to the contract target cost.
Electronic copies of all contract mods for the last 12 months.
07 | Organization Breakdown Structure | Provide in organization chart form, to include OBS codes which align to those in RAM, as well as names of personnel responsible for each organizational function who have authority to commit resources. OBS also needs to include major subcontractors/suppliers.
08 | Control Account Plan (CAP) | Control Account Plans (CAP) by element of cost (i.e., labor hours and dollars, material dollars and other direct cost dollars) and their associated burdens and overhead costs. Must include any Summary Level Planning Packages (SLPPs). Provide these CAPs in the form of an excel export.
09 | Work Authorization Documentation (WAD) | Work Authorization Documents for entire program.
10 | Integrated Master Plan (IMP) | Integrated Master Plan (IMP) if on Contract.
11 | Integrated Master Schedule (IMS) | Integrated Master Schedule including summary, intermediate and detailed schedules. Provide backups directly from the scheduling tool (native format).
12 | Program Critical Path | Provide the program latest critical path. Include a list of the settings used during the critical path calculation including the status date, calendar and any calculation options that could impact how the tool calculates critical path. Also, include critical path procedure(s) and/or references to critical path procedure(s) in system description (or other applicable documents)
13 | EV Cost Tool Data | “Data shall be provided for all reporting periods from contract start and include all records down to the work package (WP) level. The data must include unique identifier(s) that allows for Summary Level Planning Packages (SLPP), Control Account (CA) and WP comparison. Dollars ($s), thousands of dollars (K$s) or hours must be identified as such. In addition to the data export, provide a data dictionary for all codes used in the requested fields.”
Unique ID
Control account ID
Work package ID
Planning package and work package indicator (e.g., PP, WP, SLPP)
Description
WBS
OBS
Subcontractor/Supplier ID/Name
CAM name
Earned Value Technique (EVT)
Element of Cost (EOC)
Reporting period (month and year)
Baseline Start
Baseline Finish
|  | Actual Start | Monthly
|  | Actual Finish | Annual
|  | Forecast Start | Quarterly
|  | Forecast Finish | Annual
|  | Current BCWS | Annual
|  | Current BCWP | Monthly
Current ACWP
CUM BCWS
CUM BCWP
CUM ACWP
BAC
EAC
ETC
Current Cost Variance
Current Schedule Variance
Cumulative Cost Variance
Cumulative Schedule Variance
Variance at Complete
14 | Accounting System Data | See specific testing information
15 | Internal Variance Analysis Thresholds | Internal variance analysis thresholds
16 | Internal Variance Analysis Reports | Internal Variance Analysis Reports (VARs)
17 | Variance Analysis Reports (VARs) | Variance Analysis Reports (VARs) (Direct/Indirect)
18 | Baseline Control Logs | Baseline Control Logs
Management Reserve (MR)
Undistributed Budget (UB)
Performance Measurement Baseline (PMB) and/or Contract Budget Base (CBB)
19 | Corrective Action Log | Corrective Action Tracking System Log or database
20 | IPMR/CPR/IPMDAR | Integrated Program Management Report (IPMR)/Contract Performance Report (CPR)/Integrated Program Management Data and Analysis Report (IPMDAR)*
Format 1
Format 2
Format 3
Format 5
Contract Performance Dataset (CPD)*
Schedule Performance Dataset (SPD)*
Native Schedule File*
Performace Narrative Report*
21 | List of Major Subcontractors/Suppliers | List of Major Subcontractors/Suppliers & intra-organizational elements w/EVMS flow down
22 | Subcontractor/Supplier IPMR/CPR/IPMDAR | Subcontractor/Supplier IPMR/CPR (All Formats); Subcontractor/Supplier IPMDAR
23 | CAS Disclosure Statement | CAS Disclosure Statement and any applicable policies and procedures, desk instructions, etc., addressing the accounting process
24 | FPRA/FPRP (or published rates) | Forward Pricing Rate documentation, at time of program baseline, last OTB - if applicable, and start of current fiscal year. (Provide most recent FPRA, FPRP being utilized.)
25 | Customer Approval for OTB
26 | CBAR - MMAS, Accounting System Status
27 | CFSR
28 | Risk & Opportunities Log/Register
29 | MRP/ERP System Data
32 | Quantifiable Backup Data
33 | Comprehensive EAC Documentation
34 | Mapping of EVMS Data from Sub to Prime
35 | Intermediate Schedules
36 | Program Detail Schedules
37 | Subcontractor/Supplier Schedule (IMS)
38 | Contract WBS
39 | Organizational Charts
40 | Program WBS
41 | Budget Log
42 | wInsight Data (or equivalent) | wInsight .wsa files (entire program at lowest level produced from cost tool).
43 | Baseline Change Request | or equivalent Baseline Change Documentation
44 | Cost Data Dictionary
45 | IMS Data Dictionary
46 | IPMR/CPR CDRL
47 | IMS CDRL
48 | CAS Disclosure Statement Approval
49 | Estimated Actuals Reconciliation | To include supporting documentation (eg, invoices, emails, subcontractor CPR)
50 | Cost Tool Calendar
51 | LOE Justification
52 | EVMS Analysis Tool Data
53 | Resource Plans
54 | Actual Cost Reconciliation
55 | BOM
56 | CSDR
57 | Customer Approval for OTS
58 | Other Lower Level/Supplemental Schedules (e.g., MRP/ERP System)
59 | RAM
60 | Letter of Accounting System Approval from ACO or other cognizant authority
61 | Letter of MMAS Approval from ACO or other cognizant authority
62 | Risk Management Process/ Plan

## Deleted Metrics Archive
Metrics Archive - purpose is to show the history of metrics that were deleted from the pilot phase until time now
Unique Test Metric ID | Attribute ID | Status | Test Metric Rev Date | Test Step | Test Metric Numerator (X) | Test Metric Denominator (Y) | Metric Threshold | Min Freq | Artifacts | Test Type | Comments | Status
03A103a | 03A1 | Deleted Durring Aug 2025 CCB | 2025-08-21 | Do the forecast start and finish dates in the subcontractor/supplier IMS reconcile to the prime IMS? | X = Count of sampled incomplete tasks/activities & milestones in the subcontractor/supplier IMS with a forecast start/finish date that cannot be reconciled to the forecast start/finish date in the prime IMS | Y = Total count of sampled incomplete subcontractor/supplier tasks/activities & milestones in the prime contractor IMS | X/Y ≤ 5% |  | 03, 11, 37, 45 | M | v7.0 Update layout for Section 508 Accessibility Compliance v6.0 Update layout for Section 508 Accessibility Compliance v5.0 No changes – updated to v5.0 v4.0 Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 45 to supplement artifact 11 & updated blk 10 to align with test requirements. Added “/supplier” (lower level IMS must support prime IMS) regardless of EVMS flow down. Replaced "discrepancy" for "deficiency" - to be consistent with the overarching 2303-01. Updated asm 3 blk 9 to align definition of IMS “incomplete” with DECM verbiage for consistency. v3.6.1 Re-defined incomplete. Added “tasks” and “& milestones” in block 11 and 12. Updated data elements in block 10 for consistency v3.6 No changes – updated to v3.6 v3.5 Update Assumptions v3.4 Update Assumptions v3.3 No changes – updated to v3.3 v3.1 Removed Block 4 (Frequency) v3.0 Minor changes v2.1 Integration – updated data elements v2.0 CCB - validated v1.0 Initial CCB | DELETED
03A103b | 03A1 | Deleted Durring Aug 2025 CCB | 2025-08-21 | Do the baseline start and finish dates in the subcontractor/supplier IMS reconcile to the prime IMS? | X = Count of sampled incomplete tasks/activities & milestones in the subcontractor/supplier IMS with a baseline start/finish date that cannot be reconciled to the baseline start/finish date in the prime IMS | Y = Total count of sampled incomplete subcontractor/supplier tasks/activities & milestones in the prime contractor IMS | X/Y ≤ 5% |  | 03, 11, 37, 45 | M | v7.0 Update layout for Section 508 Accessibility Compliance v6.0 Update layout for Section 508 Accessibility Compliance v5.0 No changes – updated to v5.0 v4.0 Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 45 to supplement artifact 11 & updated blk 10 to align with test requirements. Added “/supplier” (lower level IMS must support prime IMS) regardless of EVMS flow down. Replaced "discrepancy" for "deficiency" - to be consistent with the overarching 2303-01. Updated asm 3 blk 9 to align definition of IMS “incomplete” with DECM verbiage for consistency. v3.6.1 Re-defined incomplete. Added “tasks” and “& milestones” in block 11 and 12. Updated data elements in block 10 for consistency v3.6 Update Test Metric v3.5 Update Assumptions v3.4 Update Assumptions v3.3 No changes – updated to v3.3 v3.1 Removed Block 4 (Frequency) v3.0 Minor changes v2.1 Integration – updated data elements v2.0 CCB - validated v1.0 Initial CCB | DELETED
26A202a | 26A2 | Deleted Durring Aug 2025 CCB | 2025-08-21 | Are corrective actions being monitored to the point of resolution and closure? | X = Count of open corrective actions with estimated completion dates before time now | Y = Total count of open corrective actions | X/Y ≤ 10% |  | 19 | M | v7.0 Update layout for Section 508 Accessibility Compliance v6.0 Update layout for Section 508 Accessibility Compliance v5.0 No changes – updated to v5.0 v4.0 Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. v3.6 No changes – updated to v3.6 v3.5 No changes – updated to v3.5 v3.4 Update Attribute v3.3 No changes – updated to v3.3 v3.1 Removed Block 4 (Frequency) v3.0 No changes – updated to 3.0 v2.1 Integration – updated data elements v2.0 CCB - validated v1.0 Initial AMR CCB | DELETED
29A501b | 29A5 | DELETED DURING DEC 2022 CCB | 2022-12-05 | Are changes being controlled in the freeze period per the system description? | X = Sum of ¦(Format 3 beginning of period BCWS) – (Format 1 BCWSCUR)¦ for the last 6 reporting periods | Y = Sum of BCWSCUR for the last 6 reporting periods | X/Y ≤ 10% |  | 03, 20 | M | V5.0: No Changes V4.0: Updated Instructions V3.6: No Changes V3.5: No Changes V3.4: No Changes V3.3: No Changes V3.1: Removed Block 4 (Frequency) | DELETED
10A202a | 10A2 | DELETED DURING JAN 2021 CCB | 2020-08-30 | Is material segregated from other non-material direct elements of cost within work packages? | X = Count of incomplete material WPs that contain a second non-material direct element of cost. | n/a | X = 0 |  | 13 | M | V3.6: Update Assumptions V3.5: Update Test Step, Test Metric, and Instructions v3.4: Update Attribute V3.3: No Changes V3.1: Removed Block 4 (Frequency) Pilot: New test to ensure material EOC is segregated from other elements | DELETED
10A109a | 10A1 | DELETED DURING JAN 2020 CCB | 2019-08-31 | Does each WP/PP have an assigned budget? | X = Count of WPs, PPs, and SLPPs with BAC ≤ 0 and ¦ ACWPCUM ¦ ≥ $100 | Y = Total count of WPs, PPs, and SLPPs | X/Y ≤ 5% |  | 13 | A | v3.4: Update Attribute V3.3: Added Assumption 3 V3.1: Changed to all WPs, PPs, and SLPPs, Removed Block 4 (Frequency) Pilot: Eliminated testing of closed WPs; Keep as a count of WPs | DELETED
10I101a | 10I1 | DELETED DURING JAN 2020 CCB | 2019-08-31 | Are PPs/SLPPs detail planned prior to the freeze period? | X = Count of PPs/SLPPs that have baseline start dates within the freeze period | Y = Total count of PPs/SLPPs | X/Y ≤ 10% |  | 03, 13 | A | v3.4: Update: Data Elements Required and Assumptions V3.3: All legacy revisions are kept from metric 10A301a in this log, which this new metric (10I101a) replaced – This is the Initial Revision for 10I101a V3.1: Change to Automated and limited to Freeze Period, Removed Block 4 (Frequency) | DELETED
22I101a | 22I1 | DELETED DURING JAN 2020 CCB | 2019-08-31 | Is the reported BCWP consistent with the method used to plan and budget the associated work? | X = Count of a sample of in-progress discrete WPs that have a reported BCWPCUR that is not consistent with the budget and EVT | Y = Total count of sampled in-progress discrete WPs | X/Y ≤ 10% |  | 13, 32 | M | v3.4: Update: Test Metric and Assumptions V3.3: No Changes V3.1: Removed Block 4 (Frequency) Pilot: New intent metric added. (Note: Check 10A105a for redundancy) | DELETED
19A301a | 19A3 | DELETED JUL 2019 CCB | 2019-05-24 | Does ACWPCUM in the EVMS reconcile to actual costs in the accounting system? | X = Sum of actual indirect costs that do not reconcile between the EVMS and the Accounting System | Y = Sum of total indirect ACWPCUM from the EVMS | X/Y ≤ 1% |  | 13, 14, 54 | M | DELETED: Replaced with 19A401a V3.3: Added Data Element V3.1: Defining incomplete WPs, PPs, and SLPPs in IMS as no actual finish date, Removed Block 4 (Frequency) Pilot: Frequency changed to quarterly; threshold at 15% | DELETED
06A206a | 06A2 | DELETED JUL 2019 CCB | 2019-05-24 | Are leads used in the schedule? | X = Count of incomplete tasks/activities & milestones with at least one lead in the predecessor logic in the IMS | Y = Total count of incomplete tasks/activities & milestones in the IMS | X/Y ≤ 2% |  | 11 | A | DELETED: Leads are part of 06A212a V3.3: Added Data Element V3.1: Defining incomplete WPs, PPs, and SLPPs in IMS as no actual finish date, Removed Block 4 (Frequency) Pilot: Frequency changed to quarterly; threshold at 15% | DELETED
06A203a | 06A2 | DELETED JUL 2019 CCB | 2019-05-24 | Are start-finish relationships used in the schedule? | X = Count of incomplete tasks/activities & milestones in the IMS with at least one start-to-finish predecessor | Y = Total count of incomplete tasks/activities & milestones in the IMS | X/Y = 0% |  | 11 | A | DELETED: start-finish relationships are part of 06A212a V3.3: Added Data Element V3.1: Defining incomplete WPs, PPs, and SLPPs in IMS as no actual finish date, Removed Block 4 (Frequency) Pilot: Frequency changed to quarterly; threshold at 15% | DELETED
27A104a | 27A1 | DELETED APR 2019 CCB | 2019-02-21 | Are ETCs generated for WPs, PPs, and SLPPs? | X = Count of incomplete WPs, PPs, and SLPPs without ETC | Y = Total count of incomplete WPs, PPs, and SLPPs | X/Y = 0% |  | 13 | A | DELETED: replaced by metric 27I101a which is essentially the same except that the new metric 27I101a traces to an EVMSIG intent statement rather than an attribute. V3.2: Changed Threshold to 0% V3.1: Removed Block 4 (Frequency) Pilot: Minor wording changes. Approved. | DELETED
10A301a | 10A3 | DELETED APR 2019 CCB | 2018-11-28 | Are PPs detail planned prior to the freeze period? | X = Count of PPs that have baseline start dates within the freeze period | Y = Total count of PPs | X/Y ≤ 10% |  | 03, 13 | A | DELETED: replaced by metric 10I101a V3.1: Change to Automated and limited to Freeze Period, Removed Block 4 (Frequency) | DELETED
06A204a | 06A2 | DELETED JAN 2019 CCB | 2018-11-27 | Are start-to-start and finish-to-finish relationships used in the schedule? | X = Count of incomplete tasks/activities & milestones in the IMS with at least one start-to-start or finish-to-finish predecessor | Y = Total count of incomplete tasks/activities & milestones | X/Y ≤ 15% |  | 11 | A | DELETED: Metrics 06A204b (dangling logic), 205a (lags), and 206a (leads) should be sufficient at identifying the misuse of SS/ FF relationship types. V3.1: Defining incomplete WPs, PPs, and SLPPs in IMS as no actual finish date, Removed Block 4 (Frequency) Pilot: Threshold change to 15% | DELETED
06A213a | 06A2 | DELETED JAN 2019 CCB | 2018-11-27 | Are activity interdependencies defined? | X = Count of discrete incomplete tasks/activities & milestones with either missing predecessors or missing successors | Y = Total count of discrete incomplete tasks/activities & milestones | X/Y ≤ 10% |  | 11 | A | DELETED: This metric is covered by metric 06A204b (Dangling Logic). V3.1: Defining incomplete WPs, PPs, and SLPPs in IMS as no actual finish date, Removed Block 4 (Frequency) Pilot: Changed threshold to 10% | DELETED
19A301a | 19A3 | DELETED NOV 2018 CCB | 2017-03-23 | Are indirect rates updated as necessary to ensure a realistic allocation of indirect costs without significant year-end adjustments? | X = Indirect rates not updated in accordance with procedures | n/a | X = 0 | A | 13, 14, 23, 24 | N | Intended to capture that the ktr has a process for updating indirect rates, and is following that process; after NOV 2018 CCB, replaced with a new 19A301a that checks whether the ACWPcum in the EVMS reconciles to the actual costs in the accounting system | DELETED
06I101a | 06I | DELETED DURING PILOT | 2017-03-23 | Are schedule margin tasks statused correctly? | X = Count of schedule margin tasks with early finish dates not equal to the baseline finish date | n/a | X = 0 | M | 11 | A | DELETED for v3.0; consider adding to CRC as a check for schedule margin/contingency process description | DELETED
07A101a | 07A1 | DELETED DURING PILOT | 2017-03-23 | Are incomplete contractual milestones and events identified in the IMS? | X = Count of incomplete contractual milestones and events that are not in the IMS | Y = Total count of incomplete contractual milestones and events | X/Y = 0% | A | 04, 06, 11 | M | DELETED for v3.0; consider attribute 07A1 during next EVMSIG review | DELETED
08A102a | 08A1 | DELETED DURING PILOT | 2017-03-23 | Does the accounting calendar align to the calendar used within the IMS? | X = Count of sampled accounting months where the beginning of period and end of period dates do not match between the accounting calendar and the IMS. | Y = Total count of sampled accounting months | X/Y = 0% | A | 02, 11, 50 | M | Adjusted test to compare accounting calendar to IMS calendar. DELETED by CCB | DELETED
21IXXXa | 21I | DELETED DURING PILOT | 2016-09-08 | Are material transfers and loans processed to ensure appropriate collection of direct costs and performance measurement? | X = Count of sampled material transfers and loans not processed correctly | Y = Total number of sampled material transfers and loans | X/Y < 10% | A | 13, 14, 29 | M | N/A | RENAMED/COMBINED
21A501a | 21A5 | DELETED DURING PILOT | 2016-06-21 | Are EVTs for material consistent with the manner in which material is planned? | X = Count of sampled material WPs with EVTs that are not consistent with the manner in which material is planned | Y = Total count of sampled material WPs | X/Y ≤ 5% | A | 03, 13, 29 | M | New test to validate that material BCWP is established in accordance with correct type of material. Check for redundancy of 10A201a and eliminate test 10A201a. | DELETED
10A101a | 10A1 | DELETED DURING PILOT | 2016-06-07 | Is performance greater than budget (BAC)? | X = BCWPCUM for WPs where BCWPCUM is greater than BAC | Y = Total BCWPCUM for all WPs | X/Y = 0% | M | 13 | A | Approved | RENAMED/COMBINED
11A102a | 11A1 | DELETED DURING PILOT | 2016-06-07 | For all CAs, does BCWSCUR for the CA equal the sum of the BCWSCUR of the WPs and PPs within the CA? | X = Sum of the absolute values of (CA BCWSCUR – sum of its WP and PP BCWSCUR) | Y = Total CA BCWSCUR | X/Y ≤ 2% | M | 13 | A | Approved | DELETED
15A201a | 15A2 | DELETED DURING PILOT | 2016-06-07 | For a recognized OTB, does the TAB reconcile to the CBB? | X = (TAB – CBB) – OTB | Y = OTB | X/Y < 0% | Q | 18, 20, 25 | M | Updated to validate OTB value | RENAMED/COMBINED
29A206a | 29A2 | DELETED DURING PILOT | 2016-05-04 | Is UB negative? | X = $ value of Format 1 UB | n/a | X >= 0 | M | 20 | A | Merged with 29A201b and deleted. | DELETED
29A207a | 29A2 | DELETED DURING PILOT | 2016-05-04 | Is MR negative? | X = $ value of Format 1 MR | n/a | X >= 0 | M | 20 | A | Merged with 29A201a and deleted. | DELETED
30A101a | 30A1 | DELETED DURING PILOT | 2016-05-04 | Are retroactive changes being made? | X = $ value of BCWSCURR where BCWSCURR < 0 (at level where budgets are established) | Y = total BCWSCURR | X/Y < 5% | M | 13 | A | Deleted | DELETED
30A101b | 30A1 | DELETED DURING PILOT | 2016-05-04 | Are retroactive changes being made? | X = $ value of BCWPCURR where BCWPCURR < 0 (at level where performance is assessed) | Y = total BCWPCURR | X/Y < 5% | M | 13 | A | Deleted | DELETED
30A101c | 30A1 | DELETED DURING PILOT | 2016-05-04 | Are retroactive changes being made? | Excluding adjustments for estimated actuals, X = $ value of ACWPCURR where ACWPCURR < 0 (at level where actuals are incurred) | Y = Excluding adjustments for estimated actuals, total ACWPCURR | X/Y < 5% | M | 13 | A | Deleted | DELETED
32A103a | 32A1 | DELETED DURING PILOT | 2016-05-04 | Does the time-phased CAP match the baseline change document(s) for budget? | X = $ of misaligned budget between baseline change document budget and CAP budget delta from prior month | Y = sum of the BAC for all measured CAs | X/Y < 5% | A | 08, 18, 43 | M | Deleted | DELETED
32A105a | 32A1 | DELETED DURING PILOT | 2016-05-04 | Are changes approved prior to the commencement of new work? | X = # of baseline change documents with approval dates after first occurrence of actuals | Y = total # of baseline changes | X/Y < 10% | A | 13, 18, 43 | M | Deleted (Already covered by 09A102a). | DELETED
24A201a | 24A2 | DELETED DURING PILOT | 2016-03-29 | Does the Root Cause Analysis and Corrective Action Plan address the variance/issue? | Manual check of Indirect VARs; sample size/frequency to be determined (25%) X = total # of RCAs that do not address variance/issue | Y = total # of CAPs | X/Y < 15% | A | 17 | M | Elements merged with 24A101a; attribute 24A2 will not be tested. | DELETED
25A101b | 25A1 | DELETED DURING PILOT | 2016-03-29 | Do BCWS, BCWP, ACWP, BAC and EAC summarize through the WBS? | X = Count of occurrences where WBS Levels (Format 1 total BCWSCUM - (sum (all BCWSCUM from Cost Tool))) ≠ 0, for every level of the WBS | Y = total # of WBS Elements in Format 1 | X/Y < 10% | M | 13, 20 | A | Merged with 25A101a and deleted. | DELETED
25A101c | 25A1 | DELETED DURING PILOT | 2016-03-29 | Do BCWS, BCWP, ACWP, BAC and EAC summarize through the WBS? | X = Count of occurrences where WBS Levels (Format 1 total BCWPCURR - (sum (all BCWPCURR from Cost Tool))) ≠ 0, for every level of the WBS | Y = total # of WBS Elements in Format 1 | X/Y < 10% | M | 13, 20 | A | Merged with 25A101a and deleted. | DELETED
25A101d | 25A1 | DELETED DURING PILOT | 2016-03-29 | Do BCWS, BCWP, ACWP, BAC and EAC summarize through the WBS? | X = Count of occurrences where WBS Levels (Format 1 total BCWPCUM - (sum (all BCWPCUM from Cost Tool))) ≠ 0, for every level of the WBS | Y = total # of WBS Elements in Format 1 | X/Y < 10% | M | 13, 20 | A | Merged with 25A101a and deleted. | DELETED
25A101e | 25A1 | DELETED DURING PILOT | 2016-03-29 | Do BCWS, BCWP, ACWP, BAC and EAC summarize through the WBS? | X = Count of occurrences where WBS Levels (Format 1 total ACWPCUM - (sum (all ACWPCUM from Cost Tool))) ≠ 0, for every level of the WBS | Y = total # of WBS Elements in Format 1 | X/Y < 10% | M | 13, 20 | A | Merged with 25A101a and deleted. | DELETED
25A101f | 25A1 | DELETED DURING PILOT | 2016-03-29 | Do BCWS, BCWP, ACWP, BAC and EAC summarize through the WBS? | X = Count of occurrences where WBS Levels (Format 1 total BAC - (sum (all BAC from Cost Tool))) ≠ 0, for every level of the WBS | Y = total # of WBS Elements in Format 1 | X/Y < 10% | M | 13, 20 | A | Merged with 25A101a and deleted. | DELETED
25A101g | 25A1 | DELETED DURING PILOT | 2016-03-29 | Do BCWS, BCWP, ACWP, BAC and EAC summarize through the WBS? | X = Count of occurrences where WBS Levels (Format 1 total EAC - (sum (all EAC from Cost Tool))) ≠ 0, for every level of the WBS | Y = total # of WBS Elements in Format 1 | X/Y < 10% | M | 13, 20 | A | Merged with 25A101a and deleted. | DELETED
25A102b | 25A1 | DELETED DURING PILOT | 2016-03-29 | Do BCWS, BCWP, ACWP, BAC and EAC summarize through the OBS? | X = Count of occurrences where OBS Levels (Format 2 total BCWSCUM - (sum (all BCWSCUM from Cost Tool))) ≠ 0, for every level of the OBS | Y = total # of OBS Elements in Format 2 or EV Cost Tool Data | X/Y < 10% | M | 13, 20 | A | Merged with 25A102a and deleted. | DELETED
25A102c | 25A1 | DELETED DURING PILOT | 2016-03-29 | Do BCWS, BCWP, ACWP, BAC and EAC summarize through the OBS? | X = Count of occurrences where OBS Levels (Format 2 total BCWPCURR - (sum (all BCWPCURR from Cost Tool))) ≠ 0, for every level of the OBS | Y = total # of OBS Elements in Format 2 or EV Cost Tool Data | X/Y < 10% | M | 13, 20 | A | Merged with 25A102a and deleted. | DELETED
25A102d | 25A1 | DELETED DURING PILOT | 2016-03-29 | Do BCWS, BCWP, ACWP, BAC and EAC summarize through the OBS? | X = Count of occurrences where OBS Levels (Format 2 total BCWPCUM - (sum (all BCWPCUM from Cost Tool))) ≠ 0, for every level of the OBS | Y = total # of OBS Elements in Format 2 or EV Cost Tool Data | X/Y < 10% | M | 13, 20 | A | Merged with 25A102a and deleted. | DELETED
25A102e | 25A1 | DELETED DURING PILOT | 2016-03-29 | Do BCWS, BCWP, ACWP, BAC and EAC summarize through the OBS? | X = Count of occurrences where OBS Levels (Format 2 total ACWPCUM - (sum (all ACWPCUM from Cost Tool))) ≠ 0, for every level of the OBS | Y = total # of OBS Elements in Format 2 or EV Cost Tool Data | X/Y < 10% | M | 13, 20 | A | Merged with 25A102a and deleted. | DELETED
25A102f | 25A1 | DELETED DURING PILOT | 2016-03-29 | Do BCWS, BCWP, ACWP, BAC and EAC summarize through the OBS? | X = Count of occurrences where OBS Levels (Format 2 total BAC - (sum (all BAC from Cost Tool))) ≠ 0, for every level of the OBS | Y = total # of OBS Elements in Format 2 or EV Cost Tool Data | X/Y < 10% | M | 13, 20 | A | Merged with 25A102a and deleted. | DELETED
25A102g | 25A1 | DELETED DURING PILOT | 2016-03-29 | Do BCWS, BCWP, ACWP, BAC and EAC summarize through the OBS? | X = Count of occurrences where OBS Levels (Format 2 total EAC - (sum (all EAC from Cost Tool))) ≠ 0, for every level of the OBS | Y = total # of OBS Elements in Format 2 or EV Cost Tool Data | X/Y < 10% | M | 13, 20 | A | Merged with 25A102a and deleted. | DELETED
26A101a | 26A1 | DELETED DURING PILOT | 2016-03-29 | Is there evidence of management decision making based on the use and analysis of EV information? | Interviews or observations (e.g., attend monthly meetings) to determine use of EV information; PM, CAM at a minimum | n/a | Pass/Fail | A | 17, 19, 20 | M | Deleted; test too subjective. | DELETED
27A201a | 27A2 | DELETED DURING PILOT | 2016-03-29 | Do EACs consider performance to date? | X = # of CAs where TCPIEAC - CPI > 0.1 for CAs that do not have ACWPCUM = 0 or ETC = 0 | Y = total # of incomplete CAs | X/Y < 25% | A | 13 | M | Merged with 27A106a and DELETED. | DELETED
27A201b | 27A2 | DELETED DURING PILOT | 2016-03-29 | Do EACs consider performance to date? | X =$ value of (VAC - CVCUM) for CAs where TCPIEAC - CPI > 0.1 for CAs that do not have ACWPCUM = 0 or ETC = 0 | Y = total $ value of ETC for incomplete CAs | X/Y < 25% | A | 13 | M | Merged with 27A106b and DELETED. | DELETED
27A201c | 27A2 | DELETED DURING PILOT | 2016-03-29 | Do EACs consider performance to date? | X = # of CAs where TCPIEAC - CPI < -0.1 for CAs that do not have ACWPCUM = 0 or ETC = 0 | Y = total # of incomplete CAs | X/Y < 25% | A | 13 | M | Merged with 27A106a and DELETED. | DELETED
27A201d | 27A2 | DELETED DURING PILOT | 2016-03-29 | Do EACs consider performance to date? | X =$ value of (VAC - CVCUM) for CAs where TCPIEAC - CPI < -0.1 for CAs that do not have ACWPCUM = 0 or ETC = 0 | Y = total $ value of ETC for incomplete CAs | X/Y < 25% | A | 13 | M | Merged with 27A106b and DELETED. | DELETED
27A202a | 27A2 | DELETED DURING PILOT | 2016-03-29 | Do EACs consider Actual costs to date? | At the CA level (at a minimum), X = ACWPCUM - (EAC - ETC) | Y = $ value of ACWPCUM | X/Y < 5% | M | 13 | A | Merged with 27A108a and DELETED. | DELETED
27A501a | 27A5 | DELETED DURING PILOT | 2016-03-29 | Are the reported EACs the basis of the latest CFSR? | X = Format 1 Most Likely EAC - CFSR EAC | n/a | X = 0 | Q | 20, 27 | M | Redundant with 27A401a; DELETED | DELETED
27A502a | 27A5 | DELETED DURING PILOT | 2016-03-29 | Does any complete work have ETC? | X = $ value of CAs (at a minimum) where ¦BCWPCUM - BAC¦ = 0 and ETC > 0 | Y = total value of CAs (at a minimum) | X/Y < 10% | M | 13 | A | Merged with 27A107a; DELETED | DELETED
16A102a | 16A1 | DELETED DURING PILOT | 2016-03-02 | Does the EVMS actual cost match the CPR ACWP? | X = EVMS cumulative actual cost - ACWPCUM on CPR Format 1 | Y = $ value of EVMS cumulative actual cost | X/Y < 5% | M | 13, 20 | A |  | DELETED
16A201a | 16A2 | DELETED DURING PILOT | 2016-03-02 | Are direct actual costs recorded on the same basis as CA/WP budgets are planned? | X = ACWPCUM for all incomplete CAs/WPs where actual costs have not been recorded on the same basis (element of cost) as budgets | Y = Total ACWPCUM for all incomplete CAs/WPs | X/Y < 5% | M | 13 | A | Revised metric up for CCB discussion | DELETED
16A401a | 16A4 | DELETED DURING PILOT | 2016-03-02 | Does the contractor have an approved Accounting System? | Manual check for approved Accounting System | n/a | Pass/Fail | A | 26 | M |  | DELETED
16A402a | 16A4 | DELETED DURING PILOT | 2016-03-02 | Does the contractor have an accepted/approved Disclosure Statement? | Manual Check to see if Disclosure Statement is approved | n/a | Pass/Fail | A | 48 | M |  | DELETED
16A501c | 16A5 | DELETED DURING PILOT | 2016-03-02 | Are non-material actual costs being recorded in concert with work performance? | X = $ value of non-material BCWPCURR where BCWPCURR > 0 and ACWPCURR = 0 | Y = non-material BCWPCURR | X/Y < 5% | M | 13 | A | Deleted and merged with 16A501b; CUM test unnecessary if CUR conducted on a monthly basis | DELETED
16A502b | 16A5 | DELETED DURING PILOT | 2016-03-02 | Are actual costs excluding material being incurred on completed work? | X = $ value of ACWPCURR for non-material CA/WP (only LOE) with ACWPCURR with BCWPCUM = BAC and BCWPCURR = 0 | Y = non-material ACWPCURR | X/Y < 25% | M | 13 | A | LOE issue moved to GL 12? | DELETED
21A302c | 21A3 | DELETED DURING PILOT | 2016-03-02 | Is material ACWP being recorded in concert with work performance? | X = $ value of material BCWPCURR where material BCWPCURR > 0 and material ACWPCURR = 0 | Y = material BCWPCURR | X/Y < 5% | M | 13 | A | Test metric addressed in 21A301a & 21A301b | DELETED
08A202a | 08A2 | DELETED DURING PILOT | 2016-01-19 | Does CA time-phased BCWS equal BAC? | X = $ value of CAs where sum of all BCWS ≠ BAC | Y = total BAC | X/Y < 10% | M | 08, 13 | A | DELETED - circular test | DELETED
08A203a | 08A2 | DELETED DURING PILOT | 2016-01-19 | Does SLPP time-phased BCWS equal BAC? | X = $ value of SLPPs where time-phased BCWS ≠ BAC | Y = total BAC | X/Y < 10% | M | 08, 13 | A | DELETED - circular test | DELETED
10A106a | 10A1 | DELETED DURING PILOT | 2016-01-19 | Do you have LOE schedule variance? | X = # of LOE WPs where (BCWPCUM - BCWSCUM) ≠ 0 | Y = total # of LOE WPs | X/Y < 10% | M | 13 | A | DELETED - similar metric developed under GL12 (12I101a) | DELETED
10A107a | 10A1 | DELETED DURING PILOT | 2016-01-19 | Does each WP/PP have an OBS assigned to it? | X = # of WPs/PPs where # of assigned OBS ≠ 1 | Y = total # of WPs/PPs | X/Y ≤ 5% | M | 13 | A | DELETED - redundant to ORG tests; site to revisit metric and resubmit | DELETED
10A108a | 10A1 | DELETED DURING PILOT | 2016-01-19 | Does each in-process WP/PP have an assigned budget value? | X = value of ACWPCUM where BAC ≤ 0 | Y = total value of ACWPCUM | X/Y ≤ 5% | M | 13 | A | DELETED - redundant test | DELETED
14A102a | 14A1 | DELETED DURING PILOT | 2016-01-19 | Does MR have no scope defined? | Manual check to ensure MR transactions do not have defined scope, X = # of MR transactions with defined scope | Y = total # of MR transactions | X/Y ≤ 20% |  | 18, 43 | M | Deleted - MR transactions tested in GL29 | DELETED
06A201a | 06A2 | DELETED DURING PILOT | 2015-12-17 | Are actual start and finish dates valid for all tasks and milestones in the IMS? | X = # of tasks and milestones with either actual start or actual finish past status date | Y = total # of tasks and milestones | X/Y < 5% | M | 11 | A | Attribute changed to A5 - metric renumbered see 06A506a | RENAMED/COMBINED
06A202a | 06A2 | DELETED DURING PILOT | 2015-12-17 | Are forecast start and finish dates valid for all tasks and milestones in the IMS? | X= # of incomplete tasks and milestones with either forecast start or forecast finish before status date | Y = total # of incomplete tasks and milestones | X/Y < 5% | M | 11 | A | Attribute changed to A5 - metric renumbered see 06A506b | RENAMED/COMBINED
06A207a | 06A2 | DELETED DURING PILOT | 2015-12-17 | Does the schedule tool produce a critical path that represents the longest total duration with the least amount of float (“Total Float”)? | X = comparison of activities on IMS identified critical path and critical path calculated using push test results Contractor to provide activities/milestone used for push test | n/a | Pass/Fail | Q | 11, 12, 45 | M | Attribute changed to A4 - renumbered see 06A401A | RENAMED/COMBINED
06A502a | 06A5 | DELETED DURING PILOT | 2015-12-17 | In the IMS, do all of the tasks with an actual start have an expected finish? | X = # of tasks with an actual start (in progress) without an expected finish date | Y = total # of tasks | X/Y < 5% | M | 11 | A |  | DELETED
06A503a | 06A5 | DELETED DURING PILOT | 2015-12-17 | When applicable, are authorized risks incorporated into the IMS? | X = # of risks (High, Moderate) with mitigation plans that do not have activities identified in the IMS | Y = total # of risks (High, moderate) with mitigation plans | X/Y < 10% | A | 03, 11, 28 | M | Attribute changed to A1 - renumbered see 06A102a | RENAMED/COMBINED
07A102a | 07A1 | DELETED DURING PILOT | 2015-12-17 | If the IMP is contractually required, is the IMP traceable to the IMS? | X = # of mismatched IMP codes | n/a | Pass/Fail | A | 10, 11, 45, 47 | M | DELETED - redundant to 07A102b | DELETED
07A102c | 07A1 | DELETED DURING PILOT | 2015-12-17 | If the IMP is contractually required, is the IMP traceable to the IMS? | X = # of IMP failures (criteria, accomplishment criteria or events) | Y = total # of incomplete activities | X/Y < 11% | A | 10, 11, 45 | M | DELETED - not a requirement | DELETED
07A103a | 07A1 | DELETED DURING PILOT | 2015-12-17 | Do EVTs trace between the IMS and Cost System? | X = # of incomplete WPs where EVT does not match between IMS and the cost system | Y = total # of incomplete WPs | X/Y < 10% | M | 11, 13 | A | DELETED - redundant to GL3 03A104a | DELETED
07A104a | 07A1 | DELETED DURING PILOT | 2015-12-17 | Is there POP alignment between the baseline IMS and contract? | Manual comparison of contract baseline start and complete dates with the IMS | n/a | X/Y = 0% | A | 06, 11 | M | Revised attribute to 06A3; added CLIN and milestone dates as options for trace. New metric ID 06A301b | RENAMED/COMBINED
01A101a | 01A1 | DELETED DURING PILOT | 2015-11-19 | Does the WBS extend to the level required by the EVM System Description or CPR/IPMR requirement? | X = Count of required WBS elements that do not extend to the level required by the EVMSD or CPR/IPMR reporting requirements | Y = Total count of lowest level WBS elements | X/Y = 0% | A | 20, 38, 46 | M | Set threshold to 0; clarified WBS test to the level of CDRL or SD . | DELETED
03A101b | 03A1 | DELETED DURING PILOT | 2015-11-19 | Is CA data (e.g. ID, budget, PoP, WBS/OBS) traceable between the system artifacts including schedule, cost data, and WAD? | X = Total $ BAC (from WAD) of incomplete CAs (at a minimum) with IMS baseline dates outside the WAD PoP | Y = Total $ BAC (from WAD) of incomplete CAs in IMS | X/Y < 10% |  | 09, 11 |  | DELETED - test measure of materiality | DELETED
03A101d | 03A1 | DELETED DURING PILOT | 2015-11-19 | Is CA data (e.g. ID, budget, PoP, WBS/OBS) traceable between the system artifacts including schedule, cost data, and WAD? | X = (Cost Tool BAC - WAD BAC) for incomplete CAs where the BAC from the WAD does not match the BAC from the Cost tool | Y = total $ BAC of incomplete CAs in the Cost tool | X/Y < 10% |  | 09, 13 |  | DELETED - test measure of materiality | DELETED
32A106a | 32A1 | DELETED DURING PILOT |  | See submittal for 29A101a | [6 empty] | Need to update so that sample is taken from the EV cost tool data and traced through change documentation. Use rewrite for 29A101a for reference; create new metric, 32A106a (?). X = Count of sampled CAs with changes to BAC without documentation. Rework required. | DELETED

## Revision History
EVMS Surveillance Metrics Revision History
Version Date | Revision Description
2019-01-28 | Updated for Nov 2018 CCB meeting results. Seven new metrics added, specific metric changes implemented, and all metrics affected by global changes thereby resulting in all metrics changing to version 3.1.
2019-02-19 | Updated to add BP number and BP4 group number columns and tabs. Assigned BP4 group numbers to the 7 new metrics resulting from the Nov 2018 CCB. Fixed X value on 03A101e to match spec sheet. Added this "Revision History" tab and "Metrics Breakdown" tab.
2019-02-21 | BP3 tab was missing three metrics.
2019-03-01 | Updated Artifact 13 description to include the phrase: "for all reporting periods from contract start and include all records..." Added Artifact 13 data element "AA BCWPCUR (monthly historical)." Updated 44 metrics to version 3.2 - includes 4 new metrics (16A501c [GP1], 16A501d [GP1], 21A302c [GP1], 21A302d [GP1]), and 2 metrics were deleted (06A204a [GP1] & 06A213a [GP1]) for a new metrics total of 139. All tabs updated accordingly.
2019-05-24 | Updated Artifact 13 data element "AA BCWPCUR (monthly historical)" to "BB BCWPCUR (monthly historical)" due to an error in duplicating the "AA" identifier with another element ("AA CA UIDs"). Added data elements: 03W - CEAC Process/Requirements (ref 27A101b), 17E Rate Variance (RV) Formula (ref 23A201a), 17F Volume Variance (VV) Formula (ref 23A201a). Changes to 46 metrics - includes 6 new metrics (08I101a [BP3&4 GP1], 08I102a [BP4 GP1], 08I103a [BP4 GP1], 10I101a [BP3&4 GP3]), 27I101a [BP3&4 GP1], 27I201a [BP3&4 GP1]),and 2 metrics were deleted (10A301a [BP4 GP3], 27A104a [BP4, GP1]) for a new metrics total of 143. All 143 metrics updated to version 3.3 even if there were no changes; updating all metrics to the newest version number will be the process going forward. Added column F for ease of identifying metrics that experienced an actual change since the most recent CCB. All tabs updated accordingly.
2019-08-31 | Changes to 105 metrics - added 1 metric (19A401a [BP4], 3 metrics were deleted (06A203a [BP3&4], 06A206a [BP3&4] and 19A301a [BP4]) for a new metrics total of 141. All 141 metrics updated to version 3.4 even if there were no changes; updating all metrics to the newest version number will be the process going forward. BP4 will no longer contain metric groups. Renamed Column D on EVMS Metrics Tracker tab from BP4 Group to GL. Deleted tabs "BP4 Group1", "BP4 Group2", "BP4 Group3", "BP4 Group4", BP4 Group5". Deleted BP4 groupings from Metrics Breakdown tab. All tabs updated accordingly.
2019-09-10 | Change to one metric, 16A501a. Updated to v3.4.1
2020-01-23 | Change to 45 Metrics. 3 Metrics deleted (10A109a, 10I101a, and 22I101a).
2020-03-26 | Changes to 06A506b, 06A506c, and 27A102a
2020-07-29 | Change to 33 metrics. 5 metrics added (27A102b, 29I402a, 29I402b, 29I402c, 29I402d)
2020-11-02 | Changes to 24 metrics as interim release (v3.6.1). Unchanged metrics remain version v3.6.
2021-03-05 | Changes to 17 metrics. One metric deleted. All metrics were updated to v4.0. Release 4.0 included changes to DECM template and updates to wording and formatting for consistency between the DECM. Tracker was updated to include new column "M" identifying any metric that requires sampling.
2021-12-13 | Changes to 31 metrics. All metrics adminstratively updated to v5.0.
2022-12-05 | Changes to 40 metrics; 1 metric DELETED (29A501b) and replaced with 1 NEW metric (29A501c); all metrics updated formatting IAW section 508 Accessability Compliance; 1 NEW Data Artifact (62 - Risk Management Process/ Plan); Artifacts 20, 22, and 46 updated to include IPMDAR Data Elements; Artifact Descriptions updated accordingly
2024-12-06 | All metric updated for section 508 Accessability Complaince. Changes to 27 metrics, 06A101a adjusted to prevent conditions where over 100% trip could occur. 01A101b removed language concerning MIL-STD 881, 26 Metrics added Assumptions.
2025-10-08 | Changed to 35 metrics; 3 metrics DELETE (03A103a, 03A103b, and 26A202a); 03A103a and 03A103b were determined to overlap with 06A301a; 26A201a was updated to include the checks of 26A202a;
2026-02-11 | Updated Revision History in DECM 08A103a