EVMS Test Metric Specification

Guideline No:

- 01

Test Metric ID:

01A101b

Test Type:

Manual

Attribute/Intent Definition:

01A1:  A single product-oriented WBS is used for a given contract and extends to the level necessary for management action.

Test Definition:

Is there a single product-oriented WBS?

Test Metric:

X = Occurrence of a WBS that is not product-oriented

Metric Threshold:

X = 0

Data Elements Required:

03 EVM System Description

03Q WBS reporting level requirements

20 IPMR/CPR/IPMDAR

20G Format 1 lowest reporting-level WBS elements/ CPD WBS

38 Contract WBS

38A Lowest reporting-level WBS elements

46 IPMR/CPR/IPMDAR CDRL

46B WBS reporting level requirements

Assumptions:

- Test is performed in accordance with IPMR/CPR/IPMDAR requirements or EVMSD, whichever is at lowest level.

Instructions:

- Review the EVMSD and IPMR/CPR/IPMDAR CDRL to ensure that  there is a single product-oriented WBS.

- If the WBS is a single product-oriented WBS (X = 0), then the metric is not out of threshold.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial CCB |  | 11/19/2015 |
| v2.0 | CCB - validated |  | 7/19/2016 |
| v2.1 | Integration – updated data elements |  | 9/8/2016 |
| RED | Minor change submitted to CCB |  | 2/28/2017 |
| v3.0 | Minor changes accepted by CCB |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | No changes – updated to v3.4 |  | 8/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Updated blk 8 DEs to align with metric steps & asms. Moved step 1 blk 10 (is not an action to perform) into blk 9 as asm 4. Merged asm 2 with step 1 as they are the same instruction. | 8, 9, 10 | 3/05/2021 |
| v5.0 | Added standard zero based sampling language to blk 9. Deleted instruction step 5 as intent met with risk assessment included in step 4. | 9, 10 | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/02/2022 |
| v7.0 | Update Test Metric, Assumptions, and Instructions Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | No changes - updated to v8.0 |  | 8/21/2025 |