EVMS Test Metric Specification

Guideline No:

- 02

Test Metric ID:

02A102a

Test Type:

Manual

Attribute/Intent Definition:

02A1:  A single organizational structure exists that contains all of the organizational elements, including major subcontractors and inter-organizational units, necessary to execute the contract.

Test Definition:

Are all major subcontractors/suppliers and intra-organizational work with an EVMS DFARS clause flow down requirement included in the OBS reporting requirements in Format 2 or CPD?

Test Metric:

X = Count of major subcontractors/suppliers and intra-organizational elements with an EVMS DFARS clause flow down requirement not identified in the OBS reporting requirements in Format 2 or CPD

Y = Total count of major subcontractors/supplier and intra-organizational elements with an EVMS DFARS clause flow down requirement

Metric Threshold:

X/Y=0%

Data Elements Required:

06 Contractual Documents

06F Subcontractor EVMS flow-down requirements

20 IPMR/CPR/IPMDAR

20Q Format 2 OBS elements/ CPD OBS

21 List of Major Subcontractors/Suppliers

21A Subcontractors/Suppliers and intra-organizational elements

Assumptions:

- None

Instructions:

- Review the contractor’s CPR/IPMR Format 2 or IPMDAR CPD OBS and list of major subcontractors/supplier & intra-organizational elements with EVMS flow down requirements.

- Identify the number of subcontractors/suppliers or intra-organizational elements requirements with an EVMS DFARS clause flow down requirement that are not reflected in the CPR/IPMR Format 2 or IPMDAR CPD OBS in accordance with reporting requirements; this is the numerator (X) of the metric.

- Identify the total number of major subcontractors/suppliers and intra-organizational elements with an EVMS DFARS clause flow down requirement; this is the denominator (Y) of the metric.

- Calculate the test metric (Block 7):  X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial CCB |  | 11/19/2015 |
| v2.0 | CCB – validated |  | 7/19/2016 |
| v2.1 | Integration – data elements updated |  | 9/8/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Attribute |  | 8/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added “/supplier” for DECM consistency. | 5, 6, 8, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Updated to include IPMDAR; updated assumptions to say “None” | 5, 6, 8, 9, 10 | 12/6/2022 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/07/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | No changes - updated to v8.0 |  | 8/21/2025 |