EVMS Test Metric Specification

Guideline No:

- 04

Test Metric ID:

04A101a

Test Type:

Manual

Attribute/Intent Definition:

04A1:  There is an indirect account organization structure with designated manager(s) with authority to implement documented processes that define resource assignment, budget establishment and control for indirect costs.

Test Definition:

Has an organizational authority been established for indirect cost management?

Test Metric:

X = Count of the functions/positions identified within the EVMSD that do not correspond with the functions/positions responsible for approval and control of indirect costs found in the organizational chart(s) or any other company documentation

Metric Threshold:

X=0

Data Elements Required:

03 EVM System Description

03R Indirect Cost Management Organization

39 Organizational Charts

39A Indirect Cost Management Organization

Assumptions:

- None

Instructions:

- Use the contractor’s organizational chart(s) or any other company documentation to verify that there is an organizational structure in which designated managers have authority to approve and manage indirect rates and control related indirect costs or expenditures.

- Compare the documentation identified in Step 1 with the company’s EVMSD. Count the number of functions/positions identified in the EVMSD that do not correspond with the functions/positions responsible for approval and control of indirect costs; this is the value (X) of the test metric.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial CCB |  | 11/19/2015 |
| v2.0 | CCB - validated |  | 8/16/2016 |
| v2.1 | Integration – updated data elements |  | 9/13/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.2 | Updated Assumptions and Instructions |  | 2/21/2019 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Attribute |  | 8/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. | 10 | 3/05/2021 |
| v5.0 | Assumptions 1 and 2 deleted. Deleted Data Elements 23 and 60 and instruction step 1 as no longer applicable with assumption updates. | 8, 9, 10 | 12/13/2021 |
| v6.0 | Updated assumptions to say “None” | 9 | 12/6/2022 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/07/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | No changes - updated to v8.0 |  | 8/21/2025 |