EVMS Test Metric Specification

Guideline No:

- 05

Test Metric ID:

05A103a

Test Type:

Automated

Attribute/Intent Definition:

05A1:  Each control account is assigned to a single organizational element directly responsible for the work identifiable to a single element of the WBS.  One or more control accounts are visible at the intersection of the WBS and responsible organizational structure.

Test Definition:

Does each control account have exactly one WBS element assigned?

Test Metric:

X = Count of CAs with more than one WBS element or no WBS elements assigned

Y = Total count of CAs

Metric Threshold:

X/Y=0%

Data Elements Required:

13 EV Cost Tool Data

13AA Control Account UIDs

13AZ WBS Elements

44 Cost Data Dictionary

Assumptions:

- Analysis is based on current month in EV Cost Tool data only.

Instructions:

- Count the number of unique control accounts in the EV Cost Tool data; this is the denominator (Y) of the test metric.

- From the list of CAs from step 1:

  - When the EV Cost Tool data WBS elements are only provided at the CA level, count the CAs with more than one WBS element or no WBS elements assigned.

  - When the EV Cost Tool data WBS elements are provided at the work package (WP) level, count the CAs that meet one or more of the below conditions.

    - WPs under a CA do not have matching WBS elements; more than one WBS condition check.

    - WBS element is not consistently applied (e.g., some WP WBS elements are populated, and others are not); more than one WBS condition check.

    - No WP under a CA have assigned WBS elements; no WBS condition check.

  - When the EV Cost Tool data WBS elements are provided separately at both the CA level and WP level, count the CAs where WBS element is not consistently applied (i.e., WBS elements do not match between levels)

- Add the results of steps 2a, 2b, and 2c as applicable, not counting any duplicative CA UIDs between the three sets; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7):  X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial CCB |  | 11/19/2015 |
| v2.0 | CCB - validated |  | 4/20/2016 |
| v2.1 | Integration – updated data elements |  | 9/13/2016 |
| v3.0 | Minor changes accepted by CCB |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Attribute |  | 8/31/2019 |
| v3.5 | Update Instructions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 44 to supplement artifact 13. Corrected capitalization for consistency. | 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/02/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | No changes - updated to v8.0 |  | 8/21/2025 |