EVMS Test Metric Specification

Guideline No:

- 06

Test Metric ID:

06A101a

Test Type:

Automated

Attribute/Intent Definition:

06A1:  The IMS reflects all authorized, time-phased discrete work, including subcontracted effort and critical and high-value material.

Test Definition:

Does each non-LOE unique WP, PP, SLPP have task(s) represented in both the IMS and EV Cost Tool?

Test Metric:

X = Count of all PPs/SLPPs and incomplete non-LOE WPs in the EV Cost Tool that are not in the IMS and count of incomplete non-LOE WPs, PPs, SLPPs in the IMS that are not in the EV Cost Tool

Y = Total count of all unique PP and SLPP, and incomplete, non-LOE WPs in the EV Cost Tool or the IMS

Metric Threshold:

X/Y = 0%

Data Elements Required:

03 EVM System Description

03V Process for LOE/discrete work decomposition

03U Guidance on EVTs

11 Integrated Master Schedule

11A Actual Finish Date

11U EVT

11AG Status Date

11AP WP/PP/SLPP UIDs

13 EV Cost Tool Data

13H BAC

13Q BCWPCUM

13AP EVT

13BA WP/PP/SLPP UIDs

13BC Cost Data Status Date

44 Cost Data Dictionary

45 IMS Data Dictionary

Assumptions:

- Status date of EV Cost Tool data is aligned with IMS status date.

- Test Metric is performed with incomplete non-LOE WPs, all PPs (GL10 – Attribute 3), and all SLPPs (GL 8 – Attribute 1).

- If BAC and BCWPCUM are within $100 (or 1 hour), then WPs/PPs/SLPPs are complete.

- Review the contractor’s System Description and determine how the M/ERP managed scope is aggregated, with the appropriate interdependencies and sequencing preserved, within the IMS.

- Incomplete WP equals at least one task/activity or milestone without an actual finish date in the IMS.

- Review EVM System Description for what work is required to be in the IMS. If the system description is silent, only work with earned value techniques defined as non-discrete or LOE may be omitted from the IMS.

Instructions:

- Identify and count all PPs/SLPPs and incomplete Non-LOE WPs in the EV Cost Tool data.

- Compare the WP/PP/SLPP unique IDs from step 1 with the IMS. Count each incomplete WP, PP, SLPP in the EV Cost Tool data that is not in the IMS.

- Identify and count all PPs/SLPPs and incomplete Non-LOE WPs in the IMS.

- Compare the WP/PP/SLPP unique IDs from step 3 with the EV Cost Tool data. Count each WP/PP/SLPP unique ID that is not in the EV Cost Tool data.

- The Y Value is the sum the unique WP/PP/SLPPs in steps 1 and 3.

- The X Value is the sum of steps 2 and 4.

- Calculate the test metric (Block 7):  X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial CCB |  | 11/19/2015 |
| v2.0 | CCB – validated |  | 4/20/2016 |
| v2.1 | Integration – data elements updated |  | 9/8/2016 |
| v3.0 | Minor changes |  | 3/23/2017 |
| v.3.1 | Minor changes, Removed Block 4 (Frequency) |  | 11/27/2018 |
| v3.2 | Updated Data Elements with EV Cost Tool Data, updated assumptions |  | 2/21/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update: Attribute, Data Elements Required, and Assumptions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v.3.6.1 | Re-defined Incomplete CA in block 11 |  | 11/02/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 45 to supplement artifact 11. | 8 & 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/01/2022 |
| v7.0 | Update Test Definition, Test Metric, Data Elements Required, Assumptions, and Instructions Update layout for Section 508 Accessibility Compliance |  | 12/06/2022 |
| v8.0 | Updated to clarify all SLPP and PP are included | 6, 9, 10 | 08/21/2025 |