EVMS Test Metric Specification

Guideline No:

- 06

Test Metric ID:

06A204b

Test Type:

Automated

Attribute/Intent Definition:

06A2:  The network schedule/IMS depicts the sequence of work (horizontal integration) and identifies the significant interdependencies that are indicative of the actual way the work is planned and accomplished.

Test Definition:

Are there open starts or finishes (“dangling logic”) in the schedule?

Test Metric:

X = Count of incomplete Non-LOE tasks/activities & milestones with open starts or finishes

Y = Total count of incomplete Non-LOE tasks/activities & milestones

Metric Threshold:

X/Y = 0%

Data Elements Required:

11 Integrated Master Schedule

11A Actual Finish Date

11G Baseline Finish Date

11J Baseline Start Date

11U EVT

11AE Predecessor (Type)

11AK Successor (Type)

11AM Task/Milestone UIDs

45 IMS Data Dictionary

Assumptions:

- An “open start” is defined as:

  - tasks/activities that contains only finish to finish, start to finish, or blanks for predecessor.

  - milestones with a blank predecessor.

- An “open finish” is defined as:

  - tasks/activities that contains only start to start, start to finish, or blanks for successor.

  - milestones with a blank successor.

- The first tasks/activities & milestones have the earliest baseline start date in the IMS and should be excluded from the open start portion of this metric.

- The last tasks/activities & milestones have the latest baseline finish date in the IMS and should be excluded from the open finish portion of this metric.

- Incomplete tasks/activities & milestones equals no actual finish date in the IMS.

- Summary tasks/activities are not included.

Instructions:

- Identify and count all incomplete Non-LOE tasks/activities & milestones in the IMS; this is the denominator (Y) of the metric.

- Identify and count all incomplete Non-LOE tasks/activities & milestones with an open start or open finish relationship as defined in assumptions 1 and 2; this is the numerator (X) of the metric.

  - Situations to investigate for task/activity predecessor

    - Only FF

    - Only SF

    - Only FF + SF

    - Blank predecessor

  - Situations to investigate for task/activity successor

    - Only SS

    - Only SF

    - Only SS + SF

    - Blank successor

  - Situation to investigate for milestone predecessor:

    - Blank predecessor

  - Situation to investigate for milestone successor:

    - Blank successor

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | New metric |  | 12/02/2015 |
| v2.0 | CCB - validated |  | 4/20/2016 |
| v2.1 | Integration – updated data elements |  | 9/13/2016 |
| RED | Minor modification |  | 3/21/2017 |
| v3.0 | Minor changes accepted by CCB |  | 3/23/2017 |
| v3.1 | Defining incomplete WPs, PPs, and SLPPs in IMS as no actual finish date, Removed Block 4 (Frequency) |  | 11/27/2018 |
| v3.2 | Reworded assumptions (open finishes and starts) & specified metric to include only discrete activities |  | 2/21/2019 |
| v3.3 | Updated “discrete” to “Non-LOE” in Blocks 7 & 12 |  | 5/24/2019 |
| v3.4 | Update: Attribute, Assumptions, and Instructions |  | 8/31/2016 |
| v3.5 | Update: Assumptions and Instructions |  | 2/22/2020 |
| v3.6 | Update: Data Elements Required and Assumptions |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 45 to supplement artifact 11. Added “milestone” in blk 10 for DECM consistency. Updated blks 9 & 10 to identify open starts & open finishes separately for milestones in order to avoid false trips. | 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/02/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | No changes - updated to v8.0 |  | 8/21/2025 |