EVMS Test Metric Specification

Guideline No:

- 06

Test Metric ID:

06A208a

Test Type:

Automated

Attribute/Intent Definition:

06A2:  The network schedule/IMS depicts the sequence of work (horizontal integration) and identifies the significant interdependencies that are indicative of the actual way the work is planned and accomplished.

Test Definition:

Do summary tasks/activities in the schedule have logic applied?

Test Metric:

X = Count of summary tasks/activities with logic applied (# predecessors > 0 or # successors > 0)

Metric Threshold:

X = 0

Data Elements Required:

11 Integrated Master Schedule

11AD Predecessors

11AJ Successors

11AL Summary Task UIDs

45 IMS Data Dictionary

Assumptions:

- If the scheduling tool does not allow summary tasks/activities, the metric is not applicable.

Instructions:

- Identify and count all summary tasks/activities with relationships (i.e., applied logic); this is the numerator (X) of the test metric.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

- For a result above the threshold, determine if the summary tasks/activities with relationships are linked to the same predecessors and successors as their subordinate (i.e., lower level) tasks/activities.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial CCB |  | 12/02/2015 |
| v2.0 | CCB - validated |  | 8/16/2016 |
| v2.1 | Integration – updated data elements |  | 9/13/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Attribute |  | 8/31/2019 |
| v3.5 | Update: Test Metric, Assumptions, and Instructions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 45 to supplement artifact 11. Added “/activities” for DECM consistency. | 5, 6, 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/02/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | No changes - updated to v8.0 |  | 8/21/2025 |