EVMS Test Metric Specification

Guideline No:

- 06

Test Metric ID:

06A209a

Test Type:

Automated

Attribute/Intent Definition:

06A2:  The network schedule/IMS depicts the sequence of work (horizontal integration) and identifies the significant interdependencies that are indicative of the actual way the work is planned and accomplished.

Test Definition:

Are schedule network constraints limited?

Test Metric:

X = Count of incomplete tasks/activities & milestones with hard constraints

Y = Total count of incomplete tasks/activities & milestones

Metric Threshold:

X/Y = 0%

Data Elements Required:

11 Integrated Master Schedule

11A Actual Finish Date

11Q Constraint Type

11AM Task/Milestone UIDs

20 IPMR/CPR/IPMDAR

45 IMS Data Dictionary

Assumptions:

- Hard constraints include constraints that restrict functioning of normal logic early and late dates.

  - MS Project: Start No Later Than, Finish No Later Than, Must Start On, and Must Finish On

  - Open Plan: Start Fixed Target and Finish Fixed Target

  - Primavera: Mandatory Start and Mandatory Finish

  - IPMDAR SPD: Start No Later Than, Finish No Later Than, Must Start On, and Must Finish On

- Incomplete tasks/activities & milestones equals no actual finish date in the IMS.

Instructions:

- Identify and count all incomplete tasks/activities and milestones in the IMS; this is the denominator (Y) of the test metric.

- Identify and count all incomplete tasks/activities and milestones with a hard constraint; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7):  X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

- For a result above the threshold, determine if there is adequate rationale/justification for the use of hard constraints.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial CCB |  | 12/02/2015 |
| v2.0 | CCB - validated |  | 4/20/2016 |
| v2.1 | Integration – updated data elements |  | 9/13/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Defining incomplete WPs, PPs, and SLPPs in IMS as no actual finish date, Removed Block 4 (Frequency) |  | 11/27/2018 |
| v3.3 | Added Data Element |  | 5/24/2019 |
| v3.4 | Update Attribute |  | 8/31/2019 |
| v3.5 | Update: Assumptions and Instructions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 45 to supplement artifact 11. | 8 & 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/02/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | Added hard constraints for IPMDAR SPD | 8, 9 | 08/21/2025 |