EVMS Test Metric Specification

Guideline No:

- 06

Test Metric ID:

06I201a

Test Type:

Manual

Attribute/Intent Definition:

06I2:  Schedule Visibility Tasks (SVTs), if used, must be separately identified and controlled to represent non-PMB tasks/activities that could impact the logic driven network, and consistently identifiable as “SVT” in the IMS.

Test Definition:

Are Schedule Visibility Tasks (SVTs) identified and controlled in the IMS?

Test Metric:

X = Count of incomplete tasks/activities and milestones that are not properly identified and controlled as SVTs in the IMS

Metric Threshold:

X = 0

Data Elements Required:

03 EVM System Description

11 Integrated Master Schedule

11A Actual Finish Date

11L BCWS (time-phasing) (If Applicable)

11AM Task/Milestone UIDs

45 IMS Data Dictionary

Assumptions:

- Incomplete tasks/activities or milestones equals no actual finish date in the IMS.

- All effort on contract, regardless of who is performing the work, is part of the PMB (e.g. subcontractor/supplier effort and material items on contract are part of the PMB and must not be labeled as SVTs; in contrast, government tasks/activities & milestones, GFE, integration tasks/activities & milestones performed on other programs/platforms but necessary for this PMB and “at risk” efforts that are not in the contract are common examples of efforts that are not part of the PMB and must be labeled as SVTs).

- SVTs do not consume resources.

Instructions:

- Determine how SVTs are used and identified in the EVMSD and IMS Data Dictionary.

- Identify and count the number of incomplete SVTs that represent scope in the PMB.

- Identify and count the number of incomplete SVTs that are not identified IAW the EVMSD and IMS Data Dictionary.

- Identify and count the number of incomplete tasks/activities & milestones that use SVT identifiers other than those determined in step 1 (common locations are in the task/activity or milestone name, element type, and other text fields).

- Identify and count the number of incomplete SVTs with budget/resources assigned.

- Add the counts from Steps 2, 3, 4, and 5 ensuring no-double counting; this is (X) of the test metric.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v3.1 | Initial CCB |  | 11/27/2018 |
| v3.3 | Added Data Elements & Assumption 2 |  | 5/24/2019 |
| v3.4 | No changes – updated to v3.4 |  | 8/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | Update: Test Metric, Data Elements Required, Assumptions, and Instructions |  | 8/30/2020 |
| v3.6.1 | Re-defined IMS incomplete (block 11). Added "/activities & milestones” in blocks 11 and 12. Updated block 10 for consistency |  | 11/02/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added “/supplier” blk 9 asm 2 for DECM consistency. Updated attribute number in blk 4 to match DECM tracker and methodology. | 4, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/02/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | No changes - updated to v8.0 |  | 8/21/2025 |