EVMS Test Metric Specification

Guideline No:

- 08

Test Metric ID:

08A101a

Test Type:

Manual

Attribute/Intent Definition:

08A1: The PMB is time-phased in alignment with the Integrated Master Schedule (IMS), with budget distributed in accordance with the accounting calendar for the authorized work scope including all control accounts and SLPPs.

Test Definition:

Is the time-phased PMB in alignment with the IMS?

Test Metric:

X = Count of sampled incomplete WPs/PPs/SLPPs in the EV Cost Tool where the time-phased budget baseline does not align with the IMS

Y = Total count of sampled incomplete WPs/PPs/SLPPs in the EV Cost Tool

Metric Threshold:

X/Y ≤ 10%

Data Elements Required:

02 Accounting/Fiscal Calendar

02B Beginning of period (BOP) dates

02C End of period (EOP) dates

11 Integrated Master Schedule

11AM Task/Activity/Milestone UIDs

11AP WP/PP/SLPP UIDs

11G Baseline Finish Date

11J Baseline Start Date

11L BCWS (time-phasing) in IMS if applicable

13 EV Cost Tool Data

13AP EVT

13BA WP/PP/SLPP UIDs

13K BAC for CA and SLPP

13M BAC for WP and PP

13Q BCWPCUM

13U BCWS (time-phasing)

44 Cost Data Dictionary

45 IMS Data Dictionary

Assumptions:

- Baseline start and finish dates are to be assessed according to Accounting/Fiscal Calendar month.

- Exact dates inclusive of the day (e.g. MM/DD/YYYY) carried in the EV Cost Tool data are not utilized for this metric.

- For discrete WPs: If BAC and BCWPCUM are within $100 (or 1 hour), then WP is complete.

- For LOE WPs: If BAC and BCWPCUM are within $100 (or 1 hour) and ETC is less than $100, then the WP is complete.

- With threshold > 0, the MIL-STD-1916 and ANSI/ASQ Z1.4 Zero Based Sampling Plan does not apply. Chosen sampling methodology must be explained. When appropriate, it is acceptable to test the entire population instead of sampling.

- Alignment between IMS and EV Cost Tool data is measured in terms of Period of Performance, gaps in time, front loaded, and back loaded.

Instructions:

- Identify a sample of incomplete WPs/PPs/SLPPs in the EV Cost Tool data that exist in both Artifact 11 and 13; this is the denominator (Y) of the test metric.

- Identify the time-phased budget baseline (BCWS) in the EV Cost Tool data for the sampled incomplete WPs/PPs/SLPPs.

- Using the sample from Step 1:

  - If associated tasks/activities have BCWS time-phasing in the IMS: Compare the EV Cost Tool data BCWS time-phasing to the IMS BCWS time-phasing.

  - If associated tasks/activities do not have BCWS time-phasing in the IMS: Compare the EV Cost Tool data BCWS time-phasing to the tasks/activities baselined in the IMS.

- Count each WP/PP/SLPP where the EV Cost Tool data time-phasing does not align to the IMS time-phasing. This is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Budgeting CCB | All | 01/19/2016 |
| v1.1 | CCB – returned for retest |  | 09/01/2016 |
| v2.1 | Updated after retest |  | 11/17/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Revised alternate test for non-resource loaded IMS, Removed Block 4 (Frequency) |  | 11/27/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Assumptions |  | 8/31/2019 |
| v3.5 | Update: Data Elements Required and Assumptions |  | 2/22/2020 |
| v3.6 | Update: Test Metric, Data Elements Required, Assumptions, and Instructions |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 44 to supplement artifact 13 & 45 to supplement artifact 11. Added “tasks/” & “data” for DECM consistency. Admin update to capitalize “Cost Tool”. Update wording in blk 10 steps 3 & 4 for clarification of intent. Added asm 4 to differentiate discrete from LOE complete. Admin update to blk 6. | 6, 8, 9, 10 | 3/05/2021 |
| v5.0 | Added Data Element 13AP | 8 | 12/13/2021 |
| v6.0 | Updated Data Element 11L to be “if applicable;” replaced “resource loaded” with “BCWS time-phasing” | 8, 10 | 12/6/2022 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/07/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | No changes - updated to v8.0 |  | 8/21/2025 |