EVMS Test Metric Specification

Guideline No:

- 08

Test Metric ID:

08A103a

Test Type:

Automated

Attribute/Intent Definition:

08A1:  The PMB is time-phased in alignment with the Integrated Master Schedule (IMS), with budget distributed in accordance with the accounting calendar for the authorized work scope including all control accounts and SLPPs.

Test Definition:

Is control account data traceable between system artifacts including schedule, cost data, and work authorization documents?

- Do the baseline dates in the IMS align with the dates in the EV Cost Tool?

Test Metric:

X = Count of incomplete WPs/PPs in the IMS where POP does not align with EV Cost Tool POP

Y = Total count of incomplete WPs/PPs in the IMS

Metric Threshold:

X/Y ≤ 0%

Data Elements Required:

11 Integrated Master Schedule

11A Actual Finish Date

11G Baseline Finish Date

11J Baseline Start Date

11U EVT

11AP WPs/PPs/SLPPs UIDs

13 EV Cost Tool Data

13U BCWS (time-phasing)

13AP EVT

13BA WP/PP/SLPP UIDs

44 Cost Data Dictionary

45 IMS Data Dictionary

Assumptions:

- Test metric is established at the WP/PP level but can be calculated at CA level if WP/PP data is not available.

- Incomplete WP/PP equals at least one task/activity or milestone without an actual finish date in the IMS.  53

- EV Cost Tool data baseline start date is determined by the first Accounting/Fiscal month of non-zero time-phased BCWS.

- EV Cost Tool data baseline finish date is determined by the last Accounting/Fiscal month of non-zero time-phased BCWS.

- Incomplete WPs/PPs in the IMS that do not have time-phased BCWS in the EV Cost Tool data are considered trips.

Instructions:

- Identify and count all incomplete WPs/PPs in the IMS; this is the denominator (Y) of the metric.

- First, compare EV Cost Tool data baseline start to the baseline start date in the IMS. Second, compare EV Cost Tool data baseline finish to the baseline finish date in the IMS.  Count each WP/PP where the baseline start date, the baseline finish date, or both dates do not align; this is the numerator (X) of the metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial Scheduling CCB |  | 12/2/2015 |
| v2.0 | CCB - validated |  | 9/1/2016 |
| v2.1 | Integration – updated data elements |  | 9/13/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Attribute |  | 08/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 45 to supplement artifact 11. | 8 & 10 | 03/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/02/2022 |
| v7.0 | Update Assumptions Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| V8.0 | Realigned DECM 03A101f from GL03 to GL08. Test Metric ID changed from 03A101f to 08A103a. |  | 08/21/2025 |