EVMS Test Metric Specification

Guideline No:

- 08

Test Metric ID:

08A201a

Test Type:

Manual

Attribute/Intent Definition:

08A2:  The time-phased budget baseline reflects the resources planned to perform the authorized work scope and only exceeds the CBB with prior customer authorization of an OTB.

Test Definition:

Was customer authorization received before reporting an OTB in the Integrated Program Management Report (IPMR)/Contract Performance Report (CPR)/ Integrated Program Management Data and Analysis Report (IPMDAR)?

Test Metric:

X = Occurrences where customer authorization was not received prior to reporting an OTB on IPMR/CPR/IPMDAR

Metric Threshold:

X = 0

Data Elements Required:

20   IPMR/CPR/IPMDAR

20E Format 1 Date of OTB/OTS/ CPD Contract Data Last OTB Date

25   Customer Approval for OTB

25A OTB Approval

Assumptions:

- If no OTB has been reported, do not perform test.

Instructions:

- If the contractor is reporting an OTB, review program documentation to verify that prior authorization for an OTB was formally received from the customer.

- If prior authorization for an OTB is formally documented, the metric is within threshold.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial Budgeting CCB | All | 1/19/2016 |
| v2.0 | CCB - validated |  | 5/17/2016 |
| v2.1 | Integration – updated data elements |  | 9/13/2016 |
| v3.0 | No change – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | No changes – updated to v3.4 |  | 8/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | Updated Step 2 block 12 |  | 08/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. | 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Updated to include IPMDAR | 5, 6, 8 | 12/6/2022 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/07/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | No changes - updated to v8.0 |  | 8/21/2025 |