EVMS Test Metric Specification

Guideline No:

- 09

Test Metric ID:

09A101a

Test Type:

Manual

Attribute/Intent Definition:

09A1:  Work authorization process/documentation identifies work scope description, budgets segregated by elements of cost (i.e., direct labor dollars/hours, material dollars, subcontract dollars, and other direct costs), and period of performance for the authorized effort.

Test Definition:

Is authorization date prior to budgeted baseline start?

Test Metric:

X = Count of sampled incomplete CAs where the EV Cost Tool baseline start date precedes the WAD authorization date (signature)

Y = Total count of sampled incomplete CAs from the EV Cost Tool

Metric Threshold:

X/Y ≤ 10%

Data Elements Required:

02 Accounting Fiscal Calendar

02A Accounting month dates

09 Work Authorization Documentation (WAD)

09A Approval Date

13 EV Cost Tool Data

13H BAC

13Q BCWPCUM

13U BCWS (time-phasing)

13AA CA UIDs

44 Cost Data Dictionary

Assumptions:

- Test metric is based on a sample of incomplete CAs.

- With threshold > 0, the MIL-STD-1916 and ANSI/ASQ Z1.4 Zero Based Sampling Plan does not apply. Chosen sampling methodology must be explained. When appropriate, it is acceptable to test the entire population instead of sampling.

- If BAC and BCWPCUM are within $100 (or 1 hour), then CA is complete.

- Baseline start dates are to be assessed according to Accounting/Fiscal Calendar month.

- EV Cost Tool data baseline start date is determined by the first instance of non-zero time-phased BCWS.

Instructions:

- Identify a sample of incomplete CAs in the EV Cost Tool data; this is the denominator (Y) of the test metric.

- Identify the baseline start dates in the EV Cost Tool data for the CAs sampled in Step 1.

- Identify the WAD authorization (i.e., signature/approval) date for each sampled CA; compare the WAD approval date to the baseline start date in the EV Cost Tool data.

- Count the number of CAs where the EV Cost Tool data baseline start date precedes the WAD authorization date; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial Budgeting CCB | All | 1/19/2016 |
| v2.0 | CCB - validated |  | 5/17/2016 |
| v2.1 | Integration – updated data elements |  | 9/13/2016 |
| v3.0 | Minor changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Updated assumptions, Removed Block 4 (Frequency) |  | 11/28/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update: Attribute, Data Elements Required, and Assumptions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added “data” & “EV Cost Tool” in for DECM consistency. Admin update to capitalize “Cost Tool”. Added data element 44 to supplement artifact 13 & data element 02. Added “or” blk 9 to correct oversight. | 6, 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/02/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | No changes - updated to v8.0 |  | 8/21/2025 |