EVMS Test Metric Specification

Guideline No:

- 09

Test Metric ID:

09A103a

Test Type:

Automated

Attribute/Intent Definition:

09A1:  Work authorization process/documentation identifies work scope description, budgets segregated by elements of cost (i.e., direct labor dollars/hours, material dollars, subcontract dollars, and other direct costs), and period of performance for the authorized effort.

Test Definition:

Are elements of cost defined/identified for each control account?

Test Metric:

X = Sum of BAC for incomplete CAs with budgets that cannot be segregated by element of cost

Y = Total BAC of incomplete CAs

Metric Threshold:

X/Y ≤ 10%

Data Elements Required:

13 EV Cost Tool Data

13AA CA UIDs

13H BAC

13Q BCWPCUM

13AJ Element of Cost

44 Cost Data Dictionary

Assumptions:

- If the element of cost segregation is at a level lower than the CA, any EOC missing at the lower level trips the CA.

- Not Segregated by element of cost includes both cost with an unassigned EOC and control accounts where BAC total cost does not equal the sum of the BAC elements of cost.

Instructions:

- Sum the total BAC for incomplete CAs; this is the denominator (Y) of the test metric. If BAC and BCWPCUM are within $100 (or 1 hour), then CA is complete.

- Identify any incomplete CAs with budgets not segregated by element of cost, and sum the BAC of those CAs; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial Budgeting CCB | All | 1/19/2016 |
| v2.0 | CCB - validated |  | 5/17/2016 |
| v2.1 | Integration – updated data elements |  | 9/13/2016 |
| RED | Major change submitted to CCB |  | 2/28/2017 |
| v3.0 | Major changes accepted by CCB |  | 3/23/2017 |
| v3.1 | Updated assumptions, Removed Block 4 (Frequency) |  | 11/28/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update: Attribute and Assumptions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Admin update to capitalize “Cost Tool”. Added “data” for DECM consistency. Updated blk 8 for DECM consistency & added data element 44 to supplement artifact 13. Added “or” blk 9 to correct oversight. | 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/02/2022 |
| v7.0 | Update Assumptions Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | Clarify missing EOC in assumptions. Moved rounding Assumption 1 to instructions Step 1 | 9, 10 | 09/22/2025 |