EVMS Test Metric Specification

Guideline No:

- 09

Test Metric ID:

09A105a

Test Type:

Manual

Attribute/Intent Definition:

09A1: Work authorization process/documentation identifies work scope description, budgets segregated by elements of cost (i.e., direct labor dollars/hours, material dollars, subcontract dollars, and other direct costs), and period of performance for the authorized effort.

Test Definition:

Is control account data traceable between system artifacts including schedule, cost data, and work authorization documents?

- Does BAC (hours or dollars) within the EV Cost Tool reconcile to the work authorization documentation (WAD)? (count)

Test Metric:

X/Y ≤ 10%

Metric Threshold:

X = Count of sampled incomplete CAs where the BAC from the WAD does not match the BAC in the EV Cost Tool data

Y = Total count of sampled incomplete CAs in the EV Cost Tool data

Data Elements Required:

09 Work Authorization Documentation (WAD)

09B BAC

13 EV Cost Tool Data

13H BAC

13Q BCWPCUM

44 Cost Data Dictionary

Assumptions:

- Test to be run independently on hours, dollars, or both.

- Test metric is based on a sample of incomplete CAs.

- With threshold > 0, the MIL-STD-1916 and ANSI/ASQ Z1.4 Zero Based Sampling Plan does not apply. Chosen sampling methodology must be explained. When appropriate, it is acceptable to test the entire population instead of sampling.

- If BAC and BCWPCUM are within $100 (or 1 hour), then CA is complete.

- If WAD and EV Cost Tool data BAC are within $100 (or 1 hour), then it is not counted as a deficiency.

Instructions:

- Identify a sample of incomplete CAs in the EV Cost Tool data; this is the denominator (Y) of the metric.

- Compare the BAC for each sampled incomplete CA in the WAD and the EV Cost Tool data.  Count each instance where the BAC values differ; this is the numerator (X) of the metric.

- Calculate the test metric (Block 7):  X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial CCB |  | 11/19/2015 |
| v2.0 | CCB - validated |  | 4/20/2016 |
| v2.1 | Integration – data elements updated |  | 9/8/2016 |
| v3.0 | Minor changes |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update: Attribute and Assumptions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Admin update to add “data” after cost tool & capitalize “Cost Tool”. Removed Pass/Fail verbiage to allow assessment of test result without assuming an automatic pass or fail. Added data element 44 to supplement artifact 13. Replaced “discrepancy” for “deficiency” to be consistent with the overarching 2303-01. | 5, 6, 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/01/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| V8.0 | Realigned DECM 03A101c from GL03 to GL 09. Test Metric ID changes from 03A101c to 09A105a. | 1, 2, 4 | 08/25/2025 |