EVMS Test Metric Specification

Guideline No:

- 09

Test Metric ID:

09A106a

Test Type:

Manual

Attribute/Intent Definition:

09A1: Work authorization process/documentation identifies work scope description, budgets segregated by elements of cost (i.e., direct labor dollars/hours, material dollars, subcontract dollars, and other direct costs), and period of performance for the authorized effort.

Test Definition:

Is control account data traceable between system artifacts including schedule, cost data, and work authorization documents?

- Do the CA baseline dates align between the WAD and the EV Cost Tool?

Test Metric:

X = Count of sampled incomplete CAs with baseline start and baseline finish dates outside the WAD POP in the EV Cost Tool data

Y = Total count of sampled incomplete CAs in the EV Cost Tool data

Metric Threshold:

X/Y ≤ 5%

Data Elements Required:

02 Accounting/Fiscal Calendar

02B Beginning of period (BOP) dates

02C End of period (EOP) dates

09 Work Authorization Documentation (WAD)

09C Baseline Finish Date

09D Baseline Start Date

13 EV Cost Tool Data

13H BAC

13Q BCWPCUM

13U BCWS (time-phasing)

13AA CA UIDs

44 Cost Data Dictionary

Assumptions:

- Test metric is based on a sample of incomplete CAs.

- With threshold > 0, the MIL-STD-1916 and ANSI/ASQ Z1.4 Zero Based Sampling Plan does not apply. Chosen sampling methodology must be explained. When appropriate, it is acceptable to test the entire population instead of sampling.

- If BAC and BCWPCUM are within $100 (or 1 hour), then CA is complete.

- A CA is counted in the numerator only once if the EV Cost Tool data dates are outside the WAD dates.

- Baseline start and finish dates are to be assessed according to Accounting/Fiscal Calendar month.

- Exact dates carried in the EV Cost Tool data are not utilized for this metric.

- EV Cost Tool data baseline start date is determined by the first Accounting/Fiscal month of non-zero time-phased BCWS.

- EV Cost Tool data baseline finish date is determined by the last Accounting/Fiscal month of non-zero time-phased BCWS.

Instructions:

- Count the sampled incomplete CAs in the EV Cost Tool data; this is the denominator (Y) of the metric.

- Compare the baseline start and the baseline finish dates for each sampled incomplete CA in the EV Cost Tool data and the WAD.  Count each CA where the baseline start, baseline finish, or both baseline dates in the EV Cost Tool data are outside the WAD POP; this is the numerator (X) of the metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial CCB |  | 11/19/2015 |
| v2.0 | CCB - validated |  | 4/20/2016 |
| v2.1 | Integration – data elements updated |  | 9/8/2016 |
| v3.0 | Minor changes accepted by CCB |  | 3/23/2017 |
| v3.1 | Updated assumptions, Removed Block 4 (Frequency) |  | 11/28/2018 |
| v3.2 | Added “Date” to Data Elements for BL Finish/Start |  | 2/21/2019 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update: Attribute, Data Elements Required, and Assumptions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Admin update to add “data” after cost tool & capitalize “Cost Tool”. Removed Pass/Fail verbiage to allow assessment of test result without assuming an automatic pass or fail. Added data element 44 to supplement artifact 13. | 5, 6, 8, 9, 10 | 03/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/01/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| V8.0 | Realigned DECM 03A101g from GL03 to GL09. Test Metric ID changes from 03A101g to 09A106a. | 1, 2, 4 | 08/21/2025 |