EVMS Test Metric Specification

Guideline No:

- 10

Test Metric ID:

10A103a

Test Type:

Automated

Attribute/Intent Definition:

10A1:  Work packages have the following characteristics:

- Represent the scope of work at the level where work is performed or aggregated.

- Are distinguishable from all other work packages.

- Are assigned to a single organizational element.

- Include scheduled start and completion dates; and as applicable, interim milestones, all of which are representative of technical accomplishment.

- Have a time-phased budget or value expressed in terms of dollars, labor hours, or other measurable units that is substantiated in terms of supporting project plans.

- Have durations that are limited to a span of time that is practical for the work scope.  Longer-duration work packages have interim objective measures, such as points of technical achievement, to enable accurate performance assessment.

- Are identified within the Integrated Master Schedule (IMS) and other supporting schedules.

Test Definition:

Are 0-100 EVTs applied to incomplete WPs with one accounting period of budget?

Test Metric:

X = Count of 0-100 EVT incomplete WPs with more than one accounting period of budget

Y = Total count of 0-100 EVT incomplete WPs

Metric Threshold:

X/Y ≤ 5%

Data Elements Required:

02 Accounting/Fiscal Calendar

02A Accounting Month Dates

13 EV Cost Tool Data

13H BAC

13Q BCWPCUM

13U BCWS (time-phasing)

13AP EVT

13BA WP/PP/SLPP UIDs

44 Cost Data Dictionary

Assumptions:

- If BAC and BCWPCUM are within $100 (or 1 hour), then WP is complete.

- Use rounding to the nearest whole number for verifying time phased BCWS.

Instructions:

- Identify and count all incomplete WPs in the EV Cost Tool data with a 0-100 EVT; this is the denominator (Y) of the test metric.

- Using the set of WPs identified in Step 1, identify and count the WPs with more than one accounting period of budget; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial Budgeting CCB | All | 1/19/2016 |
| v2.0 | CCB - validated |  | 5/17/2016 |
| v2.1 | Integration – updated data elements |  | 9/13/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Minor Changes, Removed Block 4 (Frequency) |  | 11/27/2018 |
| v3.3 | Updated Assumptions |  | 5/24/2019 |
| v3.4 | Update Attribute |  | 8/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added “data” in blk 10 for DECM consistency. Admin update to capitalize “Cost Tool”. Added data element 44 to supplement artifact 13 & updated blk 8 DE for DECM consistency. Changes (to blk 5, 6-X, 9-add asm. 3, & 10-2) covers intent of deleted 10A202a. Focuses on co-mingling of EOC to verify each WP has only one EVT. Added asm 2 blk 9 to differentiate discrete from LOE complete. | 5, 6, 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/02/2022 |
| v7.0 | Update Assumptions Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | No changes - updated to v8.0 |  | 8/21/2025 |