EVMS Test Metric Specification

Guideline No:

- 10

Test Metric ID:

10A104a

Test Type:

Automated

Attribute/Intent Definition:

10A1:  Work packages have the following characteristics:

- Represent the scope of work at the level where work is performed or aggregated.

- Are distinguishable from all other work packages.

- Are assigned to a single organizational element.

- Include scheduled start and completion dates; and as applicable, interim milestones, all of which are representative of technical accomplishment.

- Have a time-phased budget or value expressed in terms of dollars, labor hours, or other measurable units that is substantiated in terms of supporting project plans.

- Have durations that are limited to a span of time that is practical for the work scope.  Longer-duration work packages have interim objective measures, such as points of technical achievement, to enable accurate performance assessment.

- Are identified within the Integrated Master Schedule (IMS) and other supporting schedules.

Test Definition:

Are %Start-%Finish EVTs applied to incomplete WPs with two accounting periods of budget?

Test Metric:

X = Count of incomplete WPs with %Start-%Finish EVTs with more than two consecutive accounting periods of budget

Y = Total count of incomplete WPs with %Start-%Finish EVTs

Metric Threshold:

X/Y ≤ 5%

Data Elements Required:

02 Accounting/Fiscal Calendar

02A Accounting Month Dates

13 EV Cost Tool Data

13H BAC

13Q BCWPCUM

13U BCWS (time-phasing)

13AP EVT

44 Cost Data Dictionary

Assumptions:

- %Start-%Finish EVTs are inclusive of 50-50 EVTs.

- %Start-%Finish EVTs are exclusive of 0-100 EVTs.

- If BAC and BCWPCUM are within $100 (or 1 hour), then WP is complete.

- Use rounding to the nearest whole number for verifying time phased BCWS.

Instructions:

- Identify and count all incomplete WPs in the EV Cost Tool data with a %Start-%Finish EVT; this is the denominator (Y) of the test metric.

- Using the set of WPs identified in Step 1, identify and count the WPs with more than two consecutive accounting periods of budget; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial Budget CCB | All | 1/19/2016 |
| v1.1 | Edited and returned for retest |  | 6/22/2016 |
| v2.1 | Updated after retest |  | 11/17/2016 |
| v3.0 | Minor changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update: Attribute and Assumptions |  | 8/31/2019 |
| v3.5 | Update: Attribute, Test Step, Step Metric, Data Elements Required, Assumptions, and Instructions |  | 2/22/2020 |
| v3.6 | Update: Test Metric, Data Elements Required, Assumptions, and Instructions |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Updated blk 8 for consistency & added data element 44 to supplement artifact 13. | 8 &10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/02/2022 |
| v7.0 | Update Assumptions Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | No changes - updated to v8.0 |  | 8/21/2025 |