EVMS Test Metric Specification

Guideline No:

- 10

Test Metric ID:

10A110a

Test Type:

Automated/Manual

Attribute/Intent Definition:

10A1: Work packages have the following characteristics: 10A1: Include scheduled start and completion dates; and as applicable, interim milestones, all of which are representative of technical accomplishment.

Test Definition:

Is control account data traceable between system artifacts including schedule, cost data, and work authorization documents?

- Does non-LOE WP EV percent complete align between the IMS and EV Cost Tool?

Test Metric:

X = Count of non-LOE WPs in IMS where EV % complete does not match EV % complete in the EV Cost Tool data

Y = Total count of non-LOE WPs in the IMS

Metric Threshold:

X/Y = 0%

Data Elements Required:

11 Integrated Master Schedule

11T EV % complete

11U EVT

11AP WP/PP/SLPP UIDs

13 EV Cost Tool Data

13AN EV % complete

13H BCWPCUM

13Q BAC

44 Cost Data Dictionary

45 IMS Data Dictionary

Assumptions:

- If there are more than one IMS task associated with any single WP ID (many to one relationship), this metric may need to be a Manual metric (not Automated).

- PPs and SLPPs are excluded in the X and Y counts.

- This metric should only be evaluated where the contractor has an internal requirement for EV % complete in the IMS or the contractor uses the IMS to status the EV Cost Tool.

Instructions:

- Verify that the IMS status date matches the cost data status date. If the IMS status date does not match the cost data status date, this metric is out of threshold.

- Identify and count all non-LOE WPs in the IMS; this is the denominator (Y) of the metric.

- Compare the EV % complete values for each non-LOE WPs in the EV Cost Tool data with the WP EV % complete in the IMS.

  - Count each instance where the values differ by >1%.

  - Count when EV% complete is undefined in cost data. (BAC = 0)

  - Count if work package is not in the cost data. (No EV% complete)

  - Sum Steps 3.a, 3.b and 3.c This is the numerator (X) of the metric.

- Calculate the test metric (Block 7):  X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial CCB |  | 11/19/2015 |
| v2.0 | CCB - validated |  | 7/19/2016 |
| v2.1 | Integration – data elements updated |  | 9/8/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Added discrete and updated assumptions, Removed Block 4 (Frequency) |  | 11/27/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update: Attribute and Assumptions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | Update Assumptions |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Admin update to add “data” after cost tool & capitalize “Cost Tool”. Removed Pass/Fail verbiage to allow assessment of test result without assuming an automatic pass or fail. Added data elements 44 & 45 to supplement artifacts 11 & 13. Replaced “discrepancy” for “deficiency” to be consistent with the overarching 2303-01. | 5, 6, 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/01/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | Realigned DECM 03A101e from GL03 to GL10. Updated Test Metric ID from 03A101e to 10A110a. Discrete changed to non-LOE. Updated assumptions and instructions to include potential issues when EV% complete is calculated. | 1, 2, 4, 5, 6, 8, 9, 10 | 09/05/2025 |