EVMS Test Metric Specification

Guideline No:

- 10

Test Metric ID:

10A201a

Test Type:

Manual

Attribute/Intent Definition:

Intent: Each work package is established using the best method to budget and then measure its progress toward completion. The EVT is established based on how the work is planned (Budgeted Cost for Work Scheduled (BCWS)), and performance (Budgeted Cost for Work Performed (BCWP)) is earned consistent with the EVT. Based on the nature of the work contained in work packages, an appropriate EVT is identified for use in measuring work accomplishment.

10A2: Other work package planning requirements include:

- Material is segregated from other elements of cost, planned in support of the need dates for the material items, and time-phased by dollar amount suitable for the type of material category.

- Establishment of EVTs for material are consistent with the manner in which material is planned.

- Subcontract effort is identified (as applicable) and time-phased consistent with subcontractor baseline plans.

Test Definition:

Are EVTs for material consistent with the manner in which material is planned and performance claimed?

Test Metric:

X = Count of sampled in-progress material WPs with EVTs that are not consistent with the manner in which material is planned

Y = Total count of sampled in-progress material

Metric Threshold:

X/Y ≤ 10%

Data Elements Required:

03 EVM System Description

03F Permitted EVTs for Material

03A High value/critical material categorization process

13 EV Cost Tool Data

13D ACWPCUM

13AJ Element of Cost

13AK Element of Cost (Material)

13AN EV % Complete

13AP EVT

13BA WP/PP/SLPP UIDs

13BB BCWPCUR (monthly historical)

13H BAC

13Q BCWPCUM

13U BCWS (time-phasing)

29 MRP/ERP System Data

29A Material Items Issued to Contract

29C Material Need dates based on Material Category

32 Quantifiable Backup Data

32A EV % Complete

44 Cost Data Dictionary

Assumptions:

- Test metric is based on a sample of incomplete material WPs.

- Test metric is performed with material EOC focus (GL 21 – Attribute 5).

- With threshold > 0, the MIL-STD-1916 and ANSI/ASQ Z1.4 Zero Based Sampling Plan does not apply. Chosen sampling methodology must be explained. When appropriate, it is acceptable to test the entire population instead of sampling.

- For discrete WPs: If BAC and BCWPCUM are within $100 (or 1 hour), then WP is complete.

- For LOE WPs: If BAC and BCWPCUM are within $100 (or 1 hour) and ETC is less than $100, then the WP is complete.

- If sampling, sample will include in-progress Non-LOE, material WPs.

- In-progress WPs have BCWPCUM or ACWPCUM greater than $100.

- When applicable, sample must include incomplete material WPs that contain a second non-material direct element of cost.

Instructions:

- Review the EVM SD for material categories and approved EVTs for material.

- Identify a sample of in-progress material WPs (reference assumptions 2, 4, 5, and 6); this count is the denominator (Y) of the test metric.

- Using the sample from step 2:

- Set 1: Identify the assigned EVT and ensure each EVT has been assigned appropriately.  The material category, the way material budget is planned, and the selected EVT must all be in agreement.  Count the number of sampled in-progress WPs where the selected EVT is not in accordance with the EVM SD.

- Set 2:   Where the EVT permits a limited range of values, identify and count any WPs that have a BCWP that is inconsistent with the way BCWS was planned (Note: An example of an inconsistent WP would be an EVT of 0-100 with percent complete that is neither 0% nor 100%).

- Set 3: Where the EVT is % complete, identify and count any WPs that have a percent complete that cannot be substantiated by the QBD associated with the WP.

- Add Set 1, Set 2, and Set 3, not counting any duplicative UIDs between the sets (So a WP is only counted once).  This is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial Budgeting CCB | All | 1/19/2016 |
| v2.0 | CCB – validated & merged with 21A501a |  | 5/17/2016 |
| v2.1 | Integration – updated data elements |  | 9/13/2016 |
| v3.0 | Minor changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Minor Changes, Removed Block 4 (Frequency) |  | 11/27/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update: Attribute and Assumptions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 44 to supplement artifact 13. Update ensures that the analysis is focused on co-mingling of EOC to cover intent of deleted 10A202a. Also, to cover removed scope from 10A105a that verifies QBD on how performance is claimed for material. | 4, 5, 8, 9, 10 | 3/05/2021 |
| v5.0 | Added assumption 2 to reference other applicable GL attributes. Fixed assumption 1 to reference WPs vice CAs. Updated WP complete assumption to align with other metrics. | 9 | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | No changes - updated to v8.0 |  | 8/21/2025 |