EVMS Test Metric Specification

Guideline No:

- 12

Test Metric ID:

12A301a

Test Type:

Manual

Attribute/Intent Definition:

12A3: Work packages for LOE have budgets and work scope supported by sound rationale and time-phased to properly reflect when the work will be accomplished.

Test Definition:

Does the time-phasing of LOE WP budgets properly reflect when the work will be accomplished?

Test Metric:

X = Count of sampled incomplete LOE WPs where budget time-phasing does not properly reflect when the work will be accomplished

Y = Total count of sampled incomplete LOE WPs

Metric Threshold:

X/Y ≤ 10%

Data Elements Required:

13 EV Cost Tool Data

13H BAC

13Q BCWPCUM

13U BCWS (time-phasing)

13AL ETC

13AP EVT

13BA WP/PP/SLPP UIDs

44 Cost Data Dictionary

Assumptions:

- If BAC and BCWPCUM are within $100 (or 1 hour) and ETC is less than $100, then WP is complete.

- Test metric is based on a sample of incomplete LOE WPs.

- With threshold > 0, the MIL-STD-1916 and ANSI/ASQ Z1.4 Zero Based Sampling Plan does not apply. Chosen sampling methodology must be explained. When appropriate, it is acceptable to test the entire population instead of sampling.

Instructions:

- Identify a sample of incomplete WPs assigned LOE EVT; this is the denominator (Y) of the test metric.

- For each sampled WP, request the CAM(s) respond to the following questions during a live demonstration at an IBR or other Surveillance Event.  In lieu of a live demonstration, send the list of sample incomplete WPs to the contractor and ask them to provide documented rationale and justification for the time-phasing of the LOE WP.

  - What is the scope of work performed within this WP?

  - Does this LOE effort support any discrete tasks/activities?

  - What defines when this work is required to be performed?

  - How were the resource requirements determined?

- If the rationale provided for a task does not adequately address the above questions, then that WP is considered not time-phased for when the work will be accomplished.

- Count each sampled WP where the budget/work time phasing does not properly reflect the monthly resource requirements; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial CCB |  | 12/02/2015 |
| v2.0 | CCB - validated |  | 4/20/2016 |
| v2.1 | Updated after retest |  | 11/17/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Updated test steps, Removed Block 4 (Frequency) |  | 11/28/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update: Attribute and Assumptions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 44 to supplement artifact 13 & updated blk 8 DE for DECM consistency. Updated blk 9 asm. 2 from CA to WP to align with blks 6 & 10. | 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | No changes - updated to v8.0 |  | 8/21/2025 |