EVMS Test Metric Specification

Guideline No:

- 12

Test Metric ID:

12A401a

Test Type:

Automated

Attribute/Intent Definition:

12A4:  Baseline dates, budgets, and scope for work packages planned as LOE are proactively managed to avoid Inaccurate performance measurement.

Test Definition:

Does the contractor proactively manage Level of Effort (LOE) CAs/WPs to avoid inaccurate performance measurement?

Test Metric:

X = Sum of BCWPCUR of incomplete LOE CAs/WPs where BCWPCUR > 0 and ACWPCUR = 0 for the last two consecutive periods

Y = Total BCWPCUR for incomplete LOE CAs/WPs

Metric Threshold:

X/Y ≤ 5%

Data Elements Required:

13 EV Cost Tool Data

13H BAC

13Q BCWPCUM

13AA CA UIDs

13AL ETC

13AP EVT

13BA WP/PP/SLPP UIDs

13BB BCWPCUR (monthly historical)

13EB ACWPCUR (monthly historical)

44 Cost Data Dictionary

Assumptions:

- If BAC and BCWPCUM are within $100 (or 1 hour) and ETC is less than $100, then the CAs/WP is complete.

- Test is conducted at the level where actual costs are collected (CA or WP).

- Test is conducted using one Artifact 13 where data is provided for all reporting periods from contract start and include all records down to the work package level.

- If actual costs cannot be separately identified for LOE and discrete work for commingled control accounts (e.g., through cost collection below the CA level or through charge numbers segmenting costs for LOE and discrete work), then the metric does not apply.

- Use rounding to the nearest whole number for BCWPCUR and ACWPCUR.

Instructions:

- Identify total BCWPCUR for incomplete LOE CAs/WPs; this is the denominator (Y) of the test metric.

- Identify incomplete CAs/WPs where LOE BCWPCUR > 0 and ACWPCUR = 0 for the last two consecutive periods.

- Sum all BCWPCUR for the CAs/WPs identified in Step 2; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial CCB |  | 12/02/2015 |
| v2.0 | CCB - validated |  | 4/20/2016 |
| v2.1 | Updated after retest |  | 11/17/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Updated test steps, Removed Block 4 (Frequency) |  | 11/28/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update: Attribute and Assumptions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 44 to supplement artifact 13 & updated blk 8 DE for DECM consistency. Updated blk 9 asm. 2 from CA to WP to align with blks 6 & 10. | 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2022 |
| v7.0 | Update Assumptions Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | No changes - updated to v8.0 |  | 8/21/2025 |