EVMS Test Metric Specification

Guideline No:

- 12

Test Metric ID:

12I101a

Test Type:

Automated

Attribute/Intent Definition:

12I1:  The nature of LOE is such that the Budgeted Cost for Work Performed (BCWP) reflects only the passage of time during which LOE tasks/activities are planned; there is never a Schedule Variance (SV), i.e., BCWP always equals Budgeted Cost for Work Scheduled (BCWS).

Test Definition:

Do LOE WPs have schedule variances?

Test Metric:

X = Count of incomplete LOE WPs where (BCWPCUM - BCWSCUM) does not equal 0

Y = Total count of incomplete LOE WPs

Metric Threshold:

X/Y = 0%

Data Elements Required:

13 EV Cost Tool Data

13H BAC

13Q BCWPCUM

13V BCWSCUM

13AP EVT

13AL ETC

13BA WP/PP/SLPP UIDs

44 Cost Data Dictionary

Assumptions:

- If BAC and BCWPCUM are within $100 (or 1 hour) and ETC is less than $100, the WP is complete.

- Use rounding to the nearest whole number for  BCWPCUM and  BCWSCUM.

Instructions:

- Identify and count all incomplete WPs with an LOE EVT; this is the denominator (Y) of the test metric.

- Using the set of WPs identified in Step 1, identify and count all incomplete LOE WPs that have a schedule variance; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial Budgeting CCB | All | 1/19/2016 |
| v1.1 | Edited and returned for retest |  | 6/22/2016 |
| v2.1 | Updated after retest |  | 11/17/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Updated assumptions, Removed Block 4 (Frequency) |  | 11/28/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update: Attribute and Assumptions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Updated DE in blk 8 for DECM consistency. Added data element 44 to supplement artifact 13. Admin updated numbering oversight in blk 10 step 2. Updated blk 9 asm 3 to align with definition of LOE complete discussed and approved on CCB 1/20/21 to add “and ETC is less than $100”. | 8, 9, 10 | 3/05/2021 |
| v5.0 | Updated language to “non-LOE” to account for WPs that are neither LOE or Discrete. | 5,6,9,10 | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2022 |
| v7.0 | Update Assumptions Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | No changes - updated to v8.0 |  | 8/21/2025 |