EVMS Test Metric Specification

Guideline No:

- 13

Test Metric ID:

13A101a

Test Type:

Manual

Attribute/Intent Definition:

13A1: Indirect budgets are established and projected, annually at a minimum, based on published rates for each organization which has authority to incur overhead costs.

13A2: Indirect budgets are incorporated into the PMB in concert with described processes and current rates (i.e., approved, provisional, proposed).

Test Definition:

Are published indirect rates consistent with those budgeted in the EV Cost Tool?

Test Metric:

X = Count of sampled budgeted indirect rates that do not match between published rates and the budget rate table in the EV Cost Tool

Y = Total count of sampled indirect rates

Metric Threshold:

X/Y = 0%

Data Elements Required:

03 EVM System Description

03K Process for incorporating indirect rates into budgets

13 EV Cost Tool Data

13AQ Indirect rate table

18 Baseline Control Logs

18C Baseline changes involving budget distributions

18E Budget change values

23 CAS Disclosure Statement

23A Indirect cost pools

23D Process for updating and applying indirect rates

24 FPRA/FPRP (or published indirect rates)

24C Published indirect rates

43 Baseline Change Request

43D Budget change values

44 Cost Data Dictionary

Assumptions:

- Test is based on a sample of published indirect rates from separate overhead pools.

- Test metric is based on a Zero-Based Sampling Plan, per MIL-STD-1916 and ANSI/ASQ Z1.4, with an Acceptable Quality Limit (AQL) of 4.0%. When a different sampling plan is used, methodology must be explained. When appropriate, it is acceptable to test the entire population instead of sampling.

- If composite rates are used based upon approval/agreement, the composite rate will be tested in lieu of indirect rate.

Instructions:

- When reviewing the initial baseline:

- Identify a sample of published indirect rates; this is the denominator (Y) of the test metric.

- Compare the sampled budgeted indirect rates to the rate table in the EV Cost Tool data.  Count each instance where the indirect rates do not match between the published rates and the rate table; this is the numerator (X) of the test metric.

- When performing an annual review:

- Review the contractor’s procedures and processes to determine how the contractor incorporates indirect budgets into the PMB based on approved published rates at the time of the baseline change.

- Identify a sample of baseline changes involving budget distributions due to customer direction (i.e., new scope to the contract such as a contract mod, ECP, etc.) since the last indirect rate update; this is the denominator (Y) of the test metric.

- Using the sample of baseline changes identified in Step 4, verify that indirect budgets were calculated using current published indirect rates.  Count any instance where indirect budgets were not calculated using current rates; this is the numerator (X) of the test metric.

- Calculate the test metric:

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial Budgeting CCB | All | 1/19/2016 |
| v1.1 | Edited and returned for retest |  | 6/22/2016 |
| v2.1 | Updated after retest |  | 11/17/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Assumptions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Updated capitalization & added “data” in blk 10 step 2 for DECM consistency. Added data element 44 to supplement artifact 13. Updated Cost Tool capitalization in blk 5 & 6 for DECM consistency. | 5, 6, 8, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | No changes - updated to v8.0 |  | 8/21/2025 |