EVMS Test Metric Specification

Guideline No:

- 14

Test Metric ID:

14I101a

Test Type:

Manual

Attribute/Intent Definition:

14I1:  MR belonging to a major subcontractor must be incorporated into the prime contractor’s EVMS with traceability to the subcontractor’s reported MR.

Test Definition:

Is MR traceable from the subcontractor/supplier to the prime EVMS?

Test Metric:

X = Subcontractor/Supplier MR that is not traceable to the prime EVMS

Y = Subcontractor/Supplier MR

Metric Threshold:

X/Y ≤ 5%

Data Elements Required:

03 System Description

03L Process for Incorporating Subcontractor MR

06 Contractual Documents

06F Subcontractor EVMS Flow-Down Requirements

13 EV Cost Tool Data

13AV Subcontractor MR

20 IPMR/CPR/IPMDAR

20J Format 1 MR/ CPD Summary Performance MR

22 Subcontractor/Supplier IPMR/CPR/IPMDAR

22E Subcontractor/Supplier MR/ CPD Summary Performance MR

44 Cost Data Dictionary

Assumptions:

- There is EVM flow down to at least one subcontractor/supplier; metric test can be repeated for up to five subcontractors/suppliers with EVM flow down requirements.

- “Subcontractor/supplier MR” refers to the dollar value of subcontractor/supplier MR for the purposes of this metric.

Instructions:

- For each subcontractor/supplier with EVM flow down requirements, identify the dollar value of subcontractor/supplier MR; this is the denominator (Y) of the test metric.

- Identify how subcontractor/supplier MR is incorporated into the prime EVMS.  Identify the dollar value of subcontractor/supplier MR that cannot be traced to the prime EVMS; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7):  X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | New Metric | All | 1/14/16 |
| v2.0 | CCB - validated |  | 5/17/16 |
| v2.1 | Integration – updated data elements |  | 9/14/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | No changes – updated to v3.4 |  | 8/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 44 to supplement artifact 13. Added “/supplier” for DECM consistency. Updated attribute number in blk 4 to match DECM tracker and methodology. | 4, 5, 6, 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Updated to include IPMDAR | 8 | 12/6/2022 |
| v6.0 | Update layout for Section 508 Accessibility |  | 12/07/2022 |
| v7.0 | Update layout for Section 508 Accessibility |  | 12/06/2024 |
| v8.0 | No changes - updated to v8.0 |  | 8/21/2025 |