EVMS Test Metric Specification

Guideline No:

- 15

Test Metric ID:

15A101a

Test Type:

Automated

Attribute/Intent Definition:

15A1:  The sum of the control account budgets, SLPP budgets, UB, and MR reconcile and trace to the NCC plus the estimated cost of AUW.

15A2:  There is a reconciliation of the TAB to the CBB/NCC plus the estimated cost of AUW for any recognized OTB.

Test Definition:

Does Total Allocated Budget (TAB) reconcile to the sum of budgets?

Test Metric:

X = |(NCC + AUW + OTB) – (PMB + MR)|

Y = TAB

Metric Threshold:

X/Y = 0%

Data Elements Required:

13 EV Cost Tool Data

13K BAC for CAs and SLPPs

20 IPMR/CPR/IPMDAR

20J Format 1 MR/ CPD Summary Performance MR BAC (Dollars)

20N Format 1 TAB/ CPD Contract Data TAB

20P Format 1 UB/ CPD Summary Performance UB BAC (Dollars)

20AA Format 1 OTB/reprogramming budget/ CPD Reprogramming Adjustments

20Y Format 1 NCC/ CPD Contract Data NCC

20Z Format 1 AUW/ CPD Contract Data AUW

44 Cost Data Dictionary

Assumptions:

- None

Instructions:

- Identify the reported TAB using Block 8.g.14 of the IPMR/CPR Format 1. For CPD Data, the TAB is found in the Contract Data section. This is the denominator (Y) of the test metric.

- Calculate the PMB by first summing CA and SLPP budgets using EV Cost Tool data, and then adding UB using Block 8.d.14 of the IPMR/CPR Format 1. For CPD Data, UB is found in the Summary Performance section.

- Using Block 8.f.14 of the IPMR/CPR Format 1, add MR to the PMB calculated in Step 2. For CPD data, MR is found in the Summary Performance section.

- Calculate the TAB by adding NCC (using Block 5.b of the IPMR/CPR Format 1), AUW (using Block 5.c of the IPMR/CPR Format 1, if any), and OTB/reprogramming budget (using Block 8.g.13 of the IPMR/CPR Format 1, if any). When the data is in CPD format, the NCC and AUW are found in the Contract Data section. The OTB/reprogramming budget must be summed from the Reprogramming Adjustments section.

- Subtract the result in Step 3 (i.e., PMB + MR) from the TAB calculated in Step 4 and take the absolute value of the result; this is the numerator (X) of the test metric. If X ≤ $1,000, then X = $0.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial Budgeting CCB | All | 1/19/2016 |
| v2.1 | Updated at CCB |  | 11/17/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Changed to Automated, Removed Block 4 (Frequency) |  | 11/28/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Attribute |  | 8/31/2019 |
| v3.5 | Update: Test Metric and Instructions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 44 to supplement artifact 13. Replaced "discrepancy" with "deficiency" in blk 9 to be consistent with the overarching 2303-01. | 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Updated to include IPMDAR | 8, 9, 10 | 12/8/2022 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/15/2022 |
| V7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | Moved rounding assumption to instructions | 9, 10 | 9/05/2025 |