EVMS Test Metric Specification

Guideline No:

- 16

Test Metric ID:

16A301a

Test Type:

Manual

Attribute/Intent Definition:

16A3:  The EVMS uses estimated costs (estimated actuals) to account for the costs of work accomplished that have not yet had direct costs recorded in the accounting system.

Test Definition:

Are estimated actuals properly used to account for the cost of work accomplished that has not yet been recorded in the accounting system?

Test Metric:

X = Count of sampled instances of estimated actuals that are not supported/documented

Y = Total count of sampled instances of estimated actuals

Metric Threshold:

X/Y ≤ 5%

Data Elements Required:

13 EV Cost Tool Data

13E ACWPCUR

44 Cost Data Dictionary

49 Estimated Actuals Reconciliation

49A Estimated Actual Costs

49B Estimated Actual Costs (Supporting Documentation

Assumptions:

- Test metric is based on a sample of instances of estimated actuals.

- With threshold > 0, the MIL-STD-1916 and ANSI/ASQ Z1.4 Zero Based Sampling Plan does not apply. Chosen sampling methodology must be explained. When appropriate, it is acceptable to test the entire population instead of sampling.

- Test can be performed using an estimated actuals reconciliation log or an estimated actuals report from the EVMS.

Instructions:

- Identify a sample of instances of the use of estimated actuals; this sample size is the denominator (Y) of the test metric.

- Verify that the estimated actual cost (ACWP) recorded in the EVMS is supported/documented.  For each instance of estimated actuals sampled, use purchase orders/invoices, subcontractor/supplier CPR/IPMR data, and/or other documentation to substantiate/support the time phasing and amount of estimated actuals used.

- Count the instances of estimated actuals lacking support/documentation identified in Step 2; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial Approval (Original) | All | 9/14/2015 |
| v2.0 | CCB - validated |  | 6/21/2016 |
| v2.1 | Integration – updated data elements |  | 9/14/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.2 | Corrected Instruction Step 3 from “Denominator” to “Numerator” for X |  | 2/21/2019 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Assumptions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 44 to supplement artifact 13. Added “/supplier” in blk 10 step 2 for DECM consistency. | 8 & 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | No changes - updated to v8.0 |  | 8/21/2025 |