EVMS Test Metric Specification

Guideline No:

- 16

Test Metric ID:

16A501b

Test Type:

Automated

Attribute/Intent Definition:

16A5:  ACWP is recorded in the same accounting period that BCWP is earned.

16A6:  Actual costs for work accomplished are transferred to the EVMS for a valid comparison of ACWP to BCWP for the same work in the same accounting period.

Test Definition:

Is Non-Material BCWP being recorded without ACWP?

Test Metric:

X = Absolute value of Non-Material, Non-LOE BCWPCUR on incomplete CAs/WPs where Non-Material, Non-LOE BCWPCUR ≠ 0 and Non-Material, Non-LOE ACWPCUR = 0

Y = Absolute value of total Non-Material, Non-LOE BCWPCUR on incomplete CAs/WPs

Metric Threshold:

X/Y ≤ 5%

Data Elements Required:

13 EV Cost Tool Data

13AA CA UIDs

13F ACWPCUR (Non-Material)

13H BAC

13T BCWPCUR (Non-Material)

13Q BCWPCUM

13AJ Element of Cost

13AP EVT

13BA WP/PP/SLPP UIDs

44 Cost Data Dictionary

Assumptions:

- Test is conducted at the level where actual costs are collected (CA or WP).

- Includes only incomplete CAs/WPs filtered on Non-Material, Non-LOE EOCs (Material cost is tested under a separate guideline).

- If Non-Material BAC and BCWPCUM are within $100 (or 1 hour), then the CA/WP is considered complete.

- Adjustments for estimated actuals are not considered a deficiency.

- PPs are excluded from this metric when it is performed at the WP level.

- When ACWP is collected at the CA level, LOE and non-LOE are included on this metric

- Use rounding to the nearest whole number for  BCWPCUR and  ACWPCUR

Instructions:

- Filter out material EOCs, then use assumption to determine incomplete CAs/WPs.

- Sum of the absolute values of Non-Material, Non-LOE BCWPCUR on incomplete CAs/WPs; this is the denominator (Y) of the test metric.

- Identify incomplete CAs/WPs where Non-Material, Non-LOE BCWPCUR ≠ 0 and ACWPCUR = 0.

- Sum of the absolute values of all BCWPCUR for the Non-Material, Non-LOE incomplete CAs/WPs identified in Step 3; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v3.2 | New metric (approved by Jan 2019 CCB) |  | 2/21/2019 |
| v3.3 | Language Added for clarification |  | 5/24/2019 |
| v3.4 | Update: Attribute and Test Metric |  | 8/31/2019 |
| v3.5 | Update: Test Metric, Data Elements Required, Assumptions, and Instructions |  | 2/22/2020 |
| v3.6 | Update Assumptions |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Updated blk 8 for consistency & added data element 44 to supplement artifact 13. Replaced "discrepancy" with "deficiency" in blk 9 asm 4 to be consistent with the overarching 2303-01. | 8, 9, 10 | 3/05/2021 |
| v5.0 | Updated Test Metric X definition and step 3 in blk10 | 6, 10 | 12/13/2021 |
| v6.0 | Added assumption to include LOE when conducted at the CA level; corrected typo in Instructions referencing Step 2 to Step 3 | 9, 10 | 12/6/2022 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/07/2022 |
| v7.0 | Update Assumptions Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | No changes - updated to v8.0 |  | 8/21/2025 |