EVMS Test Metric Specification

Guideline No:

- 17

Test Metric ID:

17A101a

Test Type:

Manual

Attribute/Intent Definition:

17A1:  Direct cost accurately summarize from the lowest defined level through the WBS hierarchy without allocation to two or more higher level WBS elements.

Test Definition:

Does ACWPCUR summarize from the lowest defined level where actual costs are collected through the WBS hierarchy without allocation to two or more higher-level WBS elements?

Test Metric:

X = Count of occurrences where the sum of the child ACWPCUR does not equal the ACWPCUR of the parent WBS element

Y = Count of parent WBS elements

Metric Threshold:

X/Y = 0%

Data Elements Required:

13 EV Cost Tool Data

13E ACWPCUR

13AZ WBS Elements

44 Cost Data Dictionary

Assumptions:

- A “child” refers to any element that rolls up to a higher “parent” element.

- Test is conducted on all WBS levels at and above the level where actual costs are collected, the control account level at a minimum.

- When the contractor uses an off-the-shelf EVM tool set to execute a roll-up function from lowest level to highest level, DCMA or SUPSHIP will confirm that the tool set performs the calculation as an initial test only until such time as a tool set change or major upgrade occurs.

Instructions:

- Identify and count the number of parent WBS elements for which a child exists; this is the denominator (Y).

- For each parent WBS, sum the ACWPCUR of its children.

- Subtract the results of Step 2 from the parent WBS ACWPCUR.  If the difference is ≥ $100 or 1 hour, count as an occurrence.

- Repeat Steps 2 and 3 through all higher WBS levels.

- The total count of occurrences is the numerator (X).

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| BSLN | Initial Approval (Original) | All | 09/14/2015 |
| v2.0 | CCB - validated |  | 09/01/2016 |
| v2.1 | Integration – updated data elements |  | 09/14/2016 |
| v3.0 | No changes – updated to 3.0 |  | 03/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.2 | Clarified rounding error assumption |  | 2/21/2019 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Attribute |  | 8/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Updated asm 2 to clarify metric & align with the intent. Removed asm 3 as test is already manual. Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 44 to supplement artifact 13. Changed "discrepancy" to "deficiency" blk 9, asm 3 to be consistent with the overarching 2303-01. | 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | Moved rounding assumption to instructions | 9, 10 | 9/05/2025 |