EVMS Test Metric Specification

Guideline No:

- 19

Test Metric ID:

19A101a

Test Type:

Manual

Attribute/Intent Definition:

19A1:  The cost accumulation system provides for the accurate allocation of indirect costs based on documented procedures.

Test Definition:

Are published indirect rates consistent with those applied in the EV Cost Tool for actual costs?

Test Metric:

X = Count of indirect rates that do not match between published rates and the rate table in the EV Cost Tool

Y = Total count of indirect rates

Metric Threshold:

X/Y = 0%

Data Elements Required:

13 EV Cost Tool Data

13AQ Indirect Rate Table

24 FPRA/FPRP (or published indirect rates)

24C Published Indirect Rates

44 Cost Data Dictionary

Assumptions:

- This metric does not apply if indirect burdens are applied in the Accounting System.  If direct hours or labor dollars in the Accounting System are transferred to the EV Cost Tool, and indirect rates are applied in the EV Cost Tool, then this test is performed.

Instructions:

- Compare the indirect rates in the most current EV Cost Tool rate table to the most current published rates.  Count each instance where the indirect rate for actual costs does not match the published rates; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| 0 | New | All | 1/27/2016 |
| v2.0 | CCB - validated |  | 6/21/2016 |
| v2.1 | Integration – updated data elements |  | 9/14/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | No changes – updated to v3.4 |  | 8/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 44 to supplement artifact 13. Updated capitalization for DECM consistency. | 5, 6, 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | No changes - updated to v8.0 |  | 8/21/2025 |