EVMS Test Metric Specification

Guideline No:

- 21

Test Metric ID:

21A302d

Test Type:

Automated

Attribute/Intent Definition:

21A3:  ACWP is recorded in the same period that earned value is measured at the point in time most suitable for the category of material involved.

Test Definition:

Is material BCWP being recorded without ACWP?

Test Metric:

X = Absolute value of Material, Non-LOE BCWPCUM on incomplete CAs/WPs where Material, Non-LOE BCWPCUM ≠  0 and Material Non-LOE ACWPCUM = 0

Y = Absolute value of total Material, Non-LOE BCWPCUM on incomplete CAs/WPs

Metric Threshold:

X/Y ≤ 5%

Data Elements Required:

13 EV Cost Tool Data

13C ACWPCUM

13H BAC

13Q BCWPCUM

13AK Element of Cost (Material)

13AP EVT

44 Cost Data Dictionary

Assumptions:

- Test is conducted at the level where actual costs are collected (CA or WP).

- Includes only incomplete CAs/WPs filtered on Material, Non-LOE EOCs (Non-material cost is tested under a separate guideline).

- If Material BAC and BCWPCUM are within $100 (or 1 hour), then the CA/WP is considered complete.

- Adjustments for estimated actuals are not considered a deficiency.

- PPs are excluded from this metric when it is performed at the WP level.

- When ACWP is collected at the CA level, LOE and non-LOE are included on this metric.

- Use rounding to the nearest whole number for BCWPCUM (identified in block 6 and block 10: X value) and ACWPCUM.

Instructions:

- Filter out Non-Material EOCs, then use assumption 3 to determine incomplete CAs/WPs.

- Sum the absolute values of Material, Non-LOE BCWPCUM on incomplete CAs/WPs; this is the denominator (Y) of the test metric.

- Identify incomplete CAs/WPs where Material, Non-LOE BCWPCUM ≠ 0 and ACWPCUM = 0.

- Sum of the absolute values of all BCWPCUM for the Material, Non-LOE incomplete CAs/WPs identified in Step 3; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial Accounting CCB | All | 2/17/2016 |
| v2.0 | CCB - validated |  | 6/21/2016 |
| v2.1 | Integration – updated data elements |  | 9/14/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Assumptions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. | 10 | 3/05/2021 |
| v5.0 | Deleted data element 61, assumptions 3 &4, and Instruction step 1 to require metric independently of MMAS approval. | 8, 9, 10 | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2022 |
| v7.0 | Update Assumptions Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | No changes - updated to v8.0 |  | 8/21/2025 |