EVMS Test Metric Specification

Guideline No:

- 21

Test Metric ID:

21A601a

Test Type:

Manual

Attribute/Intent Definition:

21A6:  There is accountability for all material purchased for the program including material issued to control accounts, return of unused material, scrap quantity and disposition, and residual inventory.

Test Definition:

Does the contractor have the ability to account for all material purchased (e.g., material issued to control accounts, return of unused material, scrap quantity and disposition, and residual inventory)?

Test Metric:

X = Count of sampled material items issued to contract that are not accounted for

Y = Total count of sampled material items identified in BOM

Metric Threshold:

X ≤ 5%

Data Elements Required:

29 MRP/ERP System Data

29A Material Items Issued to the Contract

55 BOM

55A Material Items Issued to the Contract

Assumptions:

- Test metric is based on a sample of material items identified in the BOM.

- With threshold > 0, the MIL-STD-1916 and ANSI/ASQ Z1.4 Zero Based Sampling Plan does not apply. Chosen sampling methodology must be explained. When appropriate, it is acceptable to test the entire population instead of sampling.

Instructions:

- Review documented processes for accounting for/return of unused, scrap, and residual material.

- Identify a sample of material items that were issued to the contract based upon the bill of materials (BOM); this sample size is the denominator (Y) of the test metric.

- Track the items identified within the BOM into the purchasing system and count the number of material items that cannot be accounted for in terms of being charged to a control account, returned to inventory as unused material, scrapped, or moved to a residual inventory account; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial Accounting CCB | All | 2/17/2016 |
| v2.0 | CCB - validated |  | 6/21/2016 |
| v2.1 | Integration – updated data elements |  | 9/14/2016 |
| v3.0 | No changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Assumptions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. | 10 | 3/05/2021 |
| v5.0 | Deleted data element 61, assumptions 3 &4, and Instruction step 1 to require metric independently of MMAS approval. | 8, 9, 10 | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | No changes - updated to v8.0 |  | 8/21/2025 |