EVMS Test Metric Specification

Guideline No:

- 22

Test Metric ID:

22A101a

Test Type:

Manual

Attribute/Intent Definition:

22A1:  Schedule and cost variances are calculated within the EVMS at the control account level (at a minimum) and other levels as necessary.

Test Definition:

Are there cost and schedule variance calculations at the control account level (at a minimum)?

Test Metric:

X = Count of sampled incomplete control accounts without correct variance calculations

Y = Total count of sampled incomplete control accounts

Metric Threshold:

X/Y = 0%

Data Elements Required:

13 EV Cost Tool Data

13AA CA UIDs

13AD Cumulative Cost Variance

13AE Cumulative Schedule Variance

13AF Current Cost Variance

13AG Current Schedule Variance

13AY Variance at Complete

13J BAC for CA

13Q BCWPCUM

44 Cost Data Dictionary

52 EVMS Analysis Tool Data

52A Cumulative Cost Variance

52B Cumulative Schedule Variance

52C Current Cost Variance

52D Current Schedule Variance

52E Variance at Complete

Assumptions:

- Test metric is based on a sample of incomplete CAs without correct variance calculations.

- If BAC and BCWPCUM are within $100 (or 1 hour), then CA is complete.

- Test metric is based on a Zero Based Sampling Plan, per MIL-STD-1916 and ANSI/ASQ Z1.4, with an Acceptable Quality Limit (AQL) of 4.0%. When a different sampling plan is used, methodology must be explained. When appropriate, it is acceptable to test the entire population instead of sampling.

- The EV Cost Tool Database either contains fields for variances, or the contractor can demonstrate that it calculates variances using EVMS Analysis Tool Data at least monthly.

- When the contractor uses an off-the-shelf EVM tool set to calculate variances, DCMA or SUPSHIP will confirm that the tool set performs the calculation as an initial test only until such time as a tool set change or major upgrade occurs.

Instructions:

- Identify a sample of incomplete control accounts using the EV Cost Tool Data; this is the denominator (Y) of the test metric.

- Verify that the EV Cost Tool Data includes current and cumulative Cost Variance (CV), current and cumulative Schedule Variance (SV), and Variance At Complete (VAC) data at the CA level.  Count the CAs that do not have all of these variances calculated correctly (current and cumulative); this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial AMR CCB | All | 03/29/2016 |
| v2.0 | CCB - validated |  | 07/19/2016 |
| v2.1 | Integration – updated data elements |  | 09/14/2016 |
| v3.0 | No changes – updated to 3.0 |  | 03/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.2 | SUPSHIP added as an organization that can validate tool set in Assumption #2 |  | 2/21/2019 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Assumptions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Change formatting per CCB 10/8/2020 – delete blocks & update blk numbering. Add data element 44 & updated data elements to supplement artifact 13 in blk 8. Change "validate" to "confirm" in blk 9 (if we agree to language stating "validate tool", we strive away from our scope of evaluating the EVMS and into tool validation). Add asm 2 to establish “complete" for consistency between DECMs. Added “incomplete” in blks 6 & 10 for clarification. | 6, 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | No changes - updated to v8.0 |  | 8/21/2025 |