EVMS Test Metric Specification

Guideline No:

- 23

Test Metric ID:

23A101a

Test Type:

Manual

Attribute/Intent Definition:

23A1:  Schedule and cost variances are identified and analyzed at control account and summary level.

Test Definition:

Are required VARs being generated for control accounts and SLPPs that exceed established internal thresholds?

Test Metric:

X = Count of incomplete control accounts and SLPPs missing VARs where required

Y = Total count of incomplete control accounts and SLPPs requiring VARs

Metric Threshold:

X/Y ≤ 2%

Data Elements Required:

03 EVM System Description

03P Variance Analysis Thresholds

13 EV Cost Tool Data

13H BAC

13Q BCWPCUM

13AA CA UIDs

13AD Cumulative Cost Variance

13AE Cumulative Schedule Variance

13AF Current Cost Variance

13AG Current Schedule Variance

13AY Variance at Complete

13BA WP/PP/SLPP UIDs

15 Internal Variance Analysis Thresholds

15A Internal Variance Analysis Thresholds

16 Internal Variance Analysis Reports (VARs)

16A VARs

44 Cost Data Dictionary

Assumptions:

- A single control account may potentially breach 5 separate thresholds – current period schedule variance, current period cost variance, cumulative schedule variance, cumulative cost variance, variance at complete.

- An SLPP may potentially breach only a single threshold – variance at complete.

- Multiple missing VARs in the same control account are only counted as a single deficiency.

- If BAC and BCWPCUM are within $100 (or 1 hour), then the CA is complete.

Instructions:

- Review contractor EVM system description and/or program documentation to identify internal variance analysis thresholds for cost, schedule and variance at complete (VAC) variances.

- Using EV Cost Tool data, count the total number of incomplete control accounts and SLPPs that require VARs based upon the established internal variance analysis thresholds; this is the denominator (Y) of the metric.

- Count the number of control accounts and SLPPs that breach the internal variance analysis thresholds that do not have all required VARs completed; this is the numerator (X) of the metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial AMR CCB | All | 03/29/2016 |
| v2.0 | CCB - validated |  | 07/19/2016 |
| v2.1 | Integration – updated data elements |  | 09/14/2016 |
| RED | Minor change submitted to CCB |  | 02/28/2017 |
| v3.0 | Minor changes accepted by CCB |  | 03/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | Added SLPP into the test step, assumptions and instructions |  | 5/24/2019 |
| v3.4 | No changes – updated to v3.4 |  | 8/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 44 to supplement artifact 13. Replaced "discrepancy" with "deficiency" - to be consistent with the overarching 2303-01. | 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2022 |
| V7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | No changes - updated to v8.0 |  | 8/21/2025 |