EVMS Test Metric Specification

Guideline No:

- 25

Test Metric ID:

25A101a

Test Type:

Manual

Attribute/Intent Definition:

25A1: Performance measurement data and variance analysis are summarized from control accounts (at a minimum) through WBS and organization structure hierarchies to the contract level for program management analysis purposes.

Test Definition:

Do BCWS, BCWP, ACWP, BAC and EAC summarize through the WBS?

Test Metric:

X = Count of occurrences where the sum of the child {*} does not equal the {*} of the parent WBS element, where {*} equals:

- BCWSCUR

- BCWSCUM

- BCWPCUR

- BCWPCUM

- ACWPCUM

- BAC

- EAC

Y = Total count of parent WBS elements

Metric Threshold:

X/Y = 0%

Data Elements Required:

13 EV Cost Tool Data

13C ACWPCUM

13H BAC

13Q BCWPCUM

13S BCWPCUR

13V BCWSCUM

13X BCWSCUR

13AH EAC

13AZ WBS Elements

44 Cost Data Dictionary

Assumptions:

- Test is conducted on all data elements listed in Block 7.

- A “child” refers to any element that rolls up to a higher “parent” element.

- Test is conducted on all WBS levels at and above the level where actual costs are collected, the control account level at a minimum.

- Summarization of ACWPCUR through the WBS is tested under Guideline 17.

- When the contractor uses an off-the-shelf EVM tool set to execute a roll-up function from lowest level to highest level, DCMA or SUPSHIP will confirm that the tool set performs the calculation as an initial test only until such time as a tool set change or major upgrade occurs.

Instructions:

- For each {*}, identify and count the number of parent WBS elements for which a child exists; this is the denominator (Y).

- For each parent WBS, sum the corresponding {*} of its children.

- Subtract the results of Step 2 from the parent WBS corresponding {*}.  If the difference i s ≥ $100 or 1 hour , count as an occurrence.

- Repeat Steps 2 and 3 through all higher WBS levels.

- The total count of occurrences is the numerator (X).

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial AMR CCB | All | 03/29/2016 |
| v2.0 | CCB - validated |  | 09/01/2016 |
| v2.1 | Integration – updated data elements |  | 09/14/2016 |
| v3.0 | No changes – updated to 3.0 |  | 03/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.2 | Clarified rounding error assumption |  | 2/21/2019 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Attribute |  | 8/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blks 4, 9, 13, & 14 & updated blk numbering & wording. Removed Pass/Fail verbiage to allow assessment of test result without assuming an automatic pass or fail. Added data elements 44 to supplement artifact 13. Remove redundant asm 7. Update asm 6 verbiage regarding “enterprise-level” tool for clarity. Replace "discrepancies" to "deficiencies" to be consistent with the overarching 2303-01. | 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/05/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | Moved rounding assumption to instructions | 9, 10 | 9/05/2025 |