EVMS Test Metric Specification

Guideline No:

- 25

Test Metric ID:

25A201a

Test Type:

Manual

Attribute/Intent Definition:

25A2: The data elements reconcile between internal and external reports.

Test Definition:

Is subcontractor/supplier data aligned with and traceable through the prime system?

•	Do the subcontractor/supplier EVM data elements reconcile to the prime EV Cost Tool?

Test Metric:

X = The sampled BAC value of the incomplete subcontractor/supplier CAs where a data element (BCWP, BCWS, ACWP, BAC) from the subcontractor's/supplier’s IPMR/CPR/IMPDAR cannot be reconciled to the prime EV Cost Tool

Y = Sum of sampled BAC for CA element tested

Metric Threshold:

X/Y ≤ 5%

Data Elements Required:

13 EV Cost Tool Data

13AA CA UIDs

13C ACWPCUM

13E ACWPCUR

13H BAC

13Q BCWPCUM

13S BCWPCUR

13V BCWSCUM

13X BCWSCUR

22 Subcontractor/Supplier IPMR/CPR/IPMDAR

22A ACWPCUM/ CPD Summary Performance

22B BAC/ CPD Summary Performance

22C BCWPCUM/ CPD Summary Performance

22D BCWSCUM/ CPD Summary Performance

22F ACWPCUR/ CPD ACWP (To Date)

22G BCWPCUR/ CPD BCWP (To Date)

22H BCWSCUR/ CPD BCWS (To Date)

44 Cost Data Dictionary

Assumptions:

- Test metric is based on a sample of incomplete CAs.

- With threshold > 0, the MIL-STD-1916 and ANSI/ASQ Z1.4 Zero Based Sampling Plan does not apply. Chosen sampling methodology must be explained. When appropriate, it is acceptable to test the entire population instead of sampling.

- If BAC and BCWPCUM are within $100 (or 1 hour), then CA is complete.

- EVM data elements include current and cumulative values of BCWS, BCWP, ACWP, and BAC.

- Test to be run independently on dollars, hours, or both.

- Test applies only to subcontractors/suppliers with EVMS reporting requirements.

Instructions:

- Sum the BAC values for the sampled incomplete subcontractor/supplier CAs; this is the denominator (Y) of the metric.

- For all CAs identified in Step 1, compare the EVM data elements reported by the subcontractor/supplier to the corresponding values recorded in the prime contractor’s EV Cost Tool data.

- Sum the control account BAC values for each control account with at least one mismatched data element.  The corresponding sum is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial CCB |  | 11/19/2015 |
| v2.0 | CCB - validated |  | 4/20/2016 |
| v2.1 | Integration – updated data elements |  | 9/13/2016 |
| v3.0 | Minor changes |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.2 | Added Complete CA definition in Assumptions |  | 2/21/2019 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | No changes – updated to v3.4 |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | Update Test Metric |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Updated blk 8 for consistency & added data element 44 to supplement artifact 13. Corrected admin errors & added “/supplier” for DECM consistency. Updated blk 6-X & 10 instruction 1 to align with asm 1 blk 9 to say “incomplete” vs “open” CAs. | 5, 6, 8, 9 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Updated to include IPMDAR | 6, 8 | 12/6/2022 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/07/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| V8.0 | Realigned from Guideline 3 to Guideline 25. Test Metric ID changed from 03A102a to 25A201a. | 1, 2, 4 | 08/21/2025 |