EVMS Test Metric Specification

Guideline No:

- 26

Test Metric ID:

26A201a

Test Type:

Manual

Attribute/Intent Definition:

26A2:  Corrective actions, based on variances, are managed and tracked to resolution and closure.

Test Definition:

Are corrective actions properly managed and tracked?

Test Metric:

X = Count of VARs with corrective actions that are missing or not properly recorded

Y = Total count of VARs with corrective actions

Metric Threshold:

X/Y ≤ 10%

Data Elements Required:

19 Corrective Action Log/Documentation

19A Corrective Action Log Entries

19B Corrective Action Log Status Date

19C Estimated Completion Dates (Open Corrective Actions)

20 IPMR/CPR/IPMDAR

20V Format 5/ Performance Narrative Report VARs Requiring Corrective Actions

Assumptions:

- If no corrective action log exists, the contractor must demonstrate how management tracks corrective actions to closure (e.g., through management action plans, review briefings, or the risk register).

Instructions:

- Using the IPMR/CPR Format 5 or IPMDAR Performance Narrative Report, count the VARs with corrective actions (which may include multiple steps within the corrective actions); this is the denominator (Y) of the test metric.

- Identify and count the number of VARs with corrective actions that are missing or not properly recorded in the Corrective Action Log using the following elements:

  - Identification of the person responsible for each action

  - The current status (open/closed)

  - For open actions, a due date which is after the status date

  - For closed actions, a completion date that is on or before the status date

  - A description of the action that is traceable to the VAR, and

  - Traceability to internal control account level variance analysis, this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial AMR CCB | All | 03/26/2016 |
| v2.0 | CCB - validated |  | 07/19/2016 |
| v2.1 | Integration – updated data elements |  | 09/14/2016 |
| v3.0 | No changes – updated to 3.0 |  | 03/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | No changes – updated to v3.4 |  | 8/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. | 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Updated to include IPMDAR | 8, 10 | 12/6/2022 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/07/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | Incorporated checking for ECD in the past from DECM 26A201b and deleted that DECM. Threshold lowered to 10%. | 5, 6, 9, 10 | 08/21/2025 |