EVMS Test Metric Specification

Guideline No:

- 27

Test Metric ID:

27A101a

Test Type:

Manual

Attribute/Intent Definition:

27A1:  A properly maintained control account EAC is regularly adjusted to reflect program progress, as well as scope and schedule changes. This is supported by timely updates at the work package, planning package, or lower levels, based on modified resource requirements.

Test Definition:

Are comprehensive EACs completed at least annually?

Test Metric:

X = 0 if the contract performed a comprehensive EAC (CEAC) within the past year (at a minimum).

X = 1 if a CEAC has not been performed within the past year.

Metric Threshold:

X = 0

Data Elements Required:

33 Comprehensive EAC Documentation

33A CEAC Commencement and Completion Dates

Assumptions:

- New contracts less than one year from the start of EV reporting are exempt from this metric.

Instructions:

- For the contract, review CEAC documentation and identify the commencement and completion dates of the most recent CEAC. If the most recent CEAC was not completed within the past year (at a minimum),  X=1.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial AMR CCB | All | 03/26/2016 |
| v2.0 | CCB - validated |  | 07/19/2016 |
| v2.1 | Integration – updated data elements |  | 09/14/2016 |
| v3.0 | No changes – updated to 3.0 |  | 03/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Attribute |  | 8/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | Update Assumptions |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. | 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Metric adjusted to review a single contract | 6, 7, 8, 9, 10 | 12/6/2022 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/07/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | No changes - updated to v8.0 |  | 8/21/2025 |