EVMS Test Metric Specification

Guideline No:

- 27

Test Metric ID:

27A103a

Test Type:

Automated

Attribute/Intent Definition:

27A1:  A properly maintained control account EAC is regularly adjusted to reflect program progress, as well as scope and schedule changes.  This is supported by timely updates at the work package, planning package, or lower levels, based on modified resource requirements.

Test Definition:

Do EACs exist at the control account level?

Test Metric:

X = Count of incomplete CAs with zero, missing, or negative EACs

Y = Total count of incomplete CAs

Metric Threshold:

X/Y = 0%

Data Elements Required:

13 EV Cost Tool Data

13H BAC

13Q BCWPCUM

13AA CA UIDs

13AH EAC

44 Cost Data Dictionary

Assumptions:

- If BAC and BCWPCUM are within $100 (or 1 hour), then CA is complete.

- Use rounding to the nearest whole number for EAC.

Instructions:

- Count the total number of incomplete control accounts; this is the denominator (Y) of the test metric.

- Count the total number of incomplete control accounts with zero, missing, or negative EAC; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial AMR CCB | All | 03/26/2016 |
| v2.0 | CCB - validated |  | 07/19/2016 |
| v2.1 | Integration – updated data elements |  | 09/14/2016 |
| v3.0 | No changes – updated to 3.0 |  | 03/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Attribute |  | 8/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | Update Assumptions |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. | 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Metric adjusted to review a single contract | 6, 7, 8, 9, 10 | 12/6/2022 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/07/2022 |
| v7.0 | Update Assumptions Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | No changes - updated to v8.0 |  | 8/21/2025 |