EVMS Test Metric Specification

Guideline No:

- 27

Test Metric ID:

27A105a

Test Type:

Automated

Attribute/Intent Definition:

27A1:  A properly maintained control account EAC is regularly adjusted to reflect program progress, as well as scope and schedule changes. This is supported by timely updates at the work package, planning package, or lower levels, based on modified resource requirements.

Test Definition:

Is ACWPCUM greater than EAC?

Test Metric:

X = Count of CAs/WPs where ACWPCUM > EAC

Y = Total count of CAs/WPs

Metric Threshold:

X/Y = 0%

Data Elements Required:

13 EV Cost Tool Data

13C ACWPCUM

13AA CA UIDs

13AH EAC

13BA WP/PP/SLPP UIDs

44 Cost Data Dictionary

Assumptions:

- Test is conducted at the level where actual costs are collected (CA or WP).

- PPs are excluded from this metric when it is performed at the WP level.

Instructions:

- Identify and count the total number of CAs/WPs; this is the denominator (Y) of the test metric.

- Identify and count CAs/WPs where ACWPCUM - EAC ≤ $100 or 1 hour; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial AMR CCB | All | 03/26/2016 |
| v2.0 | CCB - validated |  | 07/19/2016 |
| v2.1 | Integration – updated data elements |  | 09/14/2016 |
| v3.0 | No changes – updated to 3.0 |  | 03/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.2 | Clarified rounding error assumption |  | 2/21/2019 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update: Attribute and Metric Threshold |  | 8/31/2019 |
| v3.5 | Update: Test Metric, Metric Threshold, Assumptions, and Instructions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 44 to supplement artifact 13. Replaced "discrepancy" with "deficiency" in blk 9 asm 2 to be consistent with the overarching 2303-01. | 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/05/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | Moved rounding assumption to instructions | 9, 10 | 9/22/2025 |