EVMS Test Metric Specification

Guideline No:

- 27

Test Metric ID:

27A106a

Test Type:

Automated

Attribute/Intent Definition:

27A1:  A properly maintained control account EAC is regularly adjusted to reflect program progress, as well as scope and schedule changes. This is supported by timely updates at the work package, planning package, or lower levels, based on modified resource requirements.

Test Definition:

Do EACs consider performance to date?

Test Metric:

X = Count of CAs that are ≥ 15% and ≤ 95% complete where |TCPIEAC – CPICUM| > 0.1

Y = Total count of CAs that are ≥ 15% and ≤ 95% complete

Metric Threshold:

X/Y ≤ 25%

Data Elements Required:

13 EV Cost Tool Data

13C ACWPCUM

13H BAC

13Q BCWPCUM

13AA CA UIDs

13AC CPICUM (Derived)

13AH EAC

13AN EV % Complete

13AW TCPIEAC (Derived)

44 Cost Data Dictionary

Assumptions:

- Test only includes CAs that are ≥ 15% and ≤ 95% complete to avoid skewed CPI and TCPI values.

- TCPIEAC = (BAC – BCWPCUM) / (EAC – ACWPCUM)

- CPICUM = BCWPCUM / ACWPCUM

- CAs with ACWPCUM = 0 are excluded from the numerator. If a CA is ≥ 15% complete and ACWPCUM = 0, then an investigation is warranted.

Instructions:

- Identify and count all CAs that are ≥ 15% and ≤ 95% complete; this is the denominator (Y) of the test metric.

- For each incomplete CA, calculate TCPIEAC – CPICUM. Count all occurrences where the absolute value of TCPIEAC – CPICUM is greater than 0.1; this is the numerator (X) of the metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

- If the result is not within the threshold, follow-up with the contractor is necessary to verify EAC substantiation for CAs outside tolerance.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial AMR CCB | All | 03/26/2016 |
| v2.0 | CCB - validated |  | 07/19/2016 |
| v2.1 | Integration – updated data elements |  | 09/14/2016 |
| v3.0 | No changes – updated to 3.0 |  | 03/23/2017 |
| v3.1 | Updated assumptions, Removed Block 4 (Frequency) |  | 11/28/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update: Attribute, Test Metric, and Instructions |  | 8/31/2019 |
| v3.5 | Update: Assumptions and Instructions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 44 to supplement artifact 13. | 8 & 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/05/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | No changes - updated to v8.0 |  | 8/21/2025 |