EVMS Test Metric Specification

Guideline No:

- 27

Test Metric ID:

27A401a

Test Type:

Manual

Attribute/Intent Definition:

27A4:  Projected risks in the program EAC are substantiated by the risk and opportunity management process or the Program Manager’s assessment.

27A5:  Contractor’s externally reported EAC and internal EAC reconcile and have clear traceability based on the identified risks and opportunities or other identified factors.

Test Definition:

Is the program EAC substantiated from the risk and opportunity management process and/or the Program Manager’s assessment?

Test Metric:

X = Occurrence of a program EAC not substantiated with risks/opportunities and/or Program Manager’s assessment per the system description and risk management process

Metric Threshold:

X = 0

Data Elements Required:

03 EVM System Description

03M Requirements for EAC Risk/Opportunity Incorporation

13 EV Cost Tool Data

13AH EAC (or EAC = 13AL ETC + 13C ACWPCUM + 13AX UB)

20 IPMR/CPR/IPMDAR

20F Format 1 EACs (Best, Worst, Most Likely) / CPD Contract Data Management EAC - Most Likely

20H LRE/ CPD Summary Performance PMB EAC (Dollars)

20T Format 5 EAC Rationale/ Performance Narrative Report EAC Rationale

28 Risks & Opportunities Log/Register

28B Factored Risks/Opportunities

44 Cost Data Dictionary

62 Risk Management Process/ Plan

Assumptions:

- None

Instructions:

- Review the contractor’s IPMR/CPR/IPMDAR and EV Cost Tool data. Perform the following tests to determine if the program EAC (most likely) includes the impact of the program’s risks/opportunities or Program Manager’s assessment, and if the included risks/opportunities or Program Manager’s assessment are identified in the IPMR/CPR Format 5 or IPMDAR Performance Narrative Report:

  - Use IPMR/CPR Format 1 (Block 6.c.1) or CPD Contract Data Management EAC - Most Likely to identify the most likely EAC. Verify that the IPMR/CPR Format 5 or IPMDAR Performance Narrative Report includes risks and opportunities in the most likely EAC as required by the system description; if not documented as required by the system description, then this counts against the test metric (X=1).

  - Compare the most likely EAC and the LRE/EAC, which is IPMR/CPR Format 1 Column 15, Block 8.e or IPMDAR CPD Summary Performance PMB EAC (Dollars). If they are different, verify that IPMR/CPR Format 5 or IPMDAR Performance Narrative Report includes risks and opportunities in the most likely EAC as required by the system description; if not documented as required by the system description, then this counts against the test metric (X=1).

  - Use EV Cost Tool data to compare the internal EAC at the program level to the externally reported LRE/EAC. If the difference is ≥ $1,000, then this counts against the test metric (X=1).

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial AMR CCB | All | 03/26/2016 |
| v2.0 | CCB - validated |  | 07/19/2016 |
| v2.1 | Integration – updated data elements |  | 09/14/2016 |
| RED | Major changes accepted by CCB |  | 02/28/2017 |
| v3.0 | Major changes incorporated – updated to 3.0 |  | 03/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update: Attribute, Data Elements Required, Assumptions, and Instructions |  | 8/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 44 to supplement artifact 13. Replaced "discrepancy" with "deficiency" in blk 9 to be consistent with the overarching 2303-01. | 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Added Data Element 62; updated to include IPMDAR | 8, 9, 10 | 12/7/2022 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/15/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | Moved rounding assumption to instructions | 9, 10 | 9/05/2025 |