EVMS Test Metric Specification

Guideline No:

- 27

Test Metric ID:

27I201a

Test Type:

Automated

Attribute/Intent Definition:

27I2:  The program manager or designated manager should review, and update as needed, the EAC for Undistributed Budget (UB) and SLPPs considering factors such as current program rate performance and identified risks.

Test Definition:

Are EACs reviewed and updated as needed for UB and SLPPs?

Test Metric:

X = Count of UB and SLPPs where BAC ≠ EAC or EAC is negative

Metric Threshold:

X = 0

Data Elements Required:

13 EV Cost Tool Data

13H BAC

13AH EAC

13AX UB

13BA WP/PP/SLPP UIDs

20 IPMR/CPR/IPMDAR

20P Format 1 UB/ CPD Summary Performance UB

44 Cost Data Dictionary

Assumptions:

- Use rounding to the nearest whole number for BAC and EAC.

Instructions:

- Count the total number of instances of UB and SLPPs where BAC ≠ EAC or EAC is negative; this is the value (X) of the test metric.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

- If the result is not within the threshold, follow-up with the contractor is necessary to verify EAC substantiation for cases where UB or SLPP BAC ≠ EAC.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial AMR CCB | All | 03/26/2016 |
| v2.0 | CCB - validated |  | 07/19/2016 |
| v2.1 | Integration – updated data elements |  | 09/14/2016 |
| RED | Major changes accepted by CCB |  | 02/28/2017 |
| v3.0 | Major changes incorporated – updated to 3.0 |  | 03/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update: Attribute, Data Elements Required, Assumptions, and Instructions |  | 8/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 44 to supplement artifact 13. Replaced "discrepancy" with "deficiency" in blk 9 to be consistent with the overarching 2303-01. | 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Added Data Element 62; updated to include IPMDAR | 8, 9, 10 | 12/7/2022 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/15/2022 |
| v7.0 | Update Assumptions Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | No changes - updated to v8.0 |  | 8/21/2025 |