EVMS Test Metric Specification

Guideline No:

- 29

Test Metric ID:

29A101a

Test Type:

Manual

Attribute/Intent Definition:

29A1:  Currently authorized work/scope budget relationship is reconcilable to the prior work/scope budget relationship.

Test Definition:

Do current budgets reconcile to prior budgets through the documented changes?

Test Metric:

X = Count of sampled CAs where prior period CA BAC does not reconcile with current period CA BAC through change documentation

Y = Total count of sampled CAs with budget changes within the past 12 months

Metric Threshold:

X/Y = 0%

Data Elements Required:

13 EV Cost Tool Data

13J BAC for CA (current and prior month)

41 Budget Log

41E Current/Previous CA BAC

43 Baseline Change Request

43D Budget Change Values

44 Cost Data Dictionary

Assumptions:

- Test metric is based on a sample of control accounts with budget changes within the last 12 months.

- Test metric is based on a Zero Based Sampling Plan, per MIL-STD-1916 and ANSI/ASQ Z1.4, with an Acceptable Quality Limit (AQL) of 4.0%. When a different sampling plan is used, methodology must be explained. When appropriate, it is acceptable to test the entire population instead of sampling.

Instructions:

- Use the EV Cost Tool data to identify a sample of control accounts with CA BAC changes within the past 12 months; this sample size is the denominator (Y) of the test metric.

- Reconcile changes identified in Step 1 between the identified and previous month using the budget log and associated BCRs.

- Count the number of CAs that contain one or more BAC changes in Step 2 that do not reconcile within $100 or 1 hour; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| BSLN | Initial Approval (Original) | All | 09/14/2015 |
| v1.0 Rev 1 | Block 7: revised definition of X and Y metrics; Block 8: lowered threshold from 20% to zero; Block 10: added EV Cost Tool data; Block 12: revised instruction steps 1 through 3. | Blocks 7, 8, 10, 12 | 08/02/2016 |
| v2.0 | CCB - validated |  | 09/01/2016 |
| v2.1 | Integration – updated data elements |  | 09/14/2016 |
| v3.0 | No changes – updated to 3.0 |  | 03/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.2 | Clarified rounding error assumption |  | 2/21/2019 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Assumptions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Replaced "discrepancy" with "deficiency" in blk 9 as 3 to be consistent with the overarching 2303-01. Added data element 44 to supplement artifact 13. | 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/05/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | Moved rounding assumption to instructions | 9, 10 | 9/05/2025 |