EVMS Test Metric Specification

Guideline No:

- 30

Test Metric ID:

30A101f

Test Type:

Automated

Attribute/Intent Definition:

30A1:  A change control process exists that controls retroactive changes to previously recorded values for BCWS, BCWP, or ACWP, including approval and explanation.

Test Definition:

Are retroactive changes being made to cumulative ACWP?

Test Metric:

X = Sum ACWPCUM for all CAs/WPs where (reporting period ACWPCUM - reporting period ACWPCUR) ≠ prior period ACWPCUM

Y = Total ACWPCUM for all CAs/WPs

Metric Threshold:

X/Y ≤ 5%

Data Elements Required:

13 EV Cost Tool Data

13D ACWPCUM (current and prior reporting period)

13E ACWPCUR

13AA CA UIDs

13AP EVT

13BA WP/PP/SLPP UIDs

44 Cost Data Dictionary

Assumptions:

- Test is conducted at the level where actual costs are collected (CA or WP).

- PPs and SLPPs are not included.

Instructions:

- Sum ACWPCUM for all CAs/WPs in the EV Cost Tool data; this is the denominator (Y) of the test metric.

- Identify and sum ACWPCUM for all CAs/WPs where (current period ACWPCUM - current period ACWPCUR) ≠ prior period ACWPCUM; this is the numerator (X) of the test metric. If X ≤ $100, then X = 0.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| BSLN | Initial Approval (Original) | All | 09/14/2015 |
| v2.0 | CCB - validated |  | 08/16/2016 |
| v2.1 | Integration – updated data elements |  | 09/14/2016 |
| v3.0 | No changes – updated to 3.0 |  | 03/23/2017 |
| v3.1 | Changed from count to sum and updated assumptions, Removed Block 4 (Frequency) |  | 11/28/2018 |
| v3.2 | Added “CAs” to align with Block 11 assumption referencing the test to be conducted at the level at which actual costs are collected. |  | 2/21/2019 |
| v3.3 | Added Assumption 4 for clarification |  | 5/24/2019 |
| v3.4 | No changes – updated to v3.4 |  | 8/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 44 to supplement artifact 13 & updated data elements in blk 8. Replaced "discrepancies" with "deficiencies" to be consistent with the overarching 2303-01. Deleted unnecessary asm 1 blk 9. Updated blk 3. | 3, 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/05/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | Moved assumption into instruction to clarify where step rounding error was applied. | 9, 10 | 08/21/2025 |