EVMS Test Metric Specification

Guideline No:

- 31

Test Metric ID:

31A101a

Test Type:

Manual

Attribute/Intent Definition:

31A1:  Contractual budget values (CBB or TAB) are only revised through contractual authorization.

Test Definition:

Do all CBB or TAB changes in the baseline control log have approved contractual documentation prior to incorporation?

Test Metric:

X = Count of sampled CBB/TAB changes that do not have contractual authorization prior to incorporation

Y = Total count of sampled CBB/TAB changes

Metric Threshold:

X/Y = 0%

Data Elements Required:

06 Contractual Documents

06G Contractual Mods (Authorization Dates)

41 Budget Log

41B CBB/TAB Changes (Effective Dates)

Assumptions:

- Test metric is based on a sample of CBB/TAB changes from the CBB/budget log.

- Test metric is based on a Zero Based Sampling Plan, per MIL-STD-1916 and ANSI/ASQ Z1.4, with an Acceptable Quality Limit (AQL) of 4.0%. When a different sampling plan is used, methodology must be explained. When appropriate, it is acceptable to test the entire population instead of sampling.

Instructions:

- Select a sample of CBB/TAB changes from the CBB/budget log; this is the denominator (Y) of the test metric.

- Verify that all sampled CBB/TAB changes can be traced to contractual modification and/or customer authorization, and that authorization dates precede incorporation into the CBB/TAB.

- Identify and count any CBB/TAB changes that do not fulfill the criteria in Step 2; this is the numerator (X) of the test metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| BSLN | Initial Approval (Original) | All | 09/14/2015 |
| v2.0 | CCB - validated |  | 08/16/2016 |
| v2.1 | Integration – updated data elements |  | 09/14/2016 |
| v3.0 | No changes – updated to v3.0 |  | 03/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Assumptions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. | 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/05/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | No changes - updated to v8.0 |  | 8/21/2025 |