EVMS Test Metric Specification

Guideline No:

- 32

Test Metric ID:

32A101b

Test Type:

Manual

Attribute/Intent Definition:

32A1:  Timely and authorized changes incorporated into the PMB are properly documented and traceable throughout the system in accordance with procedures.

Test Definition:

Do the authorized budget changes in the change logs trace to the baseline change documentation?

Test Metric:

X = Sum of the budget change values from sampled baseline log changes that do not trace to the baseline change documentation IAW contractor procedures

Y = Total sum of the sampled budget change values from the baseline change log

Metric Threshold:

X/Y ≤ 5%

Data Elements Required:

18 Baseline Change Logs

18B Baseline Changes (selected)

18E Budget Change Values

43 Baseline Change Request

43D Budget Change Values

Assumptions:

- Test metric is based on a sample of baseline change values.

- With threshold > 0, the MIL-STD-1916 and ANSI/ASQ Z1.4 Zero Based Sampling Plan does not apply. Chosen sampling methodology must be explained. When appropriate, it is acceptable to test the entire population instead of sampling.

Instructions:

- Select a sample of baseline changes from the baseline control log and sum the budget; this is the denominator (Y) of the metric.

- From the sample of baseline changes in Step 1, sum the budget change values that do not trace to the baseline change documentation in accordance with contractor procedures; this is the numerator (X) of the metric.

- Calculate the test metric (Block 7): X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| NEW | Initial | All | 03/02/2016 |
| v2.0 | CCB - validated |  | 08/16/2016 |
| v2.1 | Integration – updated data elements |  | 09/14/2016 |
| v3.0 | No changes – updated to 3.0 |  | 03/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | Update Instructions |  | 8/31/2019 |
| v3.5 | Update Assumptions |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. | 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/05/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | No changes - updated to v8.0 |  | 8/21/2025 |