EVMS Test Metric Specification

Guideline No:

- 06

Test Metric ID:

06A506b

Test Type:

Automated

Attribute/Intent Definition:

06A5:  The schedule provides baseline, forecast, and actual dates.

Test Definition:

Are forecast start and finish dates representative of the remaining work for all incomplete tasks/activities & milestones in the IMS?

Test Metric:

X = Count of incomplete tasks/activities & milestones with either forecast start or forecast finish on or before the status date

Metric Threshold:

X = 0

Data Elements Required:

11 Integrated Master Schedule

11A Actual Finish Date

11C Actual Start Date

11V Forecast Finish Date

11W Forecast Start Date

11AG Status Date

11AM Task/Activity/Milestone UIDs

45 IMS Data Dictionary

Assumptions:

- A task/activity or milestone where both forecast start and forecast finish dates are before the status date is only counted as a single deficiency.

- Incomplete tasks/activities or milestones equals no actual finish date in the IMS.

Instructions:

- Identify the status date of the IMS.

- Identify and count all un-started (no actual start date) tasks/activities & milestones with forecast start dates on or before the status date.

- Identify and count all incomplete tasks/activities & milestones with forecast finish dates on or before the status date.

- Add the results from Steps 2 and 3 and subtract any tasks/activities & milestones that have both a forecast start date and forecast finish date before the status date (to avoid double counting); this is the value (X) of the metric.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial CCB |  | 12/02/2015 |
| v2.0 | CCB - validated |  | 4/20/2016 |
| v2.1 | Integration – updated data elements |  | 9/13/2016 |
| RED | Major change accepted by CCB |  | 2/28/2017 |
| v3.0 | Minor changes – updated to 3.0 |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | Actual Start Date/Finish Date added to Data Elements |  | 5/24/2019 |
| v3.4 | No changes – updated to v3.4 |  | 8/31/2019 |
| v3.5 | Update: Test Metric, Assumptions, and Instructions |  | 2/22/2020 |
| v3.5.1 | Update: Test Metric, Assumptions, and Instructions |  | 4/08/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Added data element 45 to supplement artifact 11. Add “task” & “milestone” in blks 9 & 10 for DECM consistency. Replaced "discrepancy" for "deficiency" - to be consistent with the overarching 2303-01. | 8, 9, 10 | 3/05/2021 |
| v5.0 | No changes – updated to v5.0 |  | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/02/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |
| v8.0 | Updated to include on or before status date | 5, 6, 10 | 08/21/2025 |