EVMS Test Metric Specification

Guideline No:

- 01

Test Metric ID:

01A201a

Test Type:

Manual

Attribute/Intent Definition:

01A2:  The WBS includes all contract work including the work scope performed by subcontractors and any revisions resulting from authorized changes and modifications.

Test Definition:

Are contract work scope (SOW) requirements included in the WBS?

Test Metric:

X = Count of sampled SOW paragraphs identifying scope that are not in the WBS

Y = Total count of sampled SOW paragraphs identifying scope

Metric Threshold:

X/Y = 0%

Data Elements Required:

04 Contract Statement of Work

04B SOW paragraphs

05 Contract Work Breakdown Structure Dictionary

05A SOW references

06 Contractual Documents

06H Contractual mods adding/removing scope

09 Work Authorization Documentation (WAD)

09G Scope description

38 Contract WBS

59 RAM

Assumptions:

- Contract work scope to be determined by contractual requirements (formal SOW, SOO, build spec, etc.).

- Test metric is based on a Zero Based Sampling Plan, per MIL-STD-1916 and ANSI/ASQ Z1.4, with an Acceptable Quality Limit (AQL) of 4.0%. When a different sampling plan is used, methodology must be explained. When appropriate, it is acceptable to test the entire population instead of sampling.

- Trace limited to no lower than Control Account level.

- The contractor is expected to be able to demonstrate a correlation between contract work scope requirements (e.g., SOW) and the WBS (to include the latest contract documents).  Methods of demonstration could include mapping through the WBS dictionary, WAD documentation, or RAM in accordance with the EVM system description.

Instructions:

- For recent contractual (external) changes, determine sample set of SOW paragraphs that are directly affected by the change. The number of sampled SOW paragraphs is the denominator (Y) of the test metric.

- Verify that the sampled SOW paragraphs are included in the contractor’s WBS using the applicable contractor documentation.  Count the number of SOW paragraphs in the sample that are not included in the contractor’s WBS.  This number is the numerator (X) of the test metric.

- Calculate the test metric (Block 7):  X divided by Y.

- Use block 7 as an indicator in the overall Risk Assessment to determine if further evaluation is warranted.

Configuration Summary:

| Rev Number | Detailed Description of Change | Sections Affected | Spec Sheet Date |
| --- | --- | --- | --- |
| v1.0 | Initial CCB |  | 11/19/2015 |
| v2.0 | CCB - validated |  | 7/19/2016 |
| v2.1 | Integration – updated data elements |  | 9/8/2016 |
| RED | Minor change submitted to CCB |  | 2/28/2017 |
| v3.0 | Minor changes accepted by CCB |  | 3/23/2017 |
| v3.1 | Removed Block 4 (Frequency) |  | 12/19/2018 |
| v3.3 | No changes – updated to v3.3 |  | 5/24/2019 |
| v3.4 | No changes – updated to v3.4 |  | 8/31/2019 |
| v3.5 | No changes – updated to v3.5 |  | 2/22/2020 |
| v3.6 | No changes – updated to v3.6 |  | 8/30/2020 |
| v4.0 | Changed Metric Template to delete old blocks 4, 9, 13, & 14 & updated block numbering & wording. Removed Pass/Fail verbiage to allow assessment of test results case by case. Updated blk 8 DEs to align with metric steps & asms. Moved step 1 blk 10 (is not an action to perform) into blk 9 as asm 4. Merged asm 2 with step 1 as they are the same instruction. | 8, 9, 10 | 3/05/2021 |
| v5.0 | Added standard zero based sampling language to blk 9. Deleted instruction step 5 as intent met with risk assessment included in step 4. | 9, 10 | 12/13/2021 |
| v6.0 | Update layout for Section 508 Accessibility Compliance |  | 12/02/2022 |
| v7.0 | Update layout for Section 508 Accessibility Compliance |  | 12/06/2024 |